## Prog Loc
Contract Number | Division | County | TIP# | Tier | Route | Location Description | Contract Amount | Estimate Number | Length | Contractor | Federal Aid Number | NCDOT Contact | NCDOT Contact No | Letting Date | Work Began Date | Completion Date | Revised Completion Date | Construction Progress | Completion Percent | Latest Payment Thru | Latest Payment Date
C203567 | 5 | Durham | U-3308 | Regional | NC-55 | NC-55 (ALSTON AVE) FROM NC-147 (BUCK DEAN FREEWAY) TO NORTH OF US-70BUS/NC-98 (HOLLOWAY ST). | 39756916.81 | 112 | 1.134 miles | ZACHRY CONSTRUCTION CORPORATION | STP-55(20) | James M. Nordan, PE | 9193174760 | 2016-07-19 | 2016-10-05 | 2020-03-30 | 2024-09-30 | 94.74% | 94.74% | 2026-04-15 | 2026-04-24 08:10
C204027 | 10 | Mecklenburg | I-5746C | Statewide | I-277 | I-277 (BROOKSHIRE FRWY) FROM BRIDGE DECK OVER 10TH STREET TO BRIDGE DECK OVER JOHNSON STREET AND BRIDGE DECKS OVER I-77. | 25985000 | 49 | 1.33 miles | AMERICAN CIVIL CONSTRUCTORS WEST COAST LLC | NHPIM-0277(19) | Yanwei Ma | 7048475006 | 2021-10-19 | 2022-04-08 | 2024-10-01 | 2024-10-30 | 86.26% | 86.26% | 2026-04-22 | 2026-05-13 08:10
C204070 | 2 | Pitt | U-5606 | Subregional | SR-1598 | SR-1598 (DICKINSON AVE) FROM NC-11 TO SR-1610 (READE CR). | 15747596.21 | 44 | 1.344 miles | FSC II LLC DBA FRED SMITH COMPANY | STP-1598(3) | Jason B. Beasley | 2524392970 | 2022-03-15 | 2022-06-02 | 2027-03-03 | 2027-10-16 | 87.72% | 87.72% | 2026-04-30 | 2026-05-07 10:10
C204110 | 6 | Cumberland | U-2519BA, U-2519BB | Statewide | I-295 | FAYETTEVILLE OUTER LOOP FROM SOUTH OF SR-1003 (CAMDEN ROAD) TO SOUTH OF US-401. | 151850000 | 50 | 5.293 miles | BRANCH CIVIL INC | NHF00100(024) | Donavon Hunt | 9103640608 | 2022-06-21 | 2022-08-01 | 2027-01-28 |  | 91.23% | 91.23% | 2026-04-27 | 2026-05-07 10:10
C204123 | 3 | Brunswick | R-5021 | Regional | NC-211 | NC-211 FROM SR-1500 (MIDWAY RD) TO NC-87. | 217260048.6 | 53 | 7.244 miles | BARNHILL CONTRACTING CO | STP-0211(021) | Joshua T. Pratt | 9103989100 | 2021-12-07 | 2022-01-28 | 2027-03-30 | 2028-01-07 | 68.24% | 68.24% | 2026-04-15 | 2026-04-30 09:10
C204150 | 7 | Guilford | B-5353, U-5896 | None | US-29 | US-29/US-70/I-85 BUSINESS, SR-1009 (S MAIN ST) IN HIGH POINT AND BRIDGE #147 OVER US-311 ON US-29/US-70/I-85 BUSINESS. | 25325396.73 | 49 | 0.784 miles | BOGGS CONTRACTING INC | STATE FUNDED | Leland J. Barber, PE | 3364877080 | 2022-02-15 | 2022-04-23 | 2025-02-28 | 2025-06-19 | 65.31% | 65.31% | 2026-05-07 | 2026-05-19 08:10
C204157 | 5 | Wake | U-2719, U-4437 | None | I-440 | GRADE SEPARATION-BERYL RD AT NORFOLK SOUTHERN/NC RR/CSX & NC-54 AT SR-1664; I-440/US-1-S OF SR-1313 TO N OF SR-1728. | 346200000 | 89 | 6.5 miles | THE LANE CONSTRUCTION CORPORATION | STBG-0054(031) | Niklaus C. Winkler | 9197339499 | 2018-10-02 | 2018-10-29 | 2023-07-31 | 2024-10-31 | 93.92% | 93.92% | 2026-03-31 | 2026-05-07 10:10
C204202 | 14 | Henderson |  | Statewide | I-26 | I-26/US-74 WEST BOUND LANES AND EAST BOUND LANES OVER GREEN RIVER. | 26970631.21 | 60 | 0.743 miles | FLATIRON DRAGADOS CONSTRUCTORS INC | STATE FUNDED | Patrick A. Eubanks | 8288917911 | 2021-03-16 | 2021-06-04 | 2024-12-12 | 2026-08-09 | 88.39% | 88.39% | 2026-04-22 | 2026-04-27 08:10
C204204 | 5 | Wake | P-5720 | Subregional | SR-2006 | GRADE SEPARATION OF SR-2006 (DURANT ROAD) OVER CSX S LINE RA ILROAD IN RALEIGH. | 18881899.14 | 18 | 0.677 miles | BLYTHE CONSTRUCTION INC | STATE FUNDED | David B. Moore | 9192204600 | 2024-06-18 | 2024-11-04 | 2027-04-30 | 2028-06-15 | 42.32% | 42.32% | 2026-04-30 | 2026-05-20 09:10
C204208 | 11 | Surry | B-5527 | Statewide | US-52 | BRIDGES #122 AND #126 OVER TOMS CREEK ON US-52. | 13065361.82 | 21 | 0.448 miles | SMITH-ROWE, LLC | STATE FUNDED | Benjamin D. Whitaker | 3368354241 | 2024-04-16 | 2024-09-09 | 2027-12-28 | 2028-01-13 | 66.34% | 66.34% | 2026-04-30 | 2026-05-19 08:10
C204210 | 1 | Northampton | R-2582A | Statewide | US-158 | US-158/NC-46 FROM I-95/NC-46 IN ROANOKE RAPIDS TO SR-1312 (ST JOHN CHURCH ST). | 81907374.49 | 79 | 8.197 miles | THALLE CONSTRUCTION CO INC | STATE FUNDED | Edwin W. Rose | 2525136030 | 2019-07-16 | 2019-09-23 | 2024-03-13 | 2027-01-27 | 87.08% | 87.08% | 2026-04-30 | 2026-05-08 09:10
C204225 | 2 | Craven | R-5777A, R-5777B, U-5713 | Statewide | US-70 | US-70 FROM THE NEUSE RIVER BRIDGE TO EAST OF THURMAN RD IN JAMES CITY. | 203300000 | 78 | 5.1 miles | BALFOUR BEATTY INFRASTRUCTURE INC | INFRA | Wendi O. Johnson, PE | 2524392800 | 2019-09-10 | 2019-10-22 | 2023-09-07 | 2026-01-01 | 64.3% | 64.3% | 2026-04-22 | 2026-05-19 08:10
C204248 | 14 | Cherokee | R-5735 | Statewide | US-19 | US-19/74/64/129 FROM END OF 4 LANE DIVIDED SECTION TO US-19 BUSINESS (HIWASSEE ST). | 22692801.73 | 63 | 1.216 miles | WRIGHT BROTHERS CONSTRUCTION COMPANY INC | STATE FUNDED | J. Adam Dockery | 8283215061 | 2019-06-18 | 2019-09-25 | 2022-04-13 | 2023-11-20 | 86.35% | 86.35% | 2025-11-15 | 2025-12-30 08:10
C204265 | 14 | Buncombe, Henderson | HO-0002A, I-4400BB, I-4400C | Statewide | I-26 | I-26 FROM 0.05 MILES NORTH OF US-64 TO NC-280 (EXIT 40). | 271226964.96 | 81 | 8.552 miles | ARCHER WRIGHT JV | NHPP-026-1(200)13 | Michael D. Patton | 8285862141 | 2019-09-17 | 2019-10-28 | 2024-05-31 | 2026-03-22 | 91.29% | 91.29% | 2026-04-07 | 2026-05-08 09:10
C204266 | 13 | Buncombe, Henderson | HE-0001, HO-0002A, I-4700 | Statewide | I-26 | I-26 FROM NC-280 (EXIT 40) TO I-40. | 263010000 | 83 | 7.49 miles | FLUOR UNITED ASHEVILLE LLC | NHPP-026-1(199)6 | Luke A. Middleton | 8282503000 | 2019-07-16 | 2019-09-30 | 2024-04-29 | 2027-07-01 | 86.16% | 86.16% | 2026-04-30
C204319 | 3 | New Hanover | U-4902D | Statewide | US-17 | US-17 BUS (MARKET ST) FROM SR-1403 TO SR-2734 IN WILMINGTON. | 24654091.3 | 88 | 1.67 miles | SEALAND CONTRACTORS CORP | STATE FUNDED | Joshua T. Pratt | 9103989100 | 2019-02-19 | 2019-04-04 | 2022-11-11 | 2024-03-21 | 93.82% | 93.82% | 2026-04-30 | 2026-05-08 09:10
C204339 | 5 | Wake | P-5715 | None | SR-2215 | NEW HOPE CHURCH ROAD GRADE SEPARATION OVER CSX RAIL LINE (CR OSSING #630607N AT MILE POST S 152.32). | 19633990.17 | 6 | 0.387 miles | S T WOOTEN CORPORATION | STATE FUNDED | Alexander S. Griffis | 9198358200 | 2024-10-15 | 2025-05-01 | 2028-02-28 | 2029-05-20 | 5.26% | 5.26% | 2026-04-30 | 2026-05-12 09:10
C204345 | 10 | Cabarrus | Y-4810K | Subregional | SR-1625 | GRADE SEPARATION AT SR-1625 (ROGERS LAKE RD) OVER NS/NCRR AN D CLOSURE OF AT-GRADE CROSSING #724408Y IN KANNAPOLIS. | 16278563.65 | 35 | 0.73 miles | NJR GROUP INC | STATE FUNDED | Bradley S. Eagle | 7049834380 | 2022-11-15 | 2023-05-25 | 2026-12-12 |  | 73.86% | 73.86% | 2026-04-30 | 2026-05-05 08:10
C204348 | 12 | Catawba, Iredell | R-2307B | Regional | NC-150 | NC-150 FROM SR-1840 (GREENWOOD ROAD) IN CATAWBA COUNTY TO US -21 IN IREDELL COUNTY. | 249369373.21 | 16 | 6.943 miles | BLYTHE DEVELOPMENT LLC | STP-0150(036) | Keith Anderson | 0 | 2024-10-15 | 2025-01-21 | 2030-05-14 |  | 16.25% | 16.25% | 2026-04-30 | 2026-05-15 08:10
C204355 | 11 | Watauga | R-2566BA | Regional | NC-105 | BRIDGE OVER WATAUGA RIVER AND LEFT TURN LANE AT SR-1112 (BROADSTONE RD) ON NC-105 WITHIN R-2566B LIMITS. | 20238196.05 | 50 | 0.429 miles | WRIGHT BROTHERS CONSTRUCTION COMPANY INC | STATE FUNDED | Lance K. Byrd, PE | 8282686022 | 2021-11-16 | 2022-02-02 | 2025-05-15 | 2026-02-02 | 72.32% | 72.32% | 2026-04-30 | 2026-05-11 09:10
C204356 | 11 | Ashe | R-2915E | Statewide | US-221 | US-221 FROM US-221 BYPASS TO US-221 BUSINESS/NC-88 IN JEFFERSON. | 27409543.9 | 47 | 3.537 miles | JAMES R VANNOY & SONS CONSTRUCTION COMPANY INC | STATE FUNDED | Christopher S. Pipes | 3369039170 | 2020-03-17 | 2020-07-01 | 2024-11-11 | 2025-12-15 | 91.31% | 91.31% | 2025-12-15 | 2026-05-04 10:54
C204366 | 4 | Halifax | I-5932A, I-5932B | Statewide | I-95 | I-95 FROM MILE MARKER 153.20 (NC-148) TO MILE MARKER 167.00. | 12575000 | 34 | 13.8 miles | FSC II LLC DBA ROSE BROTHERS PAVING COMPANY | NHPIM-0095(060) | P. Gray Keeter, PE | 2525835861 | 2021-09-21 | 2021-12-01 | 2023-09-01 |  | 93.64% | 93.64% | 2026-04-30 | 2026-05-15 08:10
C204369 | 8 | Lee | R-3830 | Regional | NC-42 | NC-42/SR-1579 (BROADWAY RD) FROM US-421 IN SANFORD TO SR-153 8 (E HARRINGTON AVE) IN BROADWAY. | 61627415.52 | 35 | 5.524 miles | BOGGS CONTRACTING INC | STATE FUNDED | Gary Phillips | 9197769623 | 2022-08-16 | 2023-10-02 | 2027-03-30 | 2028-05-20 | 57.79% | 57.79% | 2026-04-15 | 2026-04-24 08:10
C204374 | 8 | Moore | U-5756, U-5814, U-5815B | None | - | US-15/501 FROM US-1 TO BRUCEWOOD RD, US-1 FROM KNIGHT ST TO OLD US-1, AND NC-5 FROM US-1 TO TROTTER DR/BLAKE BLVD. | 18389860.11 | 19 | 8.58 miles | FLATIRON CONSTRUCTORS INC FRED SMITH COMPANY JV | STATE FUNDED | James A. Dietrich | 9109442344 | 2024-09-09 | 2024-09-29 | 2029-05-06 |  | 11% | 11% | 2026-04-22 | 2026-05-04 10:54
C204384 | 10 | Cabarrus | B-5372 | Subregional | SR-1706 | BRIDGE #120109 OVER US-29 (NORTH CANNON BLVD) ON SR-1706 (MA RTIN LUTHER KING JR AVENUE). | 5729282.16 | 8 | 0.224 miles | NJR GROUP INC | STATE FUNDED | Bradley S. Eagle | 7049834380 | 2024-12-17 | 2025-03-10 | 2027-03-30 |  | 31% | 31% | 2026-04-30 | 2026-05-05 08:10
C204389 | 14 | Macon | BR-0029 | Regional | NC-106 | BRIDGE #26 OVER MIDDLE CREEK ON NC-106. | 5300000 | 31 | 0.227 miles | MOUNTAIN CREEK CONTRACTORS INC | STATE FUNDED | J. Adam Dockery | 8283215061 | 2022-11-15 | 2023-01-17 | 2025-11-11 | 2026-04-11 | 87.47% | 87.47% | 2025-11-22 | 2025-12-02 09:10
C204397 | 13 | Rutherford | R-2233BB | Statewide | US-221 | US-221 SOUTH OF US-74 BUS (CHARLOTTE RD) TO NORTH OF SR-1366 (ROPER LOOP RD). | 109237300.02 | 52 | 5.164 miles | WRIGHT BROTHERS CONSTRUCTION COMPANY INC | STATE FUNDED | Travis J. Henley | 8286527848 | 2021-12-21 | 2022-03-02 | 2027-05-14 | 2027-12-10 | 65.47% | 65.47% | 2026-04-30 | 2026-05-13 08:10
C204399 | 9 | Davidson | R-5737 | None | SR-1798, US-29 | US-29/70 & I-85 BUSINESS AT SR-1798 (OLD GREENSBORO ROAD). | 25893074.9 | 46 | 1.362 miles | SMITH-ROWE, LLC | STATE FUNDED | Larry B. Shaver | 3362496255 | 2021-10-19 | 2022-01-24 | 2026-02-28 | 2026-04-13 | 94.16% | 94.16% | 2025-10-31 | 2025-12-23 08:10
C204410 | 5 | Wake | B-4654 | Regional | NC-50 | BRIDGE #69 OVER US-70 ON NC-50 (BENSON RD). | 11657111.76 | 22 | 0.396 miles | BLYTHE CONSTRUCTION INC | 0070245 | Alexander S. Griffis | 9198358200 | 2024-04-16 | 2024-07-08 | 2027-03-30 | 2027-10-11 | 70.13% | 70.13% | 2026-04-30 | 2026-05-12 09:10
C204411 | 14 | Haywood |  | Subregional | SR-1332 | BRIDGE #430175 AND BRIDGE #430174 OVER BIG CREEK ON SR-1332 (WATERVILLE ROAD). | 8416854.09 | 8 | 0.175 miles | WHALEY CONSTRUCTION LLC | STATE FUNDED | Kenneth C. McCourt | 8284977333 | 2024-05-28 | 2025-03-04 | 2027-11-11 | 2027-12-16 | 25.63% | 25.63% | 2026-03-22 | 2026-03-27 09:10
C204421 | 2 | Craven | R-4463A | Regional | NC-43 | NC-43 CONNECTOR FROM US-17 BUSINESS TO SOUTH OF US-70. | 31775930.72 | 8 | 2.384 miles | S T WOOTEN CORPORATION | STATE FUNDED | Stanley L. Harrell | 2525270053 | 2025-07-15 | 2025-10-08 | 2029-02-11 | 2029-03-13 | 8.55% | 8.55% | 2026-04-30 | 2026-05-12 09:10
C204431 | 10 | Mecklenburg | U-5873, U-5907 | None | NC-115 | ROUNDABOUTS AT NC-115/DAVIDSON ST/POTTS ST AND AT SR-6038/GR IFFITH ST/BEATY ST AND NEW LOCATION FROM SR-6037 TO SR-6038. | 15497601.78 | 26 | 0.977 miles | CATON CONSTRUCTION GROUP INC | 0115014 | Yanwei Ma | 7048475006 | 2023-12-19 | 2024-04-29 | 2027-02-28 | 2027-03-14 | 54.9% | 54.9% | 2026-04-30 | 2026-05-13 08:10
C204454 | 13 | Buncombe |  | None | NC-146, SR-1348, US-25 | BRIDGE #76 OVER SR-3556 ON US-25, AND BRIDGES #53 & #278 OVE R FRENCH BROAD RIVER ON NC-146 & SR-1348. | 4121385.4 | 1 | 0.121 miles | FREYSSINET INC | STATE FUNDED | Thomas R. Veazey | 8282980080 | 2025-06-17 | 2026-03-17 | 2026-10-15 |  | 16.25% | 16.25% | 2026-04-22 | 2026-05-06 09:10
C204455 | 8 | Chatham, Moore |  | None | US-1 | BRIDGES #180007, #180477, #620049, AND #620072 OVER THE DEEP RIVER ON US-1 SOUTH, SR-1621, AND NC-22. | 6392193.8 | 13 | 0.517 miles | FREYSSINET INC | STATE FUNDED | Gary Phillips | 9197769623 | 2024-06-18 | 2024-10-14 | 2025-11-15 |  | 61.48% | 61.48% | 2026-04-15 | 2026-04-30 09:10
C204471 | 11 | Wilkes | U-5312 | Statewide | US-421 | US-421 FROM EAST OF NC-16 TO US-421 BUS. | 81185000 | 31 | 2.616 miles | BRANCH CIVIL INC | NHS-0421(072) | Christopher S. Pipes | 3369039170 | 2023-11-21 | 2024-02-15 | 2028-02-11 | 2028-03-04 | 69.72% | 69.72% | 2026-04-30 | 2026-05-08 09:10
C204488 | 14 | Cherokee |  | Statewide | US-64 | BRIDGE #190009 AND #190010 OVER NOTTELY RIVER AND GRAVEL RD ON US-64 & US-74. | 2989180.5 | 17 | 0.142 miles | BUCKEYE BRIDGE LLC | STATE FUNDED | J. Adam Dockery | 8283215061 | 2023-10-17 | 2024-04-01 | 2025-06-01 |  | 94.84% | 94.84% | 2026-04-15 | 2026-04-27 08:10
C204491 | 13 | Mitchell | B-5893 | Regional | NC-226 | BRIDGE #19 OVER CUB CREEK ON NC-226. | 2978019.2 | 20 | 0.152 miles | APPLE TUCK & ASSOCIATES INC | STATE FUNDED | Colby D. Justice | 8286589439 | 2023-06-20 | 2023-11-28 | 2026-01-28 | 2027-01-25 | 58.22% | 58.22% | 2026-04-22 | 2026-05-01 09:10
C204495 | 10 | Mecklenburg | C-5621 | None | US-21 | DUAL ROUNDABOUTS NORTH AND SOUTH OF SR-5544 (CATAWBA AVE) AN D US-21 INTERSECTION IN CORNELIUS. | 14589405 | 28 | 0.187 miles | CATON CONSTRUCTION GROUP INC | CMS-0021(020) | Raymond R. Gerdus | 7048475006 | 2023-10-17 | 2024-01-17 | 2027-02-28 | 2027-03-06 | 55.67% | 55.67% | 2026-04-30 | 2026-05-14 09:10
C204498 | 1 | Beaufort, Martin | R-2511 | Statewide | US-17 | US-17 FROM WASHINGTON BYPASS NORTH OF NC-171 TO MULTI-LANES SOUTH OF WILLIAMSTON. | 86385000 | 45 | 10.625 miles | BRANCH CIVIL INC | STATE FUNDED | Gerard E. Mombaerts | 2527896150 | 2022-04-19 | 2022-07-26 | 2027-01-28 | 2028-04-15 | 60.08% | 60.08% | 2026-04-24 | 2026-05-01 09:10
C204501 | 10 | Mecklenburg | U-5108 | Subregional | SR-2316 | SR-2316 (NORTHCROSS DR) FROM NORTH OF NC-73 (SAM FURR RD) TO SR-2147 (WESTMORELAND RD). | 20860000 | 21 | 1.79 miles | SEALAND CONTRACTORS CORP | STBGDA-1001(093) | Michael W. Hedrick, PE | 9805230080 | 2024-06-18 | 2024-09-04 | 2027-03-14 | 2027-05-28 | 58.52% | 58.52% | 2026-04-30 | 2026-05-07 10:10
C204505 | 10 | Mecklenburg | U-5906 |  | - | SR-2195 (TORRENCE CHAPEL RD) AND SR-5544 (WEST CATAWBA AVE) IN CORNELIUS. | 0 |  | 0.405 miles | K WEST GROUP LLC DBA KWEST GROUP LLC | 2195001 | Michael W. Hedrick, PE | 9805230080 | 2025-11-18 |  | 2028-11-11 |  | 0% | 0%
C204507 | 6 | Cumberland | U-5798A | Subregional | SR-1102 | SR-1102 FROM NORTH OF SR-1112 TO US-401 AND REPLACE BRIDGE 250075 OVER LITTLE ROCKFISH CREEK. | 22639926.77 | 42 | 1.125 miles | W C ENGLISH INCORPORATED | STATE FUNDED | Spencer G. Shoffner, PE | 9103640607 | 2022-03-15 | 2022-09-12 | 2025-03-14 | 2026-07-31 | 91.33% | 91.33% | 2026-02-15 | 2026-02-24 08:10
C204512 | 5 | Wake | U-5302 |  | US-401 | US-401 FROM SOUTH OF SR-1006 (OLD STAGE ROAD) TO SOUTH OF SR -2538 (MECHANICAL BOULEVARD/GARNER STATION BOULEVARD). | 0 |  | 1.237 miles | CONTI CIVIL LLC | STATE FUNDED | David W. Conner II | 9197077370 | 2026-03-17 |  | 2029-05-14 |  | 0% | 0%
C204543 | 6 | Harnett, Johnston | I-5878, I-5883, I-5986B | Statewide | I-95 | I-95 FROM SR-1002 (EXIT 71) TO I-40 (EXIT 81). | 236460093.76 | 57 | 8.873 miles | FLATIRON FRED SMITH COMPANY JV | STATE FUNDED | Randy K. Wise, PE | 9103640600 | 2021-07-20 | 2021-09-20 | 2026-10-28 | 2028-01-22 | 69.34% | 69.34% | 2026-04-22 | 2026-05-07 10:10
C204553 | 3 | Pender | R-3300B | Regional | NC-417 | NC-417 (HAMPSTEAD BYPASS) FROM SOUTH OF NC-210 TO NORTH OF SR-1563 (SLOOP POINT LOOP RD). | 185680442 | 50 | 6.916 miles | CONTI CIVIL LLC | STATE FUNDED | Bradley L. Haste | 9103475258 | 2022-01-18 | 2022-03-30 | 2027-03-14 | 2027-12-11 | 69.16% | 69.16% | 2026-04-30 | 2026-05-13 08:10
C204554 | 5 | Wake | B-5318 | Subregional | SR-2204 | BRIDGE #126 OVER SMITH'S CREEK ON SR-2044 (LIGON MILL RD) IN WAKE FOREST. | 9583307.77 | 34 | 0.365 miles | FSC II LLC DBA FRED SMITH COMPANY | BRZ-2044(4) | David B. Moore | 9192204600 | 2022-11-15 | 2023-01-06 | 2026-02-28 |  | 93.41% | 93.41% | 2025-12-31 | 2026-01-15 09:10
C204556 | 4 | Anson, Brunswick, Buncombe, Carteret, Cleveland, Columbus, Craven, Cumberland, Gaston, Halifax, Harnett, Henderson, Johnston, Jones, Lenoir, Mecklenburg, Nash, Northampton, Polk, Richmond, Robeson, Rutherford, Scotland, Union, Wake, Wayne, Wilson | HO-0002A, HO-0002B, HO-0002C, I-5986C, R-5777D | None | I-95, US-70, US-74 | US-70 FROM I-40 TO MOREHEAD CITY PORT, I-95 FROM SC STATE LINE TO VA STATE LINE, US-74 FROM ASHEVILLE TO WILMINGTON. | 85711000 | 56 | 600 miles | BROOKS BERRY HAYNIE & ASSOCIATES INC | 0070235 | Brandon L. Herring, PE | 2522376164 | 2021-03-26 | 2021-07-31 | 2026-10-01 | 2027-08-06 | 85.34% | 85.34% | 2026-03-31 | 2026-05-07 10:10
C204567 | 11 | Ashe |  | None | NC-194 | BRIDGES #040032 ON NC-194, #040507 ON SR-1644, #040478 ON SR -1514, AND #040019 ON NC-194. | 5750777 | 7 | 0.277 miles | SAFFO CONTRACTORS INC | STATE FUNDED | Christopher S. Pipes | 3369039170 | 2025-04-15 | 2025-10-01 | 2026-10-31 |  | 36.53% | 36.53% | 2026-04-30 | 2026-05-08 09:10
C204568 | 1 | Dare |  | Statewide | US-64 | BRIDGE #270012 OVER ROANOKE SOUND ON US-64. | 21305653.3 | 28 | 1.05 miles | FREYSSINET INC | STATE FUNDED | Pablo A. Hernandez, PE | 2524733637 | 2022-01-18 | 2022-03-25 | 2025-09-15 |  | 84.36% | 84.36% | 2025-09-15 | 2025-11-12 09:10
C204570 | 6 | Columbus | R-2561CA | Regional | NC-11, NC-87 | NC-87 AT NC-11 CONSTRUCT INTERCHANGE. | 35978896.35 | 33 | 1.695 miles | BALFOUR BEATTY INFRASTRUCTURE INC | 0087051 | Jason A. Johnson | 9107886300 | 2023-05-16 | 2023-09-06 | 2026-11-11 | 2027-02-09 | 75.05% | 75.05% | 2026-05-07
C204596 | 6 | Robeson | I-5879, I-6064A, I-6064B, I-6064C | Statewide | I-95 | I-95 FROM I-74 (EXIT 13) TO SOUTH OF US-301 (EXIT 22) AND I-95/SR-1536 (CARTHAGE RD) INTERCHANGE IMPROVEMENTS. | 432700000 | 56 | 8 miles | FLATIRON UNITED JV | 0095078 | Joseph M. Parker, Jr., PLS | 9103640600 | 2021-09-21 | 2021-11-15 | 2026-11-01 | 2030-05-29 | 63.18% | 63.18% | 2026-04-22 | 2026-04-30 09:10
C204631 | 14 | Henderson | U-5887 | Subregional | SR-1783 | SR-1783 FROM NC-225 TO WEST OF US-176. | 6673982.45 | 26 | 1.064 miles | BUCHANAN AND SONS INC | STATE FUNDED | Patrick A. Eubanks | 8288917911 | 2021-05-18 | 2022-03-23 | 2024-03-13 | 2026-04-11 | 78.94% | 78.94% | 2025-10-07 | 2025-11-13 09:10
C204632 | 7 | Durham, Orange | I-3306A, W-5707C | Statewide | I-40 | I-40 FROM I-85 IN ORANGE COUNTY TO THE DURHAM COUNTY LINE AND I-40 WESTBOUND IN DURHAM COUNTY NEAR US-15/501. | 236457869 | 58 | 13 miles | THE LANE CONSTRUCTION CORPORATION | IMS-040-4(148) | Jacob T. Crews, PE | 3363751774 | 2021-08-17 | 2021-10-28 | 2025-09-01 | 2026-06-17 | 78.13% | 78.13% | 2026-04-30 | 2026-05-19 08:10
C204633 | 9 | Forsyth | U-2579AB | Statewide | I-74 | FUTURE I-74 (WINSTON-SALEM NORTHERN BELTWAY) FROM I-40 TO I-40 BUS/US 421. | 261764022.37 | 51 | 2.727 miles | WEBBER LLC | NHPIM-0040(68) | Larry B. Shaver | 3362496255 | 2021-12-21 | 2022-04-04 | 2027-04-30 | 2027-05-07 | 89.81% | 89.81% | 2026-04-15 | 2026-05-01 09:10
C204649 | 6 | Columbus | R-5020B | Statewide | US-701 | US-701 BYPASS (MADISON ST - J K POWELL BLVD) FROM SR-1437 (VIRGIL AVE) TO US-74/76. | 28249248.03 | 48 | 2.183 miles | HIGHLAND PAVING CO LLC | STATE FUNDED | Jason A. Johnson | 9107886300 | 2021-08-17 | 2021-09-27 | 2025-12-12 | 2026-03-12 | 87.45% | 87.45% | 2025-12-31 | 2026-01-08 09:10
C204654 | 14 | Haywood | B-6054A, B-6054B, B-6054C, B-6054D, B-6054E | Statewide | I-40 | I-40 OVER SR 1101 (HARMON DEN RD / COLD SPRINGS CREEK RD) AND COLD SPRING CREEK, | 18945378.96 | 56 | 0.79 miles | KIEWIT INFRASTRUCTURE SOUTH CO | STATE FUNDED | Kenneth C. McCourt | 8284977333 | 2021-10-04 | 2021-10-28 | 2023-05-20 | 2027-10-07 | 87.69% | 87.69% | 2026-03-31 | 2026-04-10 09:10
C204655 | 5 | Wake | I-5997 | Statewide | I-440 | I-440 FROM WEST OF LAKE BOONE TRAIL TO EAST OF SR-2000 (WAKE FOREST RD) IN RALEIGH. | 26387244.89 | 38 | 5.15 miles | FSC II LLC DBA FRED SMITH COMPANY | 0440024 | Niklaus C. Winkler | 9197339499 | 2022-07-19 | 2022-12-08 | 2024-09-01 | 2026-05-15 | 94.22% | 94.22% | 2026-04-30 | 2026-05-13 08:10
C204657 | 14 | Polk |  | Statewide | I-26 | I-26 FROM MILE MARKER 62.5 TO MILE MARKER 64. | 16495772.35 | 40 | 0.892 miles | WATSON CONTRACTING INC | STATE FUNDED | Patrick A. Eubanks | 8288917911 | 2021-10-19 | 2022-01-24 | 2024-03-13 | 2025-02-28 | 72.6% | 72.6% | 2026-02-28 | 2026-03-10 09:10
C204684 | 14 | Haywood | B-3186, B-5898 | Statewide | US-2374 | BRIDGES #155 AND 158 OVER RICHLAND CREEK ON US-23/74 AND BRI DGE #168 OVER US-19 AND US-23 ON US-23/74. | 42584674.65 | 27 | 0.641 miles | ZACHRY CONSTRUCTION CORPORATION | BRNHP-0023(32) | Max L. Buchanan | 8285862141 | 2023-12-19 | 2024-03-12 | 2028-03-29 | 2028-04-19 | 47.99% | 47.99% | 2026-04-22 | 2026-05-04 10:54
C204695 | 2 | Craven | R-5777C | Statewide | US-70 | US-70 FROM THE HAVELOCK BYPASS TO EAST OF SR-1116 (THURMAN R D). | 242350000 | 39 | 6.4 miles | BALFOUR BEATTY INFRASTRUCTURE INC | STATE FUNDED | Brad T. McMannen, PE | 2526496520 | 2023-01-17 | 2023-02-27 | 2028-06-07 | 2028-08-21 | 32.16% | 32.16% | 2026-04-30 | 2026-05-20 09:10
C204711 | 2 | Beaufort | B-5614 | Subregional | SR-1112 | BRIDGE #060009 OVER BLOUNTS CREEK ON SR-1112 (MOUTH OF THE C REEK ROAD). | 11018000 | 4 | 0.398 miles | SANFORD CONTRACTORS INC | 1112019 | Jason B. Beasley | 2524392970 | 2025-10-21 | 2025-12-01 | 2028-10-28 | 2029-01-26 | 12.25% | 12.25% | 2026-04-30 | 2026-05-08 09:10
C204715 | 14 | Jackson |  | None | SR-1336 | SR-1336 FROM N OF SR-1002 TO N OF SR-1337 AND SR-1002 FROM S R-1336 TO SR-1169. | 6282484.1 | 27 | 0.428 miles | IPC PAVING LLC DBA IPC STRUCTURES LLC | STATE FUNDED | Kenneth C. McCourt | 8284977333 | 2023-07-18 | 2023-10-24 | 2025-12-28 | 2026-08-13 | 85.51% | 85.51% | 2026-05-07 | 2026-05-14 09:10
C204716 | 13 | Burke | B-5869 | Statewide | US-64 | BRIDGE #99 OVER NORFOLK SOUTHERN RAILROAD ON US-64/US-70 IN MORGANTON. | 22957187.28 | 36 | 0.496 miles | MOUNTAIN CREEK CONTRACTORS INC | NHPP-0064(180) | Keith Anderson | 0 | 2023-05-16 | 2023-07-05 | 2027-02-08 | 2027-03-29 | 81.41% | 81.41% | 2026-04-30 | 2026-05-08 09:10
C204722 | 6 | Columbus | R-5819, R-5820 | Statewide | US-74/7 | INTERSECTIONS OF US-74/76 AT SR-1740 (OLD LAKE RD) AND SR-17 35 (CHANCEY TOWN RD). | 44098712.33 | 45 | 2.202 miles | BMCO CONSTRUCTION INC | STATE FUNDED | Jason A. Johnson | 9107886300 | 2022-06-21 | 2022-08-01 | 2026-01-11 | 2026-04-11 | 86.67% | 86.67% | 2026-04-15 | 2026-04-22 08:10
C204724 | 3 | Pender | B-5156 | Regional | NC-210 | BRIDGE #28 OVER LONG CREEK ON NC-210. | 5022225.46 | 20 | 0.392 miles | SMITH-ROWE, LLC | STATE FUNDED | Bradley L. Haste | 9103475258 | 2024-04-16 | 2024-06-10 | 2026-03-30 | 2026-06-12 | 90.89% | 90.89% | 2026-02-28 | 2026-04-02 08:10
C204726 | 13 | Buncombe | I-5889, I-5889B | Statewide | I-40 | I-40 FROM MILEMARKER 45.25 TO MILEMARKER 50. | 27988062.25 | 25 | 5.11 miles | APAC ATLANTIC INC DBA HARRISON CONSTRUCTION COMPANY | 0040103 | Thomas R. Veazey | 8282980080 | 2023-04-18 | 2023-10-17 | 2026-03-30 | 2026-04-22 | 89.94% | 89.94% | 2026-04-07 | 2026-04-15 08:10
C204727 | 6 | Robeson | I-5987A | Statewide | I-95 | I-95 FROM SOUTH OF US-301 TO SOUTH OF NC-20. | 247025388.37 | 43 | 8.106 miles | FLATIRON DRAGADOS CONSTRUCTORS INC | STATE FUNDED | Spencer G. Shoffner, PE | 9103640607 | 2022-09-20 | 2022-11-08 | 2027-05-14 |  | 54.56% | 54.56% | 2026-04-27 | 2026-04-30 09:10
C204728 | 6 | Robeson | I-5987B | Statewide | I-95 | I-95 FROM SOUTH OF NC-20 TO SOUTH OF PROPOSED I-295. | 282928483.37 | 44 | 7.956 miles | WEBBER LLC | STATE FUNDED | Spencer G. Shoffner, PE | 9103640607 | 2022-07-19 | 2022-10-10 | 2027-05-14 |  | 70.28% | 70.28% | 2026-03-31 | 2026-04-24 08:10
C204730 | 12 | Gaston | C-5606C, C-5703 | None | SR-1 | GASTONIA CITYWIDE SIGNAL SYSTEM UPGRADE AND CCTV CAMERAS. | 9123702.85 | 36 | 0 miles | MB HAYNES CORPORATION DBA HAYNES ELECTRIC UTILITY | CMAQ-1213(039) | Anne Burwell Schley, PE | 7044805580 | 2022-08-16 | 2022-11-01 | 2025-06-06 | 2025-06-27 | 60.99% | 60.99% | 2026-05-15
C204731 | 14 | Graham | A-0009CA | None | NC-143, SR-1223, SR-1275, US-129 | US-129 FROM SOUTH OF SR-1275 (FIVE POINTS RD) TO NC-143 AND NC-143 FROM US-129 TO SR-1223 (BEECH CREEK RD). | 47500000 | 42 | 3.727 miles | WATSON CONTRACTING INC | 0129007 | J. Adam Dockery | 8283215061 | 2022-08-16 | 2022-11-01 | 2027-04-05 |  | 85.55% | 85.55% | 2026-04-30 | 2026-05-08 09:10
C204732 | 1 | Dare | B-5610 | None | NC-12 | BRIDGE #270008 OVER THE SLASH CREEK ON NC-12 AND SR-1241(EAG LE PASS RD) FROM NC-12 TO NC-12. | 4498089.74 | 11 | 0.923 miles | SMITH-ROWE, LLC | 0012068 | Brandon J. Tatum | 2526216400 | 2024-06-18 | 2024-09-12 | 2025-11-18 | 2025-11-22 | 88.99% | 88.99% | 2025-10-31 | 2025-11-19 09:10
C204738 | 13 | McDowell | HI-0010 | Statewide | I-40 | I-40 FROM MILEMARKER 67 TO MILEMARKER 73 (OLD FORT MOUNTAIN) . | 14798732.8 | 18 | 5.94 miles | MAYMEAD INC | 0040119 | Travis J. Henley | 8286527848 | 2023-07-18 | 2023-09-13 | 2024-11-15 | 2026-08-23 | 70.78% | 70.78% | 2025-10-15 | 2025-11-25 08:10
C204739 | 14 | Graham | A-0009CB | Regional | NC-143 | NC-143 FROM SR-1223 (BEECH CREEK RD) TO 0.5 MILES NORTH OF A PPALACHIAN TRAIL. | 116407729.7 | 41 | 3.911 miles | CHARLES BLALOCK & SONS INC | 0129008 | J. Adam Dockery | 8283215061 | 2022-09-20 | 2022-11-29 | 2027-12-12 |  | 68.64% | 68.64% | 2026-04-15 | 2026-04-23 08:10
C204740 | 13 | Buncombe | B-4442 | Statewide | US-19 | BRIDGES #370 AND #373 OVER REEMS CREEK ON US-19/23, US-25, A ND US-70. | 26083192.63 | 39 | 0.665 miles | SUMMERS TAYLOR INC | 0019061 | Colby D. Justice | 8286589439 | 2022-09-20 | 2023-01-17 | 2027-03-14 | 2027-04-09 | 64.46% | 64.46% | 2026-04-30 | 2026-05-11 09:10
C204741 | 10 | Cabarrus | B-5808 | Statewide | US-29 | BRIDGES #57 AND #59 OVER IRISH BUFFALO CREEK ON US-29 AND US -601. | 11730807.95 | 33 | 0.178 miles | DANE CONSTRUCTION LLC | NHP-0029(062) | Michael Mariano | 7049834380 | 2023-04-18 | 2023-07-07 | 2027-04-30 |  | 82.13% | 82.13% | 2026-04-15 | 2026-04-24 08:10
C204745 | 6 | Harnett, Wake | R-5705B | Regional | NC-55 | NC-55 FROM NC-210 TO SR-4809 (JICARILA LANE). | 61497777.3 | 39 | 4.536 miles | HIGHLAND PAVING CO LLC | STATE FUNDED | Donavon Hunt | 9103640608 | 2022-10-18 | 2023-03-15 | 2027-05-14 | 2028-01-24 | 52.07% | 52.07% | 2026-04-30 | 2026-05-13 08:10
C204746 | 9 | Forsyth | U-2579AA | Statewide | I-74 | FUTURE I-74 (WINSTON-SALEM NORTHERN BELTWAY) FROM US-311 TO I-40. | 126045009.7 | 43 | 1.536 miles | FLATIRON DRAGADOS CONSTRUCTORS INC | 0074226 | Nicholas C. Librandi | 3367477950 | 2022-10-18 | 2022-12-01 | 2027-03-30 | 2027-04-01 | 94.35% | 94.35% | 2026-04-22 | 2026-05-04 10:54
C204748 | 8 | Randolph | HE-0004 | Statewide | US-421 | TWO INTERCHANGES ON US-421. | 1658717.02 | 41 | 0 miles | AMES CONSTRUCTION INC | STATE FUNDED | Joshua S. Brooks | 3363184020 | 2022-09-12 | 2023-01-03 | 2025-05-01 | 2026-06-14 | 82.3% | 82.3% | 2026-04-30 | 2026-05-15 08:10
C204760 | 6 | Cumberland | U-4709 | Subregional | SR-1112 | SR-1112 FROM WEST OF SR-1115 TO NC-59 & SR-1115 FROM SOUTH O F WALLACE ST TO NC-59. | 21620000 | 12 | 0.748 miles | FSC II LLC DBA FRED SMITH COMPANY | STATE FUNDED | Donavon Hunt | 9103640608 | 2025-01-21 | 2025-04-25 | 2028-03-29 |  | 46.82% | 46.82% | 2026-04-22
C204762 | 7 | Caswell | BR-0069 | None | US-158 | BRIDGE #160001 OVER COUNTRY LINE CREEK ON US-158/NC-86. | 6523842.76 | 21 | 0.267 miles | SMITH-ROWE, LLC | STATE FUNDED | Jacob B. Harris, PE | 3365206060 | 2024-05-28 | 2024-08-21 | 2026-12-12 | 2027-01-30 | 75.58% | 75.58% | 2026-04-30 | 2026-05-08 09:10
C204765 | 5 | Wake | HL-0033 | Subregional | SR-3126 | SR-3126 (AIRPORT BLVD) FROM GARDEN SQUARE LANE TO SR-1637 (C HURCH ST) IN MORRISVILLE. | 9867641.9 | 1 | 0.459 miles | SUNROCK INDUSTRIES LLC DBA CAROLINA SUNROCK LLC | 3126001 | Alexander S. Griffis | 9198358200 | 2026-02-17 | 2026-04-02 | 2028-11-28 |  | 2.57% | 2.57% | 2026-04-30 | 2026-05-05 08:10
C204766 | 13 | Madison | B-5895 | Statewide | US-25 | BRIDGE #560067 OVER THE FRENCH BROAD RIVER ON US-25/70. | 16777527.27 | 12 | 0.322 miles | KEMP SIGMON CONSTRUCTION CO INC | STATE FUNDED | Colby D. Justice | 8286589439 | 2025-03-18 | 2025-04-28 | 2029-02-28 | 2029-03-07 | 60.09% | 60.09% | 2026-04-22 | 2026-05-07 10:10
C204771 | 7 | Guilford | R-5725 | Regional | NC-68 | NC-68 AT SR-2129 (FOGLEMAN RD) TO NC-150 IN OAK RIDGE. | 10497020.93 | 15 | 0.742 miles | YATES CONSTRUCTION CO INC | STATE FUNDED | Jacob B. Harris, PE | 3365206060 | 2023-06-20 | 2024-03-15 | 2026-03-14 | 2027-03-19 | 37.43% | 37.43% | 2026-04-30 | 2026-05-12 09:10
C204772 | 6 | Robeson | R-5751 | Statewide | US-74 | US-74 AT NC-72 AND NC-130. | 24595851.2 | 39 | 1.105 miles | C M LINDSAY & SONS INC | STATE FUNDED | Joseph M. Parker, Jr., PLS | 9103640600 | 2023-02-21 | 2023-04-12 | 2026-12-12 | 2026-12-13 | 90.57% | 90.57% | 2026-05-07 | 2026-05-18 08:10
C204775 | 1 | Dare | HB-0017 | Statewide | US-64 | BRIDGE #9 ON US-64 IN MANNS HARBOR. | 33758848.88 | 34 | 2.7 miles | COASTAL GUNITE CONSTRUCTION COMPANY | 0064216 | Pablo A. Hernandez, PE | 2524733637 | 2022-09-20 | 2023-04-13 | 2026-11-01 |  | 72.53% | 72.53% | 2026-04-30 | 2026-05-14 09:10
C204785 | 6 | Harnett | R-5705A | Regional | NC-55 | NC-55 FROM SOUTH OF SR-1532 (OAK GROVE CHURCH RD) TO NC-210. | 48441330.83 | 30 | 4.364 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Donavon Hunt | 9103640608 | 2023-09-19 | 2023-12-11 | 2028-04-12 |  | 41.35% | 41.35% | 2026-04-16 | 2026-05-05 08:10
C204786 | 5 | Wake | U-5748 | Statewide | US-401 | US-401 AT SR-2044 (LIGON MILL RD)/SR-2224 (MITCHELL MILL RD) AND SR-2006 (PERRY CREEK RD). | 45353442 | 31 | 2.46 miles | CONTI CIVIL LLC | STATE FUNDED | David B. Moore | 9192204600 | 2023-07-18 | 2023-10-02 | 2027-11-11 | 2027-12-28 | 81.48% | 81.48% | 2026-04-30 | 2026-05-15 08:10
C204789 | 8 | Chatham | HE-0006 | None | US-1 | TRIANGLE INNOVATION POINT MEGASITE. | 1489407.41 | 20 | 0 miles | S T WOOTEN CORPORATION | STATE FUNDED | Joshua S. Brooks | 3363184020 | 2023-07-07 | 2023-08-14 | 2026-06-19 |  | 50.35% | 50.35% | 2026-04-30 | 2026-05-07 10:10
C204793 | 7 | Rockingham | BR-0041, BR-0043 | None | US-29 | BRIDGE 780001 OVER US-29 ON SR-2817 AND BRIDGE 780151 OVER U S-29 ON US-158. | 26223171.08 | 35 | 0.887 miles | W C ENGLISH INCORPORATED | STATE FUNDED | Jacob B. Harris, PE | 3365206060 | 2023-04-18 | 2023-06-14 | 2027-05-14 | 2027-07-12 | 72.57% | 72.57% | 2026-04-30 | 2026-05-08 09:10
C204796 | 14 | Haywood | HB-0002 | Statewide | I-40 | BRIDGES #248 AND #249 OVER SR-1613 (BEAVERDAM RD) ON I-40. | 32996977.26 | 20 | 0.54 miles | ZACHRY CONSTRUCTION CORPORATION | 0040120 | Max L. Buchanan | 8285862141 | 2024-05-28 | 2024-08-29 | 2028-04-29 | 2028-05-25 | 37.57% | 37.57% | 2026-05-07
C204797 | 6 | Cumberland | U-4405B | Statewide | US-401 | US-401 (RAEFORD RD) FROM EAST OF NC-162 (BUNCE RD) TO EAST O F BRIGHTON RD. | 48425858 | 11 | 1.908 miles | BRANCH CIVIL INC | STPDA-0401(301) | Spencer G. Shoffner, PE | 9103640607 | 2025-03-18 | 2025-06-02 | 2029-01-28 |  | 23.44% | 23.44% | 2026-04-30 | 2026-05-12 09:10
C204798 | 7 | Guilford | U-6018 | Regional | NC-62 | NC-62 FROM SR-1154 (KERSEY VALLEY RD) TO SR-1162 (WEANT RD). | 18699762.67 | 9 | 0.969 miles | TRIANGLE GRADING & PAVING INC | STATE FUNDED | Leland J. Barber, PE | 3364877080 | 2025-06-17 | 2025-07-28 | 2028-05-13 |  | 23.34% | 23.34% | 2026-04-22 | 2026-04-28 09:10
C204812 | 14 | Graham | A-0009CC | None | NC-143, NC-28, SR-1228 | NC-143 FROM 0.5 MI NORTH OF APPALACHIAN TRAIL TO NC-28 AND N C-28 FROM 0.2 MI WEST NC-143 TO 0.2 MI WEST OF SR-1228. | 67387346.29 | 40 | 2.593 miles | ADAMS CONTRACTING CO INC | 0143011 | J. Adam Dockery | 8283215061 | 2022-12-20 | 2023-01-26 | 2027-01-28 | 2028-04-30 | 87.95% | 87.95% | 2026-05-07 | 2026-05-14 09:10
C204814 | 4 | Wayne | B-4838 |  | - | BRIDGE #950020 OVER CSX TRANSPORTATION RAILROAD TRACKS ON US -70 BUS. | 0 |  | 0.607 miles | BLYTHE CONSTRUCTION INC | STATE FUNDED | Jason M. Lee | 9197395300 | 2026-01-20 |  | 2028-11-11 |  | 0% | 0%
C204815 | 9 | Davidson | B-5783 | Statewide | US-29 | BRIDGES #164 AND 168 OVER THE NORFOLK SOUTHERN RAILWAY ON US -29/70 I-85 BUS. | 12230177.29 | 27 | 0.55 miles | SMITH-ROWE, LLC | NHP-4573(831) | Larry B. Shaver | 3362496255 | 2023-08-15 | 2023-10-18 | 2027-05-14 | 2028-01-10 | 67.25% | 67.25% | 2026-04-30 | 2026-05-14 09:10
C204821 | 7 | Guilford | U-4015A | Subregional | SR-1556 | SR-1556 (GALLIMORE DAIRY RD) FROM NC-68 TO SOUTH OF AIRPARK RD. | 17747699.44 | 13 | 1.056 miles | YATES CONSTRUCTION CO INC | STATE FUNDED | Jacob T. Crews, PE | 3363751774 | 2024-12-17 | 2025-03-11 | 2027-11-29 | 2027-12-02 | 34.71% | 34.71% | 2026-04-15 | 2026-04-29 09:10
C204823 | 14 | Haywood | U-5839 | Statewide | US-276 | US-276 (RUSS AVE) FROM US-23/74 TO US-23 BUS (MAIN ST) IN WA YNESVILLE. | 42830672.6 | 26 | 1.193 miles | BUCHANAN AND SONS INC | STATE FUNDED | Max L. Buchanan | 8285862141 | 2023-12-19 | 2024-03-08 | 2028-02-11 | 2028-04-11 | 55.64% | 55.64% | 2026-04-30 | 2026-05-12 09:10
C204824 | 5 | Wake | R-2829A | Regional | NC-540 | NC-540 (TRIANGLE EXPRESSWAY SOUTHEAST EXTENSION) FROM I-40 T O SOUTH OF SR-2542 (ROCK QUARRY ROAD). | 287285000 | 29 | 4.16 miles | BRANCH S T WOOTEN JOINT VENTURE | STATE FUNDED | Bruce W. Scuffham | 0 | 2023-10-17 | 2023-11-21 | 2028-09-01 |  | 40.58% | 40.58% | 2026-03-31 | 2026-04-22 08:10
C204825 | 5 | Wake | HL-0133, R-2829B | Regional | NC-540 | NC-540 (TRIANGLE EXPRESSWAY SOUTHEAST EXTENSION) FROM SOUTH OF SR-2542 (ROCK QUARRY ROAD) TO I-87/US-64/US-264. | 449946000 | 29 | 6.01 miles | FLATIRON FRED SMITH COMPANY JV | STATE FUNDED | Bruce W. Scuffham | 0 | 2023-08-29 | 2023-09-21 | 2028-09-20 |  | 40.45% | 40.45% | 2026-04-15 | 2026-05-01 09:10
C204828 | 14 | Jackson |  | Regional | NC-116 | BRIDGE #32 OVER SAVANNAH CREEK ON NC-116. | 5386646.3 | 24 | 0.341 miles | OWLE CONSTRUCTION LLC | STATE FUNDED | Kenneth C. McCourt | 8284977333 | 2024-01-16 | 2024-02-21 | 2026-12-12 |  | 81.1% | 81.1% | 2026-01-15 | 2026-02-03 08:10
C204829 | 7 | Rockingham | B-5716 | Subregional | SR-1138 | BRIDGE #780140 OVER DAN RIVER ON SR-1138. | 12940823.6 | 3 | 0.426 miles | BLYTHE CONSTRUCTION INC | BRZ-1138(021) | Jacob B. Harris, PE | 3365206060 | 2025-08-19 | 2025-11-20 | 2028-12-12 |  | 13.82% | 13.82% | 2026-04-30 | 2026-05-08 09:10
C204832 | 4 | Halifax, Nash | BR-0090 | Regional | NC-561 | BRIDGE #630036 OVER FISHING CREEK ON NC-561. | 4253879.75 | 6 | 0.167 miles | S T WOOTEN CORPORATION | STATE FUNDED | Logan S. Ennis | 2524592129 | 2025-08-19 | 2025-11-10 | 2028-03-29 |  | 25.33% | 25.33% | 2026-05-15
C204835 | 1 | Bertie | R-5809A | Regional | NC-45 | NC-45 FROM WASHINGTON COUNTY LINE TO US-17. | 11778894 | 11 | 8.096 miles | FSC II LLC DBA FRED SMITH COMPANY | 4697601 | Gerard E. Mombaerts | 2527896150 | 2025-01-21 | 2025-06-03 | 2027-11-11 |  | 47.22% | 47.22% | 2026-04-30 | 2026-05-07 10:10
C204836 | 14 | Clay | R-5863 | Statewide | US-64 B | US-64 BUSINESS FROM US-64 TO SR-1307 (MAIN ST). | 16693118.3 | 4 | 1.181 miles | WATSON CONTRACTING INC | STATE FUNDED | J. Adam Dockery | 8283215061 | 2025-09-16 | 2025-11-29 | 2029-01-28 |  | 19.72% | 19.72% | 2026-04-15 | 2026-04-21 09:10
C204837 | 9 | Forsyth | U-2729 | None | SR-1672 | SR-1672 (HANES MILL ROAD) FROM MUSEUM DRIVE TO SR-4000 (UNIV ERSITY PARKWAY) IN WINSTON-SALEM. | 23925288.63 | 33 | 0.767 miles | CATON CONSTRUCTION GROUP INC | STATE FUNDED | Joshua A. Miller | 3362939610 | 2023-06-20 | 2023-08-24 | 2027-03-14 | 2027-06-17 | 56.59% | 56.59% | 2026-04-30 | 2026-05-14 09:10
C204838 | 4 | Edgecombe | U-4424 | Regional | NC-111 | NC-111 (WILSON ST) FROM US-64 ALT (WESTERN BLVD) TO NC-122 ( MCNAIR RD) IN TARBORO. | 18892950.04 | 28 | 2.306 miles | BARNHILL CONTRACTING CO | STATE FUNDED | P. Gray Keeter, PE | 2525835861 | 2023-06-20 | 2024-02-06 | 2026-04-30 | 2026-11-13 | 85.82% | 85.82% | 2026-04-30 | 2026-05-12 09:10
C204840 | 11 | Caldwell | U-4700CC | None | US-321 | INTERSECTION AT US-321 AND SR-1108 (MISSION RD). | 13348559.1 | 2 | 0.563 miles | HEI CIVIL CAROLINAS LLC DBA HEI CIVIL | NHP-0321(045) | Lance K. Byrd, PE | 8282686022 | 2025-10-21 | 2026-01-29 | 2028-04-12 |  | 11.24% | 11.24% | 2026-04-30 | 2026-05-07 10:10
C204842 | 10 | Union | U-5808 | Subregional | SR-1362 | SR-1362 (CHESTNUT LANE CONNECTOR) FROM SR-1367 (MATTHEWS IND IAN TRAIL ROAD) TO SR-1368 (GRIBBLE ROAD). | 18059605.83 | 22 | 0.587 miles | K WEST GROUP LLC DBA KWEST GROUP LLC | STATE FUNDED | Jake R. Koltiska | 7042185125 | 2023-12-19 | 2024-04-29 | 2027-02-11 | 2027-02-14 | 72.75% | 72.75% | 2026-03-31 | 2026-04-16 08:10
C204843 | 8 | Randolph | U-5813 | Statewide | US-64 | US-64 FROM ASHEBORO BYPASS TO EAST OF I-73/I-74/US-220. | 59000442 | 19 | 1.972 miles | CONTI CIVIL LLC | NHP-0064(206) | Joshua S. Brooks | 3363184020 | 2024-07-16 | 2024-10-17 | 2029-04-01 | 2029-04-04 | 41.2% | 41.2% | 2026-04-30 | 2026-05-20 09:10
C204844 | 11 | Caldwell | U-6036 | Subregional | SR-1109 | SR-1109 (PINEWOOD ROAD) FROM US-321 TO SR-1252 (BERT HUFFMAN ROAD). | 11480140.98 | 21 | 0.658 miles | JAMES R VANNOY & SONS CONSTRUCTION COMPANY INC | STATE FUNDED | Lance K. Byrd, PE | 8282686022 | 2024-05-28 | 2024-08-26 | 2027-03-30 | 2027-07-31 | 52.28% | 52.28% | 2026-04-30 | 2026-05-11 09:10
C204851 | 12 | Cleveland | R-2707D, R-2707E | Statewide | US-74 | US-74 SHELBY BYPASS FROM EAST OF NC-150 TO WEST OF SR-1001 ( STONEY POINT RD). | 167407389.37 | 31 | 6.099 miles | AMES CONSTRUCTION INC | STATE FUNDED | Anne Burwell Schley, PE | 7044805580 | 2023-07-18 | 2023-09-14 | 2029-04-30 | 2029-05-21 | 39.03% | 39.03% | 2026-05-07 | 2026-05-18 08:10
C204852 | 12 | Iredell | R-3833C | Subregional | SR-1100 | SR-1100 (BRAWLEY SCHOOL RD) FROM I-77 TO US-21 | 34788496.49 | 20 | 1.118 miles | THE LANE CONSTRUCTION CORPORATION | STATE FUNDED | Justin T. Johnson | 7043806050 | 2023-11-21 | 2024-07-29 | 2029-01-28 |  | 49.26% | 49.26% | 2026-03-31 | 2026-05-04 10:54
C204854 | 1 | Gates, Pasquotank | R-5808 | Statewide | US-158 | US-158 FROM SR-1002 (ACORN HILL ROAD) TO EAST OF PASQUOTANK COUNTY LINE. | 20776667.76 | 14 | 4.106 miles | FSC II LLC DBA FRED SMITH COMPANY | 0158076 | Brandon J. Tatum | 2526216400 | 2024-12-17 | 2025-03-17 | 2028-02-28 |  | 45.54% | 45.54% | 2026-04-30 | 2026-05-11 09:10
C204860 | 12 | Cleveland | BR-0012, R-4045 | Statewide | US-74 | US-74 AT SR-1168 (N ACADEMY ST/LATTIMORE RD) AND BRIDGES 220 048 AND 220049 ON US-74 OVER SANDY RUN CREEK. | 53095409 | 30 | 2.55 miles | ES WAGNER COMPANY LLC | 1168006 | Anne Burwell Schley, PE | 7044805580 | 2023-07-18 | 2023-08-28 | 2027-06-01 | 2027-06-24 | 56.14% | 56.14% | 2026-04-30 | 2026-05-08 09:10
C204861 | 2 | Lenoir | B-4926 | Regional | NC-55 | BRIDGE #530020 OVER NEUSE RIVER AND BRIDGE #530034 OVER NEUS E RIVER OVERFLOW ON NC-55. | 15552864.38 | 22 | 0.53 miles | S T WOOTEN CORPORATION | STATE FUNDED | Stanley L. Harrell | 2525270053 | 2024-05-28 | 2024-07-16 | 2028-01-11 | 2029-01-10 | 64.21% | 64.21% | 2026-05-07 | 2026-05-14 09:10
C204865 | 14 | Haywood | HB-0004 | Statewide | I-40 | BRIDGE #430243 OVER NC-215 (CHAMPION DRIVE) ON I-40. | 28324561.42 | 18 | 0.813 miles | WRIGHT BROTHERS CONSTRUCTION COMPANY INC | STATE FUNDED | Max L. Buchanan | 8285862141 | 2024-07-16 | 2024-10-16 | 2028-12-15 |  | 60.04% | 60.04% | 2026-05-07 | 2026-05-19 08:10
C204866 | 3 | Brunswick | I-6036 | Statewide | I-140 | I-140 FROM US-17 TO NORTH OF US-74. | 9551459.22 | 8 | 4.94 miles | HIGHLAND PAVING CO LLC | 0140003 | Nathan H. Tew | 9103412000 | 2023-11-21 | 2025-08-08 | 2025-06-15 | 2026-04-22 | 73.09% | 73.09% | 2026-04-30 | 2026-05-11 09:10
C204872 | 8 | Chatham | R-5930A | None | SR-2700 | CHATHAM PARKWAY FROM NORTH OF US-64 TO NORTH OF PROPOSED GRA NT DRIVE. | 13618880 | 24 | 0.852 miles | FSC II LLC DBA FRED SMITH COMPANY | STATE FUNDED | Gary Phillips | 9197769623 | 2023-08-15 | 2023-10-02 | 2026-02-28 |  | 92.58% | 92.58% | 2025-10-31 | 2025-11-14 12:00
C204873 | 4 | Johnston | I-5972 | None | I-95, US-70B | I-95 AND US-70 BUSINESS (MARKET STREET), EXIT 95 INTERCHANGE FROM OUTLET CENTER DRIVE TO WEST OF YELVERTON GROVE ROAD. | 38317295.15 | 25 | 1.031 miles | ZACHRY CONSTRUCTION CORPORATION | NHP-0095(045) | Jimmy L. Best | 9192091090 | 2023-11-21 | 2024-04-15 | 2027-12-12 |  | 75.64% | 75.64% | 2026-04-15 | 2026-04-29 09:10
C204878 | 13 | Buncombe | I-2513AA, I-2513AB | None | I-26, I-40 | I-40 FROM EAST OF SR-1224 TO PAVEMENT JOINT WEST OF SR-3412, AND I-26, I-40 AT I-40/US 19/23 INTERCHANGES IMPROVEMENTS | 105635755.92 | 15 | 2.75 miles | ARCHER WRIGHT JV | 0026024 | Thomas R. Veazey | 8282980080 | 2024-07-16 | 2025-02-10 | 2029-04-30 | 2029-09-13 | 37.25% | 37.25% | 2026-04-30 | 2026-05-14 09:10
C204879 | 9 | Forsyth | U-5824 | Regional | NC-66 | NC-66 (OLD HOLLOW ROAD) FROM HARLEY DRIVE TO US-158. | 27921302.16 | 28 | 1.807 miles | YATES CONSTRUCTION CO INC | STATE FUNDED | Joshua A. Miller | 3362939610 | 2023-11-21 | 2024-01-16 | 2027-04-13 | 2027-08-02 | 44.83% | 44.83% | 2026-04-30 | 2026-05-13 08:10
C204880 | 9 | Forsyth | U-6003 | None | NC-150 | NEW ROAD WITH BICYCLE/PEDESTRIAN ACCOMMODATIONS FROM SR-1969 (PINEY GROVE ROAD) TO NC-150 (NORTH MAIN STREET). | 10745693.35 | 28 | 0.962 miles | TRIANGLE GRADING & PAVING INC | STATE FUNDED | Nicholas C. Librandi | 3367477950 | 2023-11-21 | 2024-01-08 | 2027-01-11 |  | 84% | 84% | 2026-04-30 | 2026-05-19 08:10
C204883 | 13 | Rutherford | BR-0100 | Regional | NC-226 | BRIDGE #800040 OVER NORTH FORK FIRST BROAD CREEK ON NC-226. | 5593807.55 | 13 | 0.21 miles | KEMP SIGMON CONSTRUCTION CO INC | STATE FUNDED | Travis J. Henley | 8286527848 | 2025-02-18 | 2025-03-24 | 2027-03-30 | 2027-05-14 | 91.79% | 91.79% | 2026-04-22 | 2026-05-06 09:10
C204884 | 14 | Haywood | HB-0003 | Statewide | I-40 | I-40 FROM 0.348 MILES WEST OF SR-1550 (INCINERATOR RD) TO 0. 345 MILES EAST OF SR-1550 (INCINERATOR RD). | 23232932.81 | 17 | 0.693 miles | WRIGHT BROTHERS CONSTRUCTION COMPANY INC | STATE FUNDED | Max L. Buchanan | 8285862141 | 2024-07-16 | 2024-10-16 | 2028-04-01 |  | 57.83% | 57.83% | 2026-04-15 | 2026-04-22 08:10
C204887 | 14 | Cherokee | R-5861 | Statewide | US-19 | US-19/129 FROM GEORGIA STATE LINE TO US-64. | 67160518.63 | 26 | 3.773 miles | WRIGHT BROTHERS CONSTRUCTION COMPANY INC | 4742701 | J. Adam Dockery | 8283215061 | 2023-12-19 | 2024-02-05 | 2029-06-01 | 2029-06-02 | 44.69% | 44.69% | 2026-04-22 | 2026-05-07 10:10
C204904 | 14 | Transylvania | R-5799 | Statewide | US-64 | INTERSECTIONS OF US-64 / US-276 (HENDERSONVILLE HWY), AND US -64 / NC-280 (ASHEVILLE HWY). | 20388187.21 | 28 | 0.461 miles | MOUNTAIN CREEK CONTRACTORS INC | STATE FUNDED | Patrick A. Eubanks | 8288917911 | 2023-11-21 | 2024-01-08 | 2027-05-14 | 2027-06-08 | 45.85% | 45.85% | 2026-04-30 | 2026-05-05 08:10
C204908 | 7 | Guilford | Y-4807B | None | SR-3163 | RAILWAY-HIGHWAY CROSSING CLOSURE AT PINE STREET AND NORFOLK SOUTHERN CROSSING 722 957-L. | 4911720.11 | 11 | 0.092 miles | SMITH-ROWE, LLC | STPRR-0708(41) | Jacob T. Crews, PE | 3363751774 | 2024-05-28 | 2024-09-07 | 2026-02-11 |  | 41.98% | 41.98% | 2025-07-31 | 2025-08-20 08:10
C204913 | 9 | Forsyth | R-2577A | Statewide | US-158 | US-158 FROM MULTI-LANES NORTH OF US-421/I-40 BUSINESS TO SR- 1965 (BELEWS CREEK ROAD). | 87840567.41 | 21 | 5.804 miles | APAC ATLANTIC INC SMITH ROWE LLC JV | STATE FUNDED | Joshua A. Miller | 3362939610 | 2024-05-28 | 2024-08-19 | 2029-03-30 | 2029-07-06 | 38.57% | 38.57% | 2026-04-30 | 2026-05-18 08:10
C204915 | 8 | Randolph |  | None | NC-42 | 1 SECTION EACH OF NC-42, NC-42 SOUTH, NC-22, AND 13 SECTIONS OF SECONDARY ROADS. | 4348488.25 | 8 | 17.612 miles | TRUEROCK CONSTRUCTION LLC | STATE FUNDED | Joshua S. Brooks | 3363184020 | 2024-02-20 | 2025-07-21 | 2025-10-01 | 2026-06-15 | 90.21% | 90.21% | 2026-04-30 | 2026-05-11 09:10
C204917 | 8 | Montgomery |  | None | NC-134 | 1 SECTION EACH OF NC-134, NC-109 BUS, NC-109, US-220 ALT, AN D 4 SECTIONS OF SECONDARY ROADS. | 2368423.25 | 6 | 13.47 miles | NJR GROUP INC | STATE FUNDED | Joshua S. Brooks | 3363184020 | 2024-02-20 | 2025-07-07 | 2025-10-01 |  | 85.94% | 85.94% | 2026-04-30 | 2026-05-12 09:10
C204925 | 14 | Haywood | B-5982 | Statewide | US-74 | BRIDGE #430095 OVER SOUTHERN RAILROAD ON US-74. | 17679950.74 | 19 | 0.313 miles | NHM CONSTRUCTORS INC | STATE FUNDED | Max L. Buchanan | 8285862141 | 2024-08-20 | 2024-10-21 | 2028-02-11 |  | 43.46% | 43.46% | 2026-04-30 | 2026-05-07 10:10
C204933 | 8 | Chatham | R-5930B | None | SR-2700 | CHATHAM PARKWAY FROM NORTH OF PROPOSED GRANT DRIVE TO US-15/ US-501. | 14818648.21 | 10 | 1.483 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Jeremy B. Phillips | 9197769623 | 2025-03-18 | 2025-06-26 | 2028-02-11 |  | 16.78% | 16.78% | 2026-04-30 | 2026-05-12 09:10
C204935 | 11 | Yadkin | U-5809 | None | US-601 | US-601 (STATE ST) FROM SR-1742 (SHARON DR) TO SR-1146 (LEE A VE). | 19820039.01 | 17 | 0.678 miles | BLYTHE CONSTRUCTION INC | 4438201 | Benjamin D. Whitaker | 3368354241 | 2024-06-18 | 2024-12-09 | 2028-03-29 |  | 50.6% | 50.6% | 2026-04-30 | 2026-05-14 09:10
C204936 | 7 | Alamance | BR-0060 | Regional | NC-87 | BRIDGE #000014 OVER CANE CREEK ON NC-87. | 7695970.69 | 1 | 0.426 miles | KEMP SIGMON CONSTRUCTION CO INC | STATE FUNDED | Bobby J. Howell | 3365706830 | 2026-02-17 | 2026-03-31 | 2028-11-11 |  | 2.99% | 2.99% | 2026-04-07 | 2026-04-13 09:10
C204937 | 14 | Henderson | U-5783 | Statewide | US-64 | US-64 FROM SR-1180 (BLYTHE ST) TO SR-1173 (WHITE PINE DR)/SR -1186 (DANIEL DR). | 28223125.08 | 9 | 1.167 miles | TENNOCA CONSTRUCTION COMPANY | STATE FUNDED | Patrick A. Eubanks | 8288917911 | 2024-08-20 | 2025-05-29 | 2028-11-11 |  | 8.29% | 8.29% | 2026-05-07 | 2026-05-18 08:10
C204938 | 12 | Cleveland | B-5845 | Subregional | SR-2033 | BRIDGE #220025 OVER BUFFALO CREEK ON SR-2033 (OAK GROVE ROAD ). | 5199739.83 | 11 | 0.369 miles | SMITH-ROWE, LLC | STATE FUNDED | Anne Burwell Schley, PE | 7044805580 | 2025-03-18 | 2025-05-29 | 2027-03-30 | 2027-04-01 | 57.47% | 57.47% | 2026-05-07 | 2026-05-13 08:10
C204940 | 8 | Richmond | I-5979 | Statewide | US-74 | US-74 (FUTURE I-74) AT INTERCHANGE WITH US-1 (EXIT 311). | 8453440.09 | 13 | 0.695 miles | BARNHILL CONTRACTING CO | 0074227 | James A. Dietrich | 9109442344 | 2025-02-18 | 2025-04-05 | 2027-01-11 |  | 79.8% | 79.8% | 2026-04-15 | 2026-04-27 08:10
C204941 | 9 | Davidson | U-5757 | Regional | NC-8 | NC-8 (WINSTON RD) FROM US-29/US-70 TO SR-1846 (ARRINGTON DR) . | 13458673.9 | 18 | 0.771 miles | KEMP SIGMON CONSTRUCTION CO INC | STATE FUNDED | Eric T. Goldston | 7046303220 | 2024-09-17 | 2024-11-16 | 2027-05-14 | 2027-05-31 | 72.17% | 72.17% | 2026-04-30 | 2026-05-13 08:10
C204942 | 3 | New Hanover | U-6202 | Subregional | SR-2048 | SR-2048 (GORDON RD) FROM US-17 (MARKET ST) TO I-40. | 50843005.3 | 16 | 2.574 miles | S T WOOTEN CORPORATION | STATE FUNDED | Joshua T. Pratt | 9103989100 | 2024-11-19 | 2025-03-13 | 2029-12-12 | 2029-12-18 | 23.26% | 23.26% | 2026-04-30 | 2026-05-12 09:10
C204943 | 14 | Haywood | R-5921 | Statewide | US-276 | US-276 (JONATHAN CREEK RD) FROM US-19 TO 0.5 MILES SOUTH OF I-40. | 38576335.52 | 16 | 5.347 miles | WNC PAVING INC | 0276019 | Kenneth C. McCourt | 8284977333 | 2024-11-19 | 2025-01-13 | 2028-11-11 | 2028-12-20 | 37.62% | 37.62% | 2026-04-15 | 2026-04-22 08:10
C204944 | 5 | Granville | U-6020 | Regional | NC-56, SR-1215 | NC-56 (EAST C ST) INTERSECTION WITH SR-1215 (WEST LYON STATI ON RD). | 6239520.31 | 14 | 0.313 miles | SUNROCK INDUSTRIES LLC DBA CAROLINA SUNROCK LLC | STATE FUNDED | James M. Nordan, PE | 9193174760 | 2024-11-19 | 2025-02-15 | 2026-11-11 | 2026-11-12 | 79.33% | 79.33% | 2026-04-30 | 2026-05-14 09:10
C204948 | 12 | Iredell | I-5918 | Statewide | I-77 | I-77 FROM MILEMARKER 36.5 TO MILEMARKER 48.85. | 21385579.08 | 20 | 12.35 miles | MAYMEAD INC | 0077023 | Keith Anderson | 0 | 2024-07-16 | 2024-08-26 | 2026-11-01 |  | 74.97% | 74.97% | 2026-04-30 | 2026-05-11 09:10
C204949 | 8 | Moore | R-5726 | Regional | NC-211 | NC-211 FROM NC-73 TO WEST OF SR-1241 (HOLLY GROVE SCHOOL RD) . | 42688044.05 | 17 | 4.806 miles | S T WOOTEN CORPORATION | STATE FUNDED | James A. Dietrich | 9109442344 | 2024-11-19 | 2025-01-06 | 2028-03-29 | 2028-04-09 | 37.15% | 37.15% | 2026-04-30 | 2026-05-15 08:10
C204950 | 10 | Anson | BR-0062 | Statewide | US-52 | BRIDGE #030014 OVER S FORK JONES CREEK ON US-52. | 5435975 | 19 | 0.24 miles | ANSON CONTRACTORS INC | STATE FUNDED | Bradley S. Eagle | 7049834380 | 2024-06-18 | 2024-10-14 | 2027-03-14 | 2027-03-15 | 87.5% | 87.5% | 2026-04-30 | 2026-05-07 10:10
C204953 | 13 | Buncombe | I-2513B, I-2513D | None | I-26 | I-26/I-240 FROM SOUTH OF SR-3548 TO NORTH OF SR-1781 AND SR- 1477 FROM SR-1517 TO SR-1781. | 1147238700 | 22 | 3.206 miles | ARCHER WRIGHT JV | 3416501 | Thomas R. Veazey | 8282980080 | 2024-05-07 | 2024-06-24 | 2031-06-05 |  | 16.69% | 16.69% | 2026-03-31 | 2026-04-29 09:10
C204955 | 2 | Beaufort |  | Statewide | US-17 | BRIDGE #060353 OVER US-17 BUS/TAR RIVER ON US-17. | 6296460.59 | 1 | 2.893 miles | S T WOOTEN CORPORATION | STATE FUNDED | Jason B. Beasley | 2524392970 | 2026-02-17 | 2026-04-20 | 2028-06-01 |  | 9.51% | 9.51% | 2026-04-30 | 2026-05-11 09:10
C204956 | 13 | Burke, Caldwell | R-3430B | Subregional | SR-1001 | BRIDGE #110010 OVER CATAWBA RIVER ON SR-1001 (CONNELLY SPRIN GS RD). | 30874732.58 | 4 | 0.587 miles | BALFOUR BEATTY INFRASTRUCTURE INC | STATE FUNDED | Travis J. Henley | 8286527848 | 2025-08-19 | 2025-10-08 | 2029-03-30 |  | 7.14% | 7.14% | 2026-01-22 | 2026-03-02 10:10
C204960 | 13 | Rutherford |  | None | SR-MULTI | 26 SECTIONS OF SECONDARY ROADS. | 5031065.37 | 8 | 25.321 miles | APAC ATLANTIC INC DBA HARRISON CONSTRUCTION COMPANY | STATE FUNDED | Travis J. Henley | 8286527848 | 2024-06-18 | 2025-05-20 | 2025-11-21 |  | 85.59% | 85.59% | 2026-05-07 | 2026-05-20 09:10
C204966 | 10 | Mecklenburg | U-4713A | Subregional | SR-3440 | SR-3440 (MCKEE RD EXT) FROM SR-3448 (PLEASANT PLAINS RD) TO SR-1010 (E JOHN ST). | 10749727.9 | 13 | 0.912 miles | NJR GROUP INC | STATE FUNDED | Yanwei Ma | 7048475006 | 2024-10-15 | 2024-12-02 | 2027-03-30 | 2028-01-03 | 27.47% | 27.47% | 2026-04-30 | 2026-05-13 08:10
C204967 | 5 | Wake |  |  | - | BRIDGES #910001 AND #910538 OVER CRABTREE CREEK AND CLNA RAI LROAD ON SR-2911 (NEW BERN AVE). | 0 |  | 0.239 miles | AMERICAN CONTRACTING & SERVICES INC | STATE FUNDED | David W. Conner II | 9197077370 | 2025-11-18 |  | 2026-11-01 |  | 0% | 0%
C204968 | 5 | Wake | U-5746 | Statewide | US-401 | US-401 FROM SR-1467/SR-2839 (ALLEN ST) TO SR-1010 (TEN-TEN R D). | 6385000 | 13 | 0.638 miles | BRANCH CIVIL INC | STATE FUNDED | David W. Conner II | 9197077370 | 2024-11-19 | 2025-03-17 | 2026-12-12 |  | 38.11% | 38.11% | 2026-04-30 | 2026-05-11 09:10
C204969 | 10 | Anson | BR-0063 | Regional | NC-742 | BRIDGE #030087 OVER RICHARDSON CREEK ON NC-742. | 3783850 | 14 | 0.388 miles | SANFORD CONTRACTORS INC | STATE FUNDED | Bradley S. Eagle | 7049834380 | 2024-12-17 | 2025-01-27 | 2027-01-28 |  | 89.54% | 89.54% | 2026-04-30 | 2026-05-05 08:10
C204971 | 7 | Guilford | U-4758 | Subregional | SR-1818 | SR-1818 (JOHNSON ST)/SR-1850 (SANDY RIDGE RD) FROM SR-1820 ( SKEET CLUB RD) TO SOUTH OF I-40. | 68053984.72 | 5 | 4.467 miles | BLYTHE CONSTRUCTION INC | 0710027 | Leland J. Barber, PE | 3364877080 | 2025-09-16 | 2025-12-01 | 2030-03-28 |  | 10.39% | 10.39% | 2026-04-15 | 2026-04-24 08:10
C204972 | 4 | Johnston | BR-0086 | Statewide | US-301 | BRIDGE #500070 OVER NEUSE RIVER ON US-301. | 9415624.94 | 7 | 0.256 miles | S T WOOTEN CORPORATION | STATE FUNDED | Jimmy L. Best | 9192091090 | 2025-01-21 | 2025-06-02 | 2028-12-27 |  | 17.42% | 17.42% | 2026-03-31 | 2026-04-09 09:10
C204973 | 7 | Orange |  | None | NC-54 | 1 SECTION EACH OF NC-86, NC-751, NC-54/US 15-501 NORTH AND S OUTH, AND 2 SECTIONS OF SECONDARY ROADS. | 4888115.8 | 2 | 14.052 miles | SUNROCK INDUSTRIES LLC DBA CAROLINA SUNROCK LLC | STATE FUNDED | Bobby J. Howell | 3365706830 | 2024-08-20 | 2026-01-21 | 2026-09-15 |  | 7.01% | 7.01% | 2026-04-15 | 2026-04-27 08:10
C204975 | 9 | Forsyth | I-5880 | Statewide | I-40 | I-40/US-311 AT NC-109 INTERCHANGE. | 38891435.19 | 4 | 0.819 miles | BLYTHE CONSTRUCTION INC | 5308001 | Nicholas C. Librandi | 3367477950 | 2025-08-19 | 2026-01-05 | 2030-01-11 |  | 9.03% | 9.03% | 2026-04-30 | 2026-05-06 09:10
C204977 | 12 | Alexander, Catawba |  | None | NC-127 | BRIDGE #170091 OVER THE CATAWBA RIVER ON NC-127 AND BRIDGE # 170139 OVER THE CATAWBA RIVER ON NC-16. | 2434000 | 1 | 0.33 miles | AMERICAN CIVIL CONSTRUCTORS WEST COAST LLC | STATE FUNDED | Eric W. Conner | 8284686260 | 2025-08-19 | 2026-04-06 | 2026-10-15 |  | 8.16% | 8.16% | 2026-05-07 | 2026-05-18 08:10
C204978 | 9 | Stokes | B-5766 | Subregional | SR-1674 | BRIDGE #840082 OVER THE DAN RIVER ON SR-1674 (SHEPPARD MILL ROAD). | 6592205.52 | 9 | 0.213 miles | SMITH-ROWE, LLC | STATE FUNDED | Scott A. Jones | 9197072400 | 2025-02-18 | 2025-06-06 | 2028-01-28 |  | 40.39% | 40.39% | 2026-03-31 | 2026-04-13 09:10
C204979 | 9 | Davie | BR-0152 | Subregional | SR-1436 | BRIDGE #290076 OVER I-40 ON SR-1436 (PINEBROOK SCHOOL RD). | 4230585.11 | 11 | 0.189 miles | SMITH-ROWE, LLC | 5160001 | Larry B. Shaver | 3362496255 | 2025-02-18 | 2025-06-12 | 2027-01-28 | 2027-02-02 | 83.05% | 83.05% | 2026-04-30 | 2026-05-18 08:10
C204980 | 9 | Forsyth | U-5536 | None | SR-1001 | GREAT WAGON ROAD FROM SR-1001 (SHALLOWFORD ROAD) TO SR-1308 (LEWISVILLE-VIENNA ROAD). | 19785000 | 13 | 1.13 miles | BRANCH CIVIL INC | STATE FUNDED | Joshua A. Miller | 3362939610 | 2025-02-18 | 2025-03-31 | 2029-03-14 |  | 45.87% | 45.87% | 2026-04-30 | 2026-05-11 09:10
C204981 | 5 | Franklin, Wake |  | None | NC-50, NC-561 | 1 SECTION OF NC-561, AND 1 SECTION OF NC-50. | 2827962.75 | 5 | 17.205 miles | S T WOOTEN CORPORATION | STATE FUNDED | David B. Moore | 9192204600 | 2024-09-17 | 2025-03-15 | 2026-09-15 |  | 56.56% | 56.56% | 2026-04-30 | 2026-05-20 09:10
C204982 | 5 | Wake |  | None | NC-54, SR-1011, SR-1203, SR-1204, SR-1342, SR-1644, SR-1649, SR-1766, SR-3038, SR-3046, SR-3047, SR-3056, SR-3106, SR-3107, SR-3133, SR-5878 | 1 SECTION OF NC-54 AND 15 SECTIONS OF SECONDARY ROADS. | 4778464.39 | 1 | 17.653 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Alexander S. Griffis | 9198358200 | 2024-09-17 | 2026-03-24 | 2026-09-15 |  | 6.9% | 6.9% | 2026-04-22 | 2026-05-01 09:10
C204983 | 2 | Carteret |  | Regional | NC-24 | 1 SECTION OF NC-24. | 9007631.43 | 5 | 18.59 miles | S T WOOTEN CORPORATION | STATE FUNDED | Brad T. McMannen, PE | 2526496520 | 2024-10-15 | 2025-10-02 | 2026-12-15 | 2026-12-18 | 51.84% | 51.84% | 2026-04-30 | 2026-05-06 09:10
C204984 | 3 | Onslow |  | None | NC-24, SR-1529, SR-1530, SR-1531 | 1 SECTION OF NC-24, AND 3 SECTIONS OF SECONDARY ROADS. | 4960455.77 | 6 | 13.55 miles | S T WOOTEN CORPORATION | STATE FUNDED | Bradley L. Haste | 9103475258 | 2024-10-15 | 2025-09-02 | 2026-06-15 | 2026-06-16 | 91.14% | 91.14% | 2026-04-30 | 2026-05-12 09:10
C204985 | 9 | Forsyth |  | None | SR-1001, SR-1604, SR-1611, SR-1620, SR-1686, US-158 | 1 SECTION OF OF US-158, AND 5 SECTIONS OF SECONDARY ROADS. | 6804756.58 | 3 | 19.235 miles | APAC ATLANTIC INC THOMPSON ARTHUR DIVISION | STATE FUNDED | Scott A. Jones | 9197072400 | 2024-10-15 | 2025-06-27 | 2026-10-30 |  | 16.18% | 16.18% | 2025-08-31 | 2025-09-10 08:10
C204987 | 5 | Wake | W-5601EX | Regional | NC-42 | NC-42 FROM WEST OF SR-2734 (MARY HOBBY ROAD) TO EAST OF SR-5 367 (WINTERTON DRIVE) AND A TURN LANE ON NC 42 FOR SR-2727. | 4522370 | 12 | 0.593 miles | CARDINAL CIVIL CONTRACTING LLC | HSIP-0042(066) | David W. Conner II | 9197077370 | 2024-11-19 | 2025-01-06 | 2026-11-11 |  | 64.34% | 64.34% | 2026-02-15 | 2026-02-24 08:10
C204988 | 6 | Cumberland | U-3422A | Subregional | SR-1003 | SR-1003 (CAMDEN RD) FROM PROPOSED FAYETTEVILLE OUTER LOOP TO WEST OF SR-1112 (ROCKFISH RD). | 20241370.74 | 14 | 1.622 miles | HIGHLAND PAVING CO LLC | STATE FUNDED | Spencer G. Shoffner, PE | 9103640607 | 2024-12-17 | 2025-04-21 | 2028-12-12 | 2028-12-18 | 44.05% | 44.05% | 2026-04-22 | 2026-04-30 09:10
C204989 | 12 | Iredell | I-5919 | Statewide | I-77 | I-77 FROM MILEMARKER 52.6 TO MILEMARKER 56.77. | 7563219.1 | 4 | 4.17 miles | MAYMEAD INC | 4592601 | Justin T. Johnson | 7043806050 | 2025-02-18 | 2026-03-18 | 2026-09-01 |  | 16.02% | 16.02% | 2026-04-30 | 2026-05-11 09:10
C204991 | 10 | Mecklenburg | BP10-R013 | Subregional | SR-5469 | BRIDGE #590165 OVER COFFEY CREEK ON SR-5469 (SHOPTON RD). | 6807682 | 4 | 0.315 miles | BLYTHE DEVELOPMENT LLC | STATE FUNDED | Brian D. Davis, PE | 7048475006 | 2025-08-19 | 2026-01-06 | 2028-01-11 |  | 22.49% | 22.49% | 2026-04-30 | 2026-05-12 09:10
C204992 | 8 | Hoke | R-5709C | Regional | NC-211 | NC-211 FROM NORTH OF SR-1225 (ASHEMONT RD) TO EAST OF SR-124 4 (W PALMER ST)/SR-1311 (MOCKINGBIRD HILL RD). | 90150409.46 | 17 | 9.621 miles | BARNHILL CONTRACTING CO | STATE FUNDED | James A. Dietrich | 9109442344 | 2025-01-21 | 2025-03-07 | 2029-04-30 |  | 38.52% | 38.52% | 2026-04-30 | 2026-05-12 09:10
C204993 | 14 | Swain |  | Statewide | US-19 | BRIDGE #860008 OVER LITTLE TENNESSEE RIVER ON US-19/74. | 2963231.5 | 3 | 0.152 miles | LANFORD BROTHERS CO INC | STATE FUNDED | Kenneth C. McCourt | 8284977333 | 2025-09-16 | 2026-01-19 | 2027-10-01 |  | 19.66% | 19.66% | 2026-05-15
C204994 | 6 | Columbus | HI-0018 | Statewide | US-74 | US-74 (FUTURE I-74) FROM 0.11 MILES EAST OF US-701 BUSINESS TO 0.17 MILES WEST OF NC-214. | 22950355.5 | 13 | 17.863 miles | S T WOOTEN CORPORATION | 0074(247) | Jason A. Johnson | 9107886300 | 2025-02-18 | 2025-04-15 | 2027-06-01 | 2027-06-05 | 85.37% | 85.37% | 2026-04-22 | 2026-05-06 09:10
C204995 | 5 | Wake |  | None | SR-1993, SR-2007, SR-2008, SR-2011, SR-2183, SR-2224, SR-2227, SR-2338, SR-2434, SR-2435, SR-3540, SR-3541, SR-3542, SR-3543, SR-4501, SR-4502, SR-4517, SR-4529, SR-4560, SR-4561, SR-4568, SR-4569, SR-4582, SR-4583, SR-5240, SR-5252, SR-5431 | 27 SECTIONS OF SECONDARY ROADS. | 2739024.15 | 8 | 15.175 miles | FSC II LLC DBA FRED SMITH COMPANY | STATE FUNDED | Alexander S. Griffis | 9198358200 | 2024-11-19 | 2025-03-10 | 2026-09-15 |  | 81.81% | 81.81% | 2026-03-31 | 2026-04-09 09:10
C204996 | 6 | Cumberland, Robeson | U-2519F |  | I-295 | I-295 FROM SOUTHERN I-95 INTERCHANGE TO NORTHERN I-95 INTERC HANGE. | 0 |  | 34 miles | FULCHER ELECTRIC OF FAYETTEVILLE INC | 0295009 | Spencer G. Shoffner, PE | 9103640607 | 2026-03-17 | 2026-06-01 | 2027-10-01 |  | 0% | 0%
C204997 | 8 | Moore |  | None | - | 1 SECTION OF US-1, 2 SECTIONS OF NC-24, 2 SECTIONS OF NC-690 , AND 8 SECTIONS OF SECONDARY ROADS. | 5050317.56 | 7 | 29.675 miles | S T WOOTEN CORPORATION | STATE FUNDED | James A. Dietrich | 9109442344 | 2024-11-19 | 2025-08-02 | 2026-10-01 |  | 56.6% | 56.6% | 2026-04-22 | 2026-05-04 10:54
C204998 | 7 | Alamance |  | None | NC-49 | 1 SECTION OF NC-49/NC-54/NC-87 AND 3 SECTIONS OF SECONDARY R OADS. | 5762575 | 9 | 14.44 miles | FSC II LLC DBA FRED SMITH COMPANY | STATE FUNDED | Bobby J. Howell | 3365706830 | 2024-11-19 | 2025-08-10 | 2026-08-01 |  | 73.31% | 73.31% | 2026-04-22 | 2026-05-06 09:10
C204999 | 1 | Dare, Tyrrell | HB-0001 | Statewide | US-64 | BRIDGE #880007 OVER THE ALLIGATOR RIVER ON US-64. | 449777300 | 16 | 0 miles | SKANSKA USA CIVIL SOUTHEAST INC | 0001156 | Pablo A. Hernandez, PE | 2524733637 | 2024-12-02 | 2025-01-22 | 2030-04-19 |  | 42.73% | 42.73% | 2026-04-30 | 2026-05-11 09:10
C205001 | 12 | Gaston | I-5719B, U-5800 | None | I-5719B | NC-7 (MAIN ST) INTERSECTION WITH US-29/74 (WILKINSON BLVD), AND I-85 FROM NC-7 TO EAST OF NC-273. | 336985000 | 6 | 5.16 miles | THE LANE CONSTRUCTION CORPORATION | FUTR085 | Darin L. Waller, PE | 7044805400 | 2025-06-24 | 2025-07-28 | 2030-09-01 |  | 6.17% | 6.17% | 2026-05-07 | 2026-05-11 09:10
C205002 | 8 | Lee |  | None | - | 1 SECTION OF US-15, 1 SECTION OF US-421, 1 SECTION OF NC-87, AND 12 SECTIONS OF SECONDARY ROADS. | 3884595.94 | 2 | 20.109 miles | S T WOOTEN CORPORATION | STATE FUNDED | Jeremy B. Phillips | 9197769623 | 2024-11-19 | 2026-02-25 | 2026-10-01 |  | 58.27% | 58.27% | 2026-04-15 | 2026-04-29 09:10
C205003 | 7 | Alamance |  | None | SR-2328 | 15 SECTIONS OF SECONDARY ROADS. | 4441807.39 | 7 | 18.85 miles | APAC ATLANTIC INC THOMPSON ARTHUR DIVISION | STATE FUNDED | Bobby J. Howell | 3365706830 | 2024-12-17 | 2025-07-08 | 2026-07-17 |  | 60.87% | 60.87% | 2026-04-15 | 2026-04-22 08:10
C205004 | 12 | Cleveland |  | None | NC-18 | 1 SECTION OF NC-18, 1 SECTION OF NC-216, AND 5 SECTIONS OF S ECONDARY ROADS. | 5104283.38 | 5 | 17.9 miles | ASPHALT PAVING OF SHELBY INC | STATE FUNDED | Wesley S. Clary | 7044802080 | 2024-12-17 | 2025-11-20 | 2026-08-15 |  | 43.61% | 43.61% | 2026-04-30 | 2026-05-07 10:10
C205007 | 5 | Durham |  | None | SR-1473, SR-1474, SR-1549, SR-1607, SR-1616, SR-1708, SR-1751, SR-1798, SR-1799, SR-1820, SR-1849, SR-1868, SR-1882, SR-1883, SR-1887, SR-1892, SR-1901, SR-1912, SR-2006, SR-2051, SR-2086, SR-2089, SR-2091, SR-2092, SR-2142, SR-2426, SR-2427, SR-2539, SR-2600, SR-2601, US-15, US-70 | 2 SECTIONS OF US 15 BUSINESS, 2 SECTIONS OF US 70 BUSINESS, AND 31 SECTIONS OF SECONDARY ROADS. | 5249707.8 | 7 | 22.567 miles | SUNROCK INDUSTRIES LLC DBA CAROLINA SUNROCK LLC | STATE FUNDED | James M. Nordan, PE | 9193174760 | 2025-01-21 | 2025-08-18 | 2026-09-15 |  | 59.7% | 59.7% | 2026-04-30 | 2026-05-12 09:10
C205008 | 8 | Chatham |  | None | - | 1 SECTION OF US-1 N WITH 6 RAMPS, 1 SECTION OF US-64 BUSINES S, AND 1 SECTION OF NC-42. | 3609091.19 | 2 | 16.439 miles | S T WOOTEN CORPORATION | STATE FUNDED | Jeremy B. Phillips | 9197769623 | 2024-12-17 | 2025-09-02 | 2026-10-01 |  | 36.15% | 36.15% | 2025-12-15 | 2026-01-13 09:10
C205010 | 11 | Wilkes |  |  | - | BRIDGE #960068 OVER WARRIOR CREEK ON NC-268. | 0 |  | 0.103 miles | SAFFO CONTRACTORS INC | STATE FUNDED | Christopher S. Pipes | 3369039170 | 2025-12-16 |  | 2027-05-15 |  | 0% | 0%
C205011 | 13 | Buncombe |  |  | SR-1620 | BRIDGE #100007 OVER FRENCH BROAD RIVER/NSRR ON SR-1620 (FLET CHER MARTIN RD). | 0 |  | 0.09 miles | LORR CONSTRUCTION INC | STATE FUNDED | Thomas R. Veazey | 8282980080 | 2025-10-21 | 2026-03-20 | 2027-09-01 |  | 0% | 0%
C205012 | 9 | Forsyth | U-5760 | Subregional | SR-2649 | BIG MILL FARM RD FROM S OF US-421 TO SR-2649, SR-2649 FROM B IG MILL FARM RD TO NC-66, & INT OF US-421 & BIG MILL FARM RD | 59776710.28 | 3 | 2.034 miles | APAC ATLANTIC INC SMITH ROWE LLC JV | STATE FUNDED | Nicholas C. Librandi | 3367477950 | 2025-11-18 | 2026-02-12 | 2031-01-28 |  | 6.74% | 6.74% | 2026-04-30 | 2026-05-14 09:10
C205013 | 10 | Mecklenburg | HL-0025 |  | - | GREYLOCK RIDGE RD FROM EAST JOHN ST TO TANK TOWN RD. | 0 |  | 0.27 miles | MOUNTAINEER CONTRACTORS INC AND SUBSIDIARIES | STATE FUNDED | Brian D. Davis, PE | 7048475006 | 2026-03-17 |  | 2028-02-28 |  | 0% | 0%
C205014 | 4 | Johnston |  | Statewide | SR-1923, US-70 | BRIDGE #500608 OVER NEUSE RIVER ON SR-1923 AND BRIDGE #50004 2 OVER I-95 ON US-70. | 1915000 | 4 | 0.619 miles | AMERICAN CIVIL CONSTRUCTORS WEST COAST LLC | STATE FUNDED | Jimmy L. Best | 9192091090 | 2025-06-17 | 2025-12-15 | 2026-06-01 | 2026-06-02 | 90.27% | 90.27% | 2026-05-02 | 2026-05-11 09:10
C205015 | 14 | Haywood | B-5541 | Statewide | I-40 | BRIDGE #430236 OVER SR-1513 ON I-40. | 18127600.82 | 8 | 0.473 miles | ZACHRY CONSTRUCTION CORPORATION | STATE FUNDED | Max L. Buchanan | 8285862141 | 2025-06-17 | 2025-10-14 | 2029-04-15 |  | 17.91% | 17.91% | 2026-05-15
C205016 | 9 | Davidson | B-5777 | Regional | NC-109 | REPLACE BRIDGE #58 OVER US-64 ON NC-109. | 7680854.06 | 8 | 0.406 miles | APAC ATLANTIC INC THOMPSON ARTHUR DIVISION | STATE FUNDED | Larry B. Shaver | 3362496255 | 2025-06-17 | 2025-08-04 | 2027-12-12 |  | 33.49% | 33.49% | 2026-03-31 | 2026-04-24 08:10
C205017 | 14 | Henderson |  | Statewide | US-64 | US-64 (CHIMNEY ROCK RD) FROM SR-1613 (SLICK ROCK RD, MM 22.7 9) TO SR-1701 (ROCK BROAD RIVER RD, MM 25.06). | 32849408.89 | 14 | 2.27 miles | BLYTHE CONSTRUCTION INC | HELENE | Michael D. Patton | 8285862141 | 2025-01-21 | 2025-03-03 | 2027-06-30 | 2027-08-10 | 49.25% | 49.25% | 2026-04-24 | 2026-04-28 09:10
C205018 | 7 | Rockingham | I-5898 |  | I-73 | UPGRADE FUTURE I-73/US-220 AT US-311/NC-135 INTERCHANGE AND REPLACE BRIDGE #780074. | 0 |  | 0.514 miles | SMITH-ROWE, LLC | STATE FUNDED | Jacob B. Harris, PE | 3365206060 | 2025-12-16 |  | 2029-04-30 |  | 0% | 0%
C205019 | 13 | McDowell | 1, 2, 3 | None | SR-1569, SR-1573 | BRIDGE #580115 ON SR-1569 AND BRIDGE #580111 ON SR-1573: BOT H OVER NORTH FORK CATAWBA RIVER. | 3170014 | 12 | 0.117 miles | R E BURNS & SONS CO INC | HELENE | Travis J. Henley | 8286527848 | 2024-12-19 | 2025-01-27 | 2026-10-01 | 2026-12-04 | 72.3% | 72.3% | 2026-04-30 | 2026-05-14 09:10
C205020 | 13 | McDowell |  | None | SR-1571, US-221 | BRG #580119 ON US-221 AND BRG #580285 ON SR-1571: BOTH OVER NORTH FORK CATAWBA RIVER. | 4819886.62 | 4 | 0.107 miles | SMITH-ROWE, LLC | HELENE | Travis J. Henley | 8286527848 | 2025-01-13 | 2025-04-23 | 2026-10-01 | 2026-10-15 | 33.21% | 33.21% | 2026-04-28 | 2026-05-04 10:54
C205021 | 13 | McDowell | TIP, TIP 2 | None | SR-1407, US-70 | BRIDGE #580044 OVER CURTIS CREEK ON US-70 AND BRIDGE #580090 OVER MILL CREEK ON SR-1407. | 4562500 | 14 | 0 miles | S T WOOTEN CORPORATION | HELENE | Travis J. Henley | 8286527848 | 2025-01-09 | 2025-02-19 | 2026-10-01 | 2026-10-28 | 60.04% | 60.04% | 2026-04-30 | 2026-05-18 08:10
C205022 | 13 | Yancey | TIP, TIP 2 | None | - | BRG #990047 OVER MINE FORK CREEK ON SR-1416 AND BRG #990014 OVER BANKS CREEK ON SR-1136. | 3696600 | 12 | 0 miles | BUCKEYE BRIDGE LLC | HELENE | Robert T. Cousins | 5403206428 | 2025-01-21 | 2025-02-13 | 2026-10-01 |  | 25.71% | 25.71% | 2026-03-31 | 2026-04-09 09:10
C205023 | 13 | Yancey | TIP, TIP 2, TIP 3 | None | - | BRG #990100 AND BRG #990062 BOTH ON SR-1153, AND BRG #990097 ON SR-1152. | 10449600 | 12 | 0 miles | SANFORD CONTRACTORS INC | HELENE | Robert T. Cousins | 5403206428 | 2025-01-21 | 2025-02-13 | 2026-10-01 |  | 12.37% | 12.37% | 2026-03-31 | 2026-04-30 09:10
C205024 | 13 | Mitchell, Yancey | TIP, TIP 2, TIP 3 | None | - | BRG #600123 OVER CHARLES CRK ON SR-1345, BRG #600154 OVER CA NE CRK ON SR-1188, BRG #990194 OVER N TOE RIVER ON SR-1314. | 7600000 | 10 | 0 miles | MOUNTAIN CREEK CONTRACTORS INC | HELENE | Robert T. Cousins | 5403206428 | 2025-01-21 | 2025-02-25 | 2026-10-01 |  | 28.18% | 28.18% | 2026-03-31 | 2026-04-16 08:10
C205025 | 13 | Buncombe | TIP, TIP 2, TIP 4, TIP3 | None | - | BRG #100716 ON SR-2832, BRG #100394 ON SR-2783, BRG #100396 ON SR-2810, BRG #100118 ON SR-2782, BRG #100464 ON SR-2782. | 6389388.1 | 10 | 0 miles | S T WOOTEN CORPORATION | HELENE | Robert T. Cousins | 5403206428 | 2025-01-21 | 2025-02-19 | 2026-10-01 |  | 26.76% | 26.76% | 2026-03-31 | 2026-04-24 08:10
C205026 | 13 | Buncombe | TIP, TIP 2, TIP 3, TIP 4 | None | - | BRG #100428 ON SR-2429, BRG #100203 ON SR-2416, BRG #100307 ON SR-2426, AND BRG #100424 ON SR-2786. | 7561270 | 9 | 0 miles | NHM CONSTRUCTORS INC | HELENE | Robert T. Cousins | 5403206428 | 2025-02-18 | 2025-03-13 | 2026-10-01 |  | 43.35% | 43.35% | 2026-04-30 | 2026-05-18 08:10
C205027 | 13 | Buncombe | TIP, TIP 2, TIP 3, TIP 4 | None | NC-197 | BRG #100200 AND BRG #100175 BOTH ON NC-197, BRG #100147 ON S R-2173, AND BRG #100139 ON SR-2171. | 7477000 | 11 | 0 miles | LEE CONSTRUCTION CO OF THE CAROLINAS IN | HELENE | Thomas R. Veazey | 8282980080 | 2025-02-18 | 2025-04-01 | 2026-10-01 |  | 50.99% | 50.99% | 2026-04-30 | 2026-05-11 09:10
C205028 | 13 | Buncombe | TIP, TIP 2 | None | SR-2513 | BRG #100135 ON SR-2153, AND BRG #100132 ON SR-2150 BOTH OVER IVY CREEK. | 5515353 | 10 | 0 miles | REEVES CONSTRUCTION COMPANY | HELENE | Thomas R. Veazey | 8282980080 | 2025-02-18 | 2025-04-01 | 2026-10-01 | 2026-10-29 | 32.98% | 32.98% | 2026-04-30 | 2026-05-12 09:10
C205029 | 13 | Madison | TIP, TIP 2 | None | SR-1183, SR-1576 | BRIDGE #560042 OVER IVY CREEK ON SR-1576 (BEND OF IVY RD) AN D BRIDGE #560304 OVER SR-1183 (UPPER SHUTIN RD.) | 5900000 | 11 | 0 miles | KEMP SIGMON CONSTRUCTION CO INC | HELENE | Colby D. Justice | 8286589439 | 2025-02-18 | 2025-03-31 | 2026-10-01 |  | 16.59% | 16.59% | 2026-05-07 | 2026-05-20 09:10
C205030 | 13 | Yancey | 1, 2 | None | - | BRIDGE #990173 OVER MIDDLE CREEK ON SR-1159, AND BRIDGE #990 156 OVER COLBERT CREEK ON SR-1158. | 3046805 | 13 | 0 miles | R E BURNS & SONS CO INC | HELENE | Robert T. Cousins | 5403206428 | 2025-03-18 | 2025-04-09 | 2026-11-01 |  | 22.86% | 22.86% | 2026-04-30
C205031 | 13 | Buncombe, McDowell | TIP, TIP 2 | None | SR-1546, SR-2802 | BRIDGE #580345 OVER ARMSTRONG CREEK ON SR-1546 AND BRIDGE #1 00110 OVER BROAD RIVER ON SR-2802. | 3549434.43 | 11 | 0 miles | ES WAGNER COMPANY LLC | HELENE | Travis J. Henley | 8286527848 | 2025-01-09 | 2025-03-01 | 2026-10-01 |  | 55.75% | 55.75% | 2026-04-30 | 2026-05-15 08:10
C205032 | 8 | Chatham | R-5963A | Subregional | SR-2700 | SR-2700 (CHATHAM PARK WAY) FROM US-15/US-501 SOUTH OF PITTSB ORO TO US-64 BUSINESS. | 39590000 | 8 | 3.174 miles | FSC II LLC DBA FRED SMITH COMPANY | STATE FUNDED | Jeremy B. Phillips | 9197769623 | 2025-05-20 | 2025-09-02 | 2029-04-30 |  | 38.11% | 38.11% | 2026-04-15 | 2026-04-27 08:10
C205033 | 1 | Bertie | BR-0153 | Regional | NC-11 | BRIDGE #070024 OVER CASHIE RIVER ON NC-11. | 4295107.09 | 5 | 0.455 miles | S T WOOTEN CORPORATION | 5183101 | Edwin W. Rose | 2525136030 | 2025-09-16 | 2025-11-20 | 2027-11-03 |  | 30.47% | 30.47% | 2026-04-30 | 2026-05-08 09:10
C205034 | 1 | Northampton | R-5739 | Regional | NC-46 | NC-46 FROM THE VIRGINIA STATE LINE TO NC-48. | 40135000 | 5 | 10.375 miles | FSC II LLC DBA FRED SMITH COMPANY | STATE FUNDED | Edwin W. Rose | 2525136030 | 2025-10-21 | 2025-12-03 | 2029-05-14 |  | 14.92% | 14.92% | 2026-04-30 | 2026-05-08 09:10
C205035 | 4 | Wayne | U-3609B |  | US-13 | US-13 (BERKELEY BLVD) FROM SR-1003 (NEW HOPE RD) TO US-70 BY PASS. | 0 |  | 2.366 miles | BRANCH CIVIL INC | STATE FUNDED | Jason M. Lee | 9197395300 | 2026-02-17 | 2026-06-15 | 2030-03-30 |  | 0% | 0%
C205036 | 6 | Robeson | U-5797 |  | - | SR-1997 (FAYETTEVILLE RD) FROM FARRINGDOM ST TO EAST 22ND ST . | 0 |  | 1.304 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Joseph M. Parker, Jr., PLS | 9103640600 | 2026-02-17 |  | 2030-11-11 |  | 0% | 0%
C205037 | 9 | Davidson | BR-0015 | None | US-29 | BRIDGE #280067 AND #280068 OVER SR-1192 ON US-29/US-70. | 21685504.7 | 7 | 0.71 miles | SMITH-ROWE, LLC | STATE FUNDED | Larry B. Shaver | 3362496255 | 2025-06-17 | 2025-10-27 | 2029-03-30 | 2029-04-19 | 15.33% | 15.33% | 2026-04-30 | 2026-05-18 08:10
C205038 | 5 | Wake | HL-0008I |  | - | INTERSECTION OF SR-1006 (OLD STAGE RD) AND SR-2736 (ROCK SER VICE STATION RD). | 0 |  | 0.836 miles | FSC II LLC DBA FRED SMITH COMPANY | STATE FUNDED | Niklaus C. Winkler | 9197339499 | 2026-03-17 |  | 2028-04-29 |  | 0% | 0%
C205039 | 10 | Mecklenburg | U-4913A | Subregional | SR-3174 | SR-3174 (IDLEWILD RD) FROM SR-3175 (STALLINGS RD) TO I-485. | 8676763.3 | 6 | 0.531 miles | J T RUSSELL & SONS INC | STATE FUNDED | Jake R. Koltiska | 7042185125 | 2025-08-19 | 2025-10-15 | 2027-03-29 | 2027-06-01 | 21.96% | 21.96% | 2026-04-30 | 2026-05-08 09:10
C205040 | 3 | Onslow | U-5789 | None | -, NC-53, SR-2714 | INTERSECTION OF NC-53 (WESTERN BLVD) AND SR-2714 (JACKSONVIL LE PARKWAY). | 8535183.25 | 4 | 0.597 miles | BARNHILL CONTRACTING CO | 4436101 | Bradley L. Haste | 9103475258 | 2025-09-16 | 2026-01-09 | 2028-02-28 |  | 15.21% | 15.21% | 2026-04-30 | 2026-05-08 09:10
C205041 | 9 | Forsyth | U-5899 | None | SR-3955 | FORUM PARKWAY CONNECTOR FROM SR-3955 (FORUM PARKWAY) TO NC-6 6 (UNIVERSITY PARKWAY). | 13453482.21 | 7 | 0.542 miles | SMITH-ROWE, LLC | STATE FUNDED | Joshua A. Miller | 3362939610 | 2025-06-17 | 2025-07-28 | 2029-03-30 | 2029-04-05 | 28.57% | 28.57% | 2026-04-30 | 2026-05-11 09:10
C205042 | 8 | Moore | U-3628 | Regional | NC-24 | NC-24/NC-27 FROM WEST OF NC-22 (MCNEILL ST) TO US-15/US-501. | 4955597 | 6 | 1.028 miles | FSC II LLC DBA FRED SMITH COMPANY | 4467201 | Joshua S. Brooks | 3363184020 | 2025-09-16 | 2025-11-20 | 2027-05-14 |  | 34.39% | 34.39% | 2026-04-30 | 2026-05-06 09:10
C205043 | 12 | Catawba | U-5777 | Regional | NC-127 | NC-127 FROM 1ST AVENUE SOUTHEAST TO 2ND AVENUE SOUTHEAST. | 8533742.68 | 9 | 0.264 miles | CATON CONSTRUCTION GROUP INC | 5018901 | Eric W. Conner | 8284686260 | 2025-05-20 | 2025-10-31 | 2027-04-30 |  | 13.36% | 13.36% | 2026-04-30 | 2026-05-07 10:10
C205044 | 11 | Surry, Yadkin | B-5831 | Statewide | I-77 | BRIDGE #850006 OVER NC-268, SOUTHERN RAILROAD TRACKS, AND TH E YADKIN RIVER ON I-77. | 16781818.32 | 2 | 0.371 miles | SMITH-ROWE, LLC | 0077006 | Benjamin D. Whitaker | 3368354241 | 2025-11-18 | 2026-02-13 | 2028-11-28 | 2028-12-09 | 15.73% | 15.73% | 2026-04-30 | 2026-05-19 08:10
C205045 | 5 | Wake |  | Statewide | US-1 | 1 SECTION OF US-1 AND RAMPS. | 5597435.4 | 6 | 13.243 miles | BLYTHE CONSTRUCTION INC | STATE FUNDED | David W. Conner II | 9197077370 | 2025-01-21 | 2025-09-30 | 2026-09-15 |  | 71.83% | 71.83% | 2026-04-30 | 2026-05-11 09:10
C205046 | 8 | Hoke, Scotland |  | None | - | 1 SECTION OF US-401, 1 SECTION OF NC-79, AND 6 SECTIONS OF S ECONDARY ROADS. | 3098525.41 | 3 | 15.34 miles | BARNHILL CONTRACTING CO | STATE FUNDED | James A. Dietrich | 9109442344 | 2025-01-21 | 2025-06-10 | 2026-10-01 |  | 50.38% | 50.38% | 2026-04-15 | 2026-04-24 08:10
C205047 | 13 | Buncombe | 1, 2, 3 | None | - | BRIDGE #100115 ON SR-2789, BRIDGE #100308 ON SR-2419, AND BR IDGE #100380 ON SR-2432. | 6151245 | 13 | 0 miles | R E BURNS & SONS CO INC | HELENE | Robert T. Cousins | 5403206428 | 2025-03-18 | 2025-04-09 | 2026-11-01 |  | 22.5% | 22.5% | 2026-04-30
C205048 | 12 | Catawba |  | None | NC-10 | 1 SECTION OF NC-10, AND 53 SECTIONS OF SECONDARY ROADS. | 4777967 | 1 | 20.75 miles | MAYMEAD INC | STATE FUNDED | Travis R. Jordan | 7047482400 | 2025-02-18 | 2026-01-28 | 2026-09-21 |  | 19.48% | 19.48% | 2026-03-31 | 2026-04-09 09:10
C205049 | 13 | Buncombe | HL-0003 | Statewide | US-19 | US-19/US-23 BUS (HAYWOOD RD) FROM US-19/US-23/US-74 (PATTON AVE) TO RIDGELAWN RD. | 6985218.75 | 3 | 1.91 miles | WATSON CONTRACTING INC | 0019064 | Thomas R. Veazey | 8282980080 | 2025-02-18 | 2026-02-09 | 2026-11-01 |  | 36.4% | 36.4% | 2026-04-30 | 2026-05-20 09:10
C205050 | 14 | Haywood |  | None | SR-1101 | BRIDGE #430002 ON SR-1101, BRIDGE #430034 ON SR-1505, AND BR IDGE #430219 ON SR-1306. | 5496567 | 13 | 0 miles | BUCKEYE BRIDGE LLC | HELENE | Kenneth C. McCourt | 8284977333 | 2025-01-09 | 2025-02-18 | 2027-04-07 | 2027-05-15 | 25.8% | 25.8% | 2026-04-22 | 2026-05-04 10:54
C205052 | 5 | Wake |  | None | SR-1005, SR-1835, SR-2015, SR-3533, SR-3534 | 6 SECTIONS OF SECONDARY ROADS. | 4159626.54 | 10 | 8.387 miles | FSC II LLC DBA FRED SMITH COMPANY | STATE FUNDED | Alexander S. Griffis | 9198358200 | 2025-02-18 | 2025-04-21 | 2026-10-20 |  | 75.29% | 75.29% | 2026-04-22 | 2026-04-29 09:10
C205053 | 12 | Iredell |  | None | US-70 | 1 SECTION OF US-70, AND 31 SECTIONS OF SECONDARY ROADS. | 6273018.35 | 7 | 25.958 miles | MAYMEAD INC | STATE FUNDED | Johnathan A. Barnette | 7048763947 | 2025-02-18 | 2025-10-08 | 2026-11-13 |  | 50.04% | 50.04% | 2026-04-30 | 2026-05-11 09:10
C205054 | 9 | Davie, Rowan |  | None | US-601 | 1 SECTION OF US-601, 1 SECTION OF NC-150, 5 SECTIONS OF NC-8 01, AND 12 SECTIONS OF SECONDARY ROADS. | 11502013.43 | 4 | 45.552 miles | NJR GROUP INC | STATE FUNDED | Phillip Kelly Seitz, PE | 7046303200 | 2025-02-18 | 2025-06-08 | 2026-11-01 |  | 14.92% | 14.92% | 2026-04-30 | 2026-05-08 09:10
C205055 | 8 | Richmond |  | None | - | 1 SECTION OF US-1, 1 SECTION OF NC-177, AND 6 SECTIONS OF SE CONDARY ROADS. | 3362164.01 | 5 | 18.26 miles | FSC II LLC DBA FRED SMITH COMPANY | STATE FUNDED | James A. Dietrich | 9109442344 | 2025-02-18 | 2025-05-21 | 2026-10-01 |  | 58.39% | 58.39% | 2025-10-15 | 2025-10-24 09:10
C205056 | 14 | Henderson |  | None | SR-1578 | BRIDGE #440109 OVER CLEAR CREEK ON SR-1578 (TOWNSEND RD) AND BRIDGE #440198 OVER CLEAR CREEK ON SR-1614 (WATERS RD). | 4979550 | 14 | 0 miles | BUCKEYE BRIDGE LLC | HELENE | Michael D. Patton | 8285862141 | 2025-01-21 | 2025-03-03 | 2027-04-07 |  | 25.51% | 25.51% | 2026-04-22 | 2026-05-14 09:10
C205057 | 14 | Haywood, Henderson |  | None | SR-1500 | BRIDGE #430062 OVER COVE CREEK ON SR-1500 AND BRIDGE #440095 OVER BRANCH BROAD RIVER ON SR-1701. | 5283257.89 | 13 | 0 miles | ZACHRY CONSTRUCTION CORPORATION | HELENE | Kenneth C. McCourt | 8284977333 | 2025-01-21 | 2025-03-03 | 2027-04-07 |  | 63.06% | 63.06% | 2026-04-07 | 2026-05-04 10:54
C205058 | 5 | Granville |  | None | SR-1004, SR-1159, SR-1300, SR-1301, SR-1302, SR-1413, SR-1710 | 7 SECTIONS OF SECONDARY ROADS. | 2369325.3 | 1 | 18.611 miles | SUNROCK INDUSTRIES LLC DBA CAROLINA SUNROCK LLC | STATE FUNDED | James M. Nordan, PE | 9193174760 | 2025-03-18 | 2026-01-13 | 2026-10-28 |  | 12.93% | 12.93% | 2026-01-30 | 2026-02-12 09:10
C205059 | 9 | Stokes |  | Subregional | SR-1236 | BRIDGE #840286 OVER LITTLE YADKIN RIVER ON SR-1236 (NORTH OL D 52). | 6518964.61 | 6 | 0.483 miles | SMITH-ROWE, LLC | STATE FUNDED | Nicholas C. Librandi | 3367477950 | 2025-04-15 | 2025-06-23 | 2028-01-28 | 2028-07-08 | 15.24% | 15.24% | 2026-04-30 | 2026-05-11 09:10
C205060 | 14 | Cherokee, Swain |  |  | US-19 | 2 SECTIONS OF US-19. | 0 |  | 18.19 miles | SITE DEVELOPMENT CORPORATION | STATE FUNDED | J. Adam Dockery | 8283215061 | 2025-03-18 |  | 2026-10-15 |  | 0% | 0%
C205061 | 7 | Guilford |  | Subregional | SR-3000 | BRIDGE #400224 OVER SOUTH BUFFALO CREEK ON SR-3000 (MCCONNEL L RD). | 3990712.54 | 9 | 0.175 miles | DELLINGER INC | STATE FUNDED | Jacob T. Crews, PE | 3363751774 | 2025-04-15 | 2025-07-07 | 2027-03-14 |  | 40.05% | 40.05% | 2026-04-15 | 2026-05-13 08:10
C205063 | 5 | Vance |  | None | SR-1111 | 11 SECTIONS OF SECONDARY ROADS. | 1287978.6 | 2 | 11.964 miles | SUNROCK INDUSTRIES LLC DBA CAROLINA SUNROCK LLC | STATE FUNDED | David B. Moore | 9192204600 | 2025-03-18 | 2026-01-23 | 2026-11-19 |  | 22.71% | 22.71% | 2026-02-28 | 2026-03-06 09:10
C205064 | 13 | McDowell |  | Statewide | US-70 | BRIDGE #580058 OVER MACKEY CREEK ON US-70. | 5400000 | 10 | 0 miles | KEMP SIGMON CONSTRUCTION CO INC | HELENE | Robert T. Cousins | 5403206428 | 2025-03-18 | 2025-04-14 | 2026-10-01 |  | 11.04% | 11.04% | 2026-03-31 | 2026-05-05 08:10
C205065 | 13 | Yancey | 1, 2, 3, 4 | None | - | BRIDGE #990157 OVER ELK SHOAL CREEK ON SR-1388 AND BRIDGES # 990233, #990192, AND #990193 OVER PIGPEN CREEK ON SR-1333. | 4958190 | 11 | 0 miles | DANE CONSTRUCTION LLC | HELENE | Robert T. Cousins | 5403206428 | 2025-03-18 | 2025-04-09 | 2026-11-01 |  | 35.64% | 35.64% | 2026-04-30
C205066 | 7 | Alamance | U-6011 | None | SR-1158 | US-70 (SOUTH CHURCH ST) AT SR-1158 (HUFFMAN MILL RD). | 6097609 | 11 | 0.192 miles | FSC II LLC DBA FRED SMITH COMPANY | STATE FUNDED | Bobby J. Howell | 3365706830 | 2025-04-15 | 2025-06-16 | 2027-03-14 | 2027-03-21 | 60.76% | 60.76% | 2026-05-07 | 2026-05-19 08:10
C205067 | 5 | Granville, Vance, Warren |  | None | US-1 | 2 SECTIONS OF US-1, 1 SECTION OF US-158, 1 SECTION OF NC-56, AND 1 SECTION OF SECONDARY ROAD. | 2909198.74 | 1 | 16.863 miles | SUNROCK INDUSTRIES LLC DBA CAROLINA SUNROCK LLC | STATE FUNDED | David B. Moore | 9192204600 | 2025-03-18 | 2026-02-10 | 2026-11-05 |  | 14.98% | 14.98% | 2026-04-30 | 2026-05-06 09:10
C205068 | 13 | Henderson, Rutherford | M-0572C |  | US-74A | US-74A/NC-9/US-64 IN CHIMNEY ROCK TO WEST OF US-64 (CHIMNEY ROCK RD)/US-74A/NC-9 (GERTON HIGHWAY) INTERSECTION. | 0 |  | 2.595 miles | WRIGHT BROTHERS CONSTRUCTION COMPANY INC | ER2483 | Travis J. Henley | 8286527848 | 2026-01-22 |  | 2028-04-01 |  | 0% | 0%
C205069 | 6 | Robeson | B-5985B | Subregional | SR-1600 | BRIDGE #770175 OVER LUMBER RIVER ON SR-1600 (W 5TH ST). | 6542886.54 | 4 | 0.122 miles | S&C CONSTRUCTION LLC | 4774902 | Joseph M. Parker, Jr., PLS | 9103640600 | 2025-11-18 | 2026-01-29 | 2028-05-03 |  | 30.53% | 30.53% | 2026-05-15 | 2026-05-20 09:10
C205071 | 7 | Rockingham | BR-0155 | Statewide | US-158 | BRIDGE #780163 OVER HOGAN'S CREEK ON US-158. | 4537081.75 | 1 | 0.18 miles | SMITH-ROWE, LLC | STATE FUNDED | Jacob B. Harris, PE | 3365206060 | 2025-12-16 | 2026-04-06 | 2028-11-11 |  | 5.24% | 5.24% | 2026-04-30 | 2026-05-08 09:10
C205072 | 3 | New Hanover, Pender | R-3300A | Statewide | US-17 | US-17 (HAMPSTEAD BYPASS) FROM US-17 BYPASS SOUTH OF HAMPSTEA D TO NC-210. | 182389503.48 | 8 | 7.044 miles | S T WOOTEN CORPORATION | STATE FUNDED | Bradley L. Haste | 9103475258 | 2025-07-15 | 2025-08-25 | 2030-03-30 |  | 15.45% | 15.45% | 2026-04-30 | 2026-05-11 09:10
C205073 | 3 | Brunswick | R-5857 | Statewide | US-17 B | INTERSECTIONS AT US-17 AND US-17 BUSINESS NORTH AND SOUTH OF SHALLOTTE. | 25693279.23 | 7 | 0.91 miles | HIGHLAND PAVING CO LLC | STATE FUNDED | Joshua T. Pratt | 9103989100 | 2025-07-15 | 2025-10-06 | 2028-03-29 |  | 16.16% | 16.16% | 2026-04-30 | 2026-05-08 09:10
C205074 | 9 | Forsyth | U-6005 | Regional | NC-65 | NC-65 (BETHANIA-RURAL HALL RD) FROM US-52 TO SR-3983 (NORTHR IDGE PARK DR). | 12385000 | 8 | 0.933 miles | BRANCH CIVIL INC | STATE FUNDED | Nicholas C. Librandi | 3367477950 | 2025-07-15 | 2025-09-13 | 2028-03-13 |  | 23.27% | 23.27% | 2026-04-30 | 2026-05-18 08:10
C205075 | 2 | Carteret | U-6058 | Regional | NC-101 | NC-101 FROM S OF SR-1170 (W BEAUFORT RD) TO N OF US-70 AND S R-1493 (LIVE OAK STREET) AT NC-101. | 8090393.12 | 5 | 0.272 miles | BARNHILL CONTRACTING CO | 4748201 | Brad T. McMannen, PE | 2526496520 | 2025-07-15 | 2025-09-29 | 2027-10-28 | 2027-12-27 | 29.87% | 29.87% | 2026-04-30 | 2026-05-07 10:10
C205076 | 6 | Cumberland, Hoke | U-5798B | Subregional | SR-1102 | SR-1102 (GILLIS HILL RD) FROM SOUTH OF CELTIC DR TO NORTH OF SR-1112 (STONEY POINT RD). | 17747427.86 | 5 | 0.869 miles | HIGHLAND PAVING CO LLC | STATE FUNDED | Spencer G. Shoffner, PE | 9103640607 | 2025-08-19 | 2025-11-13 | 2028-11-11 |  | 18.07% | 18.07% | 2026-04-15 | 2026-04-23 08:10
C205077 | 14 | Haywood |  | Statewide | I-40 | I-40 FROM TENNESSEE STATE LINE TO WEST OF MM 5. | 75392045.86 | 15 | 4.81 miles | AMES CONSTRUCTION INC | HELENE | Blake R. Soblesky | 8285862141 | 2025-02-14 | 2025-02-26 | 2027-10-15 |  | 58.67% | 58.67% | 2026-04-30 | 2026-05-19 08:10
C205078 | 14 | Henderson |  | Statewide | US-74A | US-74A FROM BEARWALLOW MOUNTAIN RD TO US-64/US-47A/NC-9. (CM GC - GERTON) | 19136216.21 | 9 | 4.8 miles | WRIGHT BROTHERS CONSTRUCTION COMPANY INC | HELENE | Michael D. Patton | 8285862141 | 2025-06-25 | 2025-07-23 | 2027-12-31 |  | 45.54% | 45.54% | 2026-04-15 | 2026-05-13 08:10
C205079 | 10 | Mecklenburg | I-6016 | Statewide | I-85 | INTERCHANGE AT I-85 AND I-485 WEST OF CHARLOTTE. | 77688.9 | 8 | 1.42 miles | REEVES CONSTRUCTION COMPANY | STATE FUNDED | Yanwei Ma | 7048475006 | 2025-06-11 | 2025-07-28 | 2028-06-30 |  | 33.95% | 33.95% | 2026-04-15 | 2026-05-05 08:10
C205080 | 7 | Alamance | I-6059 | None | SR-1981 | INTERCHANGE OF I-40/I-85 AND SR-1981 (TOLLINGWOOD-HAWFIELDS RD) IN MEBANE. | 376087.37 | 12 | 0.5 miles | APAC ATLANTIC INC SMITH ROWE LLC JV | STATE FUNDED | Bobby J. Howell | 3365706830 | 2025-02-20 | 2025-04-24 | 2028-05-01 |  | 32.58% | 32.58% | 2026-04-30 | 2026-05-12 09:10
C205081 | 6 | Columbus, Robeson | HI-0016, HI-0017 | Statewide | US-74 | US-74 FROM 1 MILE EAST OF NC-41 TO 0.26 MILES EAST OF COLUMB US CO LINE AND FROM SCOTLAND CO LINE TO I-74/US-74 BUSINESS. | 18703602.78 | 8 | 13.001 miles | BARNHILL CONTRACTING CO | 0074244 | Joseph M. Parker, Jr., PLS | 9103640600 | 2025-05-20 | 2025-09-10 | 2027-06-30 |  | 51.46% | 51.46% | 2026-04-30 | 2026-05-12 09:10
C205083 | 5 | Warren |  | None | US-1 | 1 SECTION OF US-158 BUSINESS, 1SECTION OF NC-58 EAST, AND 12 SECTIONS OF SECONDARY ROADS. | 2355127.3 | 2 | 16.474 miles | SUNROCK INDUSTRIES LLC DBA CAROLINA SUNROCK LLC | STATE FUNDED | David B. Moore | 9192204600 | 2025-04-15 | 2026-02-19 | 2026-11-15 |  | 16.46% | 16.46% | 2026-03-31 | 2026-04-07 09:10
C205084 | 5 | Franklin |  | None | SR-1146 | 14 SECTIONS OF SECONDARY ROADS. | 1878128.65 | 2 | 13.582 miles | BARNHILL CONTRACTING CO | STATE FUNDED | David B. Moore | 9192204600 | 2025-04-15 | 2026-03-19 | 2026-11-15 |  | 85.67% | 85.67% | 2026-04-30 | 2026-05-12 09:10
C205086 | 14 | Jackson | R-5600 | None | NC-107 | US-23 BUSINESS AT MILL ST, TO NC-107, ALONG NC-107 (E MAIN S T) TO SOUTH OF SR-1780 (LOVEDALE RD). | 103347870.97 | 1 | 2.62 miles | BUCHANAN AND SONS INC | STP-0107(013) | Kenneth C. McCourt | 8284977333 | 2025-11-18 | 2026-03-30 | 2031-11-11 |  | 2.68% | 2.68% | 2026-05-06 | 2026-05-11 09:10
C205087 | 8 | Randolph |  | None | SR-1564 | 13 SECTIONS OF SECONDARY ROADS. | 3662144.2 | 4 | 20.198 miles | APAC ATLANTIC INC THOMPSON ARTHUR DIVISION | STATE FUNDED | Joshua S. Brooks | 3363184020 | 2025-05-20 | 2026-01-14 | 2026-10-15 |  | 64.96% | 64.96% | 2026-04-30 | 2026-05-06 09:10
C205089 | 8 | Randolph |  | None | SR-2417 | 10 SECTIONS OF SECONDARY ROADS. | 3696610.44 | 2 | 24.037 miles | TRUEROCK CONSTRUCTION LLC | STATE FUNDED | Joshua S. Brooks | 3363184020 | 2025-05-20 | 2026-01-22 | 2026-11-01 |  | 6.1% | 6.1% | 2026-04-30 | 2026-05-06 09:10
C205090 | 4 | Wilson |  |  | NC-42 | BRIDGE #970068 OVER US-301 ON NC-42. | 0 |  | 0.12 miles | SAFFO CONTRACTORS INC | STATE FUNDED | Logan S. Ennis | 2524592129 | 2025-12-16 |  | 2026-11-15 |  | 0% | 0%
C205092 | 2 | Pitt | U-5875 | Subregional | SR-1203 | SR-1203 (ALLEN RD) FROM SR-1467 (STANTONSBURG RD) TO US-13 ( DICKINSON AVE EXT). | 47191560.83 | 4 | 2.406 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Jason B. Beasley | 2524392970 | 2025-10-21 | 2026-01-19 | 2029-12-12 | 2030-01-11 | 14.79% | 14.79% | 2026-04-30 | 2026-05-07 10:10
C205093 | 9 | Davie | U-6187 | None | SR-1630 | NEW ROUTE FROM SR-1630 (BALTIMORE RD) TO I-40. | 32185000 | 5 | 1.184 miles | BRANCH CIVIL INC | STATE FUNDED | Eric T. Goldston | 7046303220 | 2025-10-21 | 2025-12-01 | 2029-12-12 |  | 23.15% | 23.15% | 2026-04-30 | 2026-05-08 09:10
C205094 | 6 | Cumberland |  |  | SR-1400 | BRIDGE #250227 OVER SR-1007 (ALL AMERICAN FREEWAY) ON SR-140 0 (CLIFFDALE RD). | 0 |  | 0.05 miles | AMERICAN CIVIL CONSTRUCTORS WEST COAST LLC | STATE FUNDED | Spencer G. Shoffner, PE | 9103640607 | 2025-11-18 | 2026-05-01 | 2026-10-01 |  | 0% | 0%
C205095 | 10 | Mecklenburg | U-6105 | Subregional | SR-2415 | SR-2415 (BAILEY RD) FROM POOLE PLACE DR TO US-21 (STATESVILL E RD). | 7809039.07 | 1 | 0.467 miles | BLYTHE DEVELOPMENT LLC | STBGDA-2415(001) | Michael W. Hedrick, PE | 9805230080 | 2026-02-17 | 2026-04-13 | 2028-05-13 |  | 3.74% | 3.74% | 2026-04-15 | 2026-04-22 08:10
C205096 | 13 | Burke, McDowell | 1, 2 | None | SR-MULTI | 20 SECTIONS OF SECONDARY ROADS. | 9350963.56 | 6 | 32.59 miles | MAYMEAD INC | STATE FUNDED | Travis J. Henley | 8286527848 | 2025-05-20 | 2025-10-21 | 2026-11-01 | 2026-11-02 | 61.76% | 61.76% | 2026-05-07 | 2026-05-19 08:10
C205097 | 13 | Buncombe |  | None | - | 51 SECTIONS OF SECONDARY ROADS. | 6085293.43 | 9 | 27.75 miles | FRENCH BROAD PAVING INC | STATE FUNDED | Thomas R. Veazey | 8282980080 | 2025-06-17 | 2025-08-12 | 2026-11-01 |  | 57.08% | 57.08% | 2026-04-22 | 2026-05-01 09:10
C205098 | 9 | Davidson, Forsyth | HI-0005 |  | - | I-285/US-52/NC-8 FROM SR-3010 (OLD US-52) TO SR-4205 (S MAIN ST). | 0 |  | 10.97 miles | GOSALIA CONCRETE CONSTRUCTORS INC | 0285003 | Eric T. Goldston | 7046303220 | 2026-02-17 |  | 2028-09-15 |  | 0% | 0%
C205099 | 11 | Surry | R-5901 |  | - | NC-89 (WEST PINE ST) AT SR-1397 (ROUND PEAK CHURCH RD) INTER SECTION. | 0 |  | 0.32 miles | SMITH-ROWE, LLC | 4841601 | Benjamin D. Whitaker | 3368354241 | 2025-09-16 | 2026-04-10 | 2028-01-11 |  | 0% | 0%
C205101 | 3 | Pender | HS-2403U | None | SR-1002, SR-1216, US-421 | 1 SECTION OF US-421, AND 2 SECTIONS OF SECONDARY ROADS. | 4612279.74 | 7 | 18.69 miles | S T WOOTEN CORPORATION | STATE FUNDED | Bradley L. Haste | 9103475258 | 2025-06-17 | 2025-07-28 | 2026-11-15 | 2026-12-15 | 90.73% | 90.73% | 2026-04-30 | 2026-05-11 09:10
C205102 | 8 | Randolph |  | None | US-64 | 1 SECTION OF US-64, 2 SECTIONS OF NC-22, AND 1 SECTION OF NC -42. | 3999558.77 | 1 | 22.217 miles | APAC ATLANTIC INC THOMPSON ARTHUR DIVISION | STATE FUNDED | Joshua S. Brooks | 3363184020 | 2025-05-20 | 2026-04-13 | 2026-11-15 |  | 26.96% | 26.96% | 2026-05-15
C205103 | 5 | Caswell, Person |  | None | SR-1219, SR-1220, SR-1318, SR-1336, SR-1390, SR-1391, SR-1415, SR-1553, SR-1580, SR-1586 | 10 SECTIONS OF SECONDARY ROADS. | 1465372.76 | 2 | 8.997 miles | SUNROCK INDUSTRIES LLC DBA CAROLINA SUNROCK LLC | STATE FUNDED | James M. Nordan, PE | 9193174760 | 2025-05-20 | 2026-01-16 | 2026-11-01 |  | 30.58% | 30.58% | 2026-03-31 | 2026-04-07 09:10
C205107 | 13 | McDowell, Rutherford | 1, 2 |  | US-221 | 4 SECTIONS OF US-221 AND FIRE DEPARTMENT PARKING LOT. | 0 |  | 18.6 miles | APAC ATLANTIC INC ASHEVILLE DIVISION | STATE FUNDED | Travis J. Henley | 8286527848 | 2025-06-17 |  | 2026-11-01 |  | 0% | 0%
C205108 | 13 | Rutherford | SS-6213AD | None | - | 42 SECTIONS OF SECONDARY ROADS. | 7442922.76 | 2 | 35.17 miles | BLYTHE CONSTRUCTION INC | STATE FUNDED | Travis J. Henley | 8286527848 | 2025-06-17 | 2025-10-28 | 2026-11-15 |  | 36.89% | 36.89% | 2026-05-07 | 2026-05-20 09:10
C205109 | 3 | Brunswick |  | None | NC-133, NC-87, SR-1300, SR-1525 | 1 SECTION OF NC-87, 1 SECTION OF NC-133, AND 3 SECTIONS OF S ECONDARY ROADS. | 5227022.21 | 6 | 26.86 miles | S T WOOTEN CORPORATION | STATE FUNDED | Nathan H. Tew | 9103412000 | 2025-06-17 | 2025-08-24 | 2026-11-20 |  | 58.45% | 58.45% | 2026-05-01 | 2026-05-11 09:10
C205110 | 3 | Sampson |  | None | NC-41, NC-55, SR-1007 | 1 SECTION OF NC-41, 1 SECTION OF NC-55, AND 1 SECTION OF SEC ONDARY ROAD. | 5243980.24 | 6 | 21.77 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Daniel F. Jones | 9106825100 | 2025-06-17 | 2025-09-12 | 2026-11-20 | 2026-11-22 | 79.25% | 79.25% | 2026-04-30 | 2026-05-11 09:10
C205111 | 13 | Mitchell, Yancey | 1, 2, 3 | None | SR-1143, SR-1206, SR-1337 | CULVERT #600050 ON SR-1206, CULVERT #990179 ON SR-1143, AND BRIDGE #990188 ON SR-1337. | 7471433.92 | 2 | 0 miles | MOUNTAIN CREEK CONTRACTORS INC | HELENE | Colby D. Justice | 8286589439 | 2025-10-21 | 2026-02-05 | 2027-10-01 |  | 7.58% | 7.58% | 2026-05-07 | 2026-05-11 09:10
C205112 | 12 | Cleveland, Gaston | I-5719FC | Statewide | I-85 | I-85 FROM US-74 TO THE SOUTH CAROLINA LINE AND I-85 FROM US- 74 TO US-321. | 6387777 | 1 | 10 miles | BROOKS BERRY HAYNIE & ASSOCIATES INC | FUTR085 | Anne Burwell Schley, PE | 7044805580 | 2025-09-16 | 2025-11-06 | 2027-11-15 |  | 6.63% | 6.63% | 2026-04-15 | 2026-05-01 09:10
C205114 | 7 | Rockingham |  | None | SR-1138 | 40 SECTIONS OF SECONDARY ROADS. | 6850869.13 | 2 | 23.87 miles | VECELLIO & GROGAN INC DBA SHARPE BROTHERS | STATE FUNDED | Jacob B. Harris, PE | 3365206060 | 2025-07-15 | 2026-03-02 | 2027-05-15 |  | 51.02% | 51.02% | 2026-04-30 | 2026-05-11 09:10
C205115 | 7 | Alamance |  |  | US-70 | 41 SECTIONS OF SECONDARY ROADS. | 0 |  | 29.85 miles | TRUEROCK CONSTRUCTION LLC | STATE FUNDED | Bobby J. Howell | 3365706830 | 2025-07-15 | 2026-05-04 | 2027-05-15 |  | 0% | 0%
C205116 | 7 | Rockingham | BR-0098 | Statewide | US-29 | BRIDGE #780183 OVER US-29 BYP ON US-29 BUS. | 4612860.74 | 2 | 0.246 miles | SMITH-ROWE, LLC | STATE FUNDED | Jacob B. Harris, PE | 3365206060 | 2025-10-21 | 2026-02-21 | 2028-01-11 | 2028-01-25 | 15.64% | 15.64% | 2026-04-30 | 2026-05-11 09:10
C205117 | 10 | Cabarrus | U-5956 |  | SR-1414, US-29 | US-29 FROM 0.6 MILES WEST OF SR-1414 (ROCK HILL CHURCH RD) T O JUST EAST OF SR-1414 (ROCK HILL CHURCH RD). | 0 |  | 0.861 miles | NJR GROUP INC | STATE FUNDED | Bradley S. Eagle | 7049834380 | 2026-01-20 | 2026-04-23 | 2028-04-29 |  | 0% | 0%
C205118 | 10 | Mecklenburg | W-5710X | None | SR-2042 | SR-2042 (OAKDALE RD), SR-2108 (SUNSET RD), SR-2025 (MIRANDA RD), AND SR-2040 (LAWING RD). | 6839336.3 | 3 | 0.286 miles | TRUEROCK CONSTRUCTION LLC | HSIP-2042(002) | Brian D. Davis, PE | 7048475006 | 2025-11-18 | 2026-02-06 | 2028-01-11 |  | 37.31% | 37.31% | 2026-04-30 | 2026-05-14 09:10
C205120 | 13 | Madison | I-5831B |  | I-26 | I-26 FROM TENNESSEE STATE LINE MILE MARKER 0.10 TO MILE MARK ER 8.45. | 0 |  | 8.32 miles | GOSALIA CONCRETE CONSTRUCTORS INC | 5303701 | Colby D. Justice | 8286589439 | 2025-12-16 |  | 2028-06-01 |  | 0% | 0%
C205121 | 14 | Henderson |  | Regional | NC-9 | NC-9 FROM 2700' NORTH OF THE US 74A / NC-9 INTERSECTION TO T HE BUNCOMBE COUNTY LINE. | 11755057.89 | 5 | 1.454 miles | IPC PAVING LLC DBA IPC STRUCTURES LLC | HELENE | Michael D. Patton | 8285862141 | 2025-08-19 | 2025-10-21 | 2028-02-28 | 2028-03-09 | 8.94% | 8.94% | 2026-04-15 | 2026-04-22 08:10
C205122 | 13 | Buncombe | TIP 1, TIP 2, TIP 3, TIP 4 | None | SR-1390, SR-2109, SR-2115, SR-2173 | BRIDGES ON SR-2109, SR-2115, SR-2173, AND CULVERT ON SR-1390 . | 8469900 | 5 | 0 miles | DANE CONSTRUCTION LLC | HELENE | Robert T. Cousins | 5403206428 | 2025-09-16 | 2025-10-15 | 2027-10-01 |  | 16.38% | 16.38% | 2026-04-30 | 2026-05-20 09:10
C205123 | 13 | Buncombe | TIP 1, TIP 2, TIP 3 | None | SR-0199, SR-0463, SR-0846 | CULVERT ON SR-2776, BRIDGE ON SR-2427, AND BRIDGE ON SR-2788 . | 4569600 | 1 | 0 miles | BLYTHE CONSTRUCTION INC | HELENE | Robert T. Cousins | 5403206428 | 2025-09-16 | 2025-10-27 | 2027-09-01 |  | 6.7% | 6.7% | 2026-03-27 | 2026-04-01 08:10
C205124 | 13 | McDowell, Rutherford |  | None | SR-1312, SR-1448 | CULVERT #580382 ON SR-1448, CULVERT #800573 ON SR-1312, AND BRIDGE #800572 ON SR-1312. | 7214044.6 | 5 | 0 miles | ES WAGNER COMPANY LLC | HELENE | Travis J. Henley | 8286527848 | 2025-10-21 | 2025-12-01 | 2027-10-01 |  | 12.84% | 12.84% | 2026-04-22 | 2026-04-30 09:10
C205126 | 13 | Buncombe | HE-0001B | Statewide | I-26 | FUTURE CONNECTOR ROAD (EAST FREDERICK LAW OLMSTEAD WAY) FROM I-26 INTERCHANGE TO ROUNDABOUT. | 5648500 | 3 | 0.503 miles | BRANCH CIVIL INC | SKYR026 | Thomas R. Veazey | 8282980080 | 2025-11-18 | 2026-02-09 | 2028-04-15 | 2028-04-25 | 20.71% | 20.71% | 2026-04-22 | 2026-05-12 09:10
C205127 | 7 | Orange |  | None | SR-1750 | 57 SECTIONS OF SECONDARY ROADS. | 5511361.6 | 2 | 20.21 miles | FSC II LLC DBA FRED SMITH COMPANY | STATE FUNDED | Bobby J. Howell | 3365706830 | 2025-09-16 | 2026-01-12 | 2027-09-01 |  | 28.42% | 28.42% | 2026-04-22 | 2026-05-06 09:10
C205128 | 7 | Rockingham | BR-0096 |  | SR-1700 | BRIDGE #780176 OVER NC-14/NC-87 ON SR-1700 (FISHER HILL RD) | 0 |  | 0.104 miles | SMITH-ROWE, LLC | 5160301 | Jacob B. Harris, PE | 3365206060 | 2026-01-20 |  | 2027-11-11 |  | 0% | 0%
C205129 | 2 | Pamlico | BR-0173 |  | - | BRIDGE #680078 OVER NEUSE RIVER ON NC-306. | 0 |  | 0.057 miles | SMITH-ROWE, LLC | RAMP078 | Brad T. McMannen, PE | 2526496520 | 2026-01-20 |  | 2027-05-14 |  | 0% | 0%
C205132 | 12 | Cleveland | BP12-R002 |  | NC-226 | BRIDGE #220075 ON NC-226 (POLKVILLE ROAD) OVER HINTON CREEK. | 0 |  | 0.275 miles | BLYTHE CONSTRUCTION INC | STATE FUNDED | Eric W. Conner | 8284686260 | 2026-01-20 | 2026-05-12 | 2028-11-11 |  | 0% | 0%
C205133 | 13 | Mitchell | TIP 1, TIP 2, TIP 3 | None | SR-1207, SR-1325, SR-1330 | BRIDGE ON CANE CRK ON SR-1207, BRIDGE OVER BIG ROCK CRK ON S R-1330, AND BRIDGE OVER BEANS CRK ON SR-1325. | 5739801.46 | 2 | 0 miles | SMITH-ROWE, LLC | HELENE | Colby D. Justice | 8286589439 | 2025-10-21 | 2025-12-01 | 2027-09-01 |  | 14.48% | 14.48% | 2026-05-07 | 2026-05-15 08:10
C205134 | 5 | Wake |  | None | SR-1820, US-70 | 1 SECTION OF US-70, 3 SECTIONS OF SECONDARY ROADS, AND 1 RAM P. | 3790141.4 | 2 | 6.458 miles | BLYTHE CONSTRUCTION INC | STATE FUNDED | Niklaus C. Winkler | 9197339499 | 2025-10-21 | 2026-03-05 | 2027-06-01 |  | 11.43% | 11.43% | 2026-04-30 | 2026-05-12 09:10
C205135 | 13 | Rutherford | HN-0019 |  | US-64, US-74A | INTERSECTION OF US-64/US-74A (WEST MOUNTAIN ST) AND NORTH WA SHINGTON ST. | 0 |  | 0.213 miles | WRIGHT BROTHERS CIVIL CONSTRUCTION LLC | 5117401 | Travis J. Henley | 8286527848 | 2025-12-16 |  | 2027-10-01 |  | 0% | 0%
C205136 | 5 | Wake |  | None | SR-1348, SR-1655, SR-1656, SR-1829, SR-2026, SR-2249, SR-2250, SR-2271, SR-3041, SR-3073, SR-3114 | 14 SECTIONS OF SECONDARY ROADS. | 4408885.2 | 4 | 11.203 miles | BLYTHE CONSTRUCTION INC | STATE FUNDED | Niklaus C. Winkler | 9197339499 | 2025-10-21 | 2026-01-19 | 2027-06-01 |  | 26.61% | 26.61% | 2026-04-30 | 2026-05-13 08:10
C205137 | 8 | Lee |  |  | US-421 | 1 SECTION OF US-1, 1 SECTION OF US-421, AND 6 RAMPS. | 0 |  | 17.39 miles | S T WOOTEN CORPORATION | STATE FUNDED | Jeremy B. Phillips | 9197769623 | 2025-10-21 |  | 2027-06-01 |  | 0% | 0%
C205141 | 13 | Rutherford |  | Statewide | US-74 B | BRIDGE #800036 OVER SECOND BROAD RIVER ON US-74 BUSINESS. | 5350016.46 | 2 | 0.2 miles | SMITH-ROWE, LLC | STATE FUNDED | Travis J. Henley | 8286527848 | 2025-12-16 | 2026-02-26 | 2027-11-15 |  | 11.3% | 11.3% | 2026-04-28 | 2026-05-04 10:54
C205142 | 9 | Forsyth |  |  | -, NC-66, SR-1001, SR-1101, SR-1152, SR-1611, US-158 | 1 SECTION OF US-158, 1 SECTION OF NC-66, AND 15 SECTIONS OF SECONDARY ROADS. | 0 |  | 28.387 miles | APAC ATLANTIC INC THOMPSON ARTHUR DIVISION | STATE FUNDED | Kevin R. Hedrick, PE | 3367477900 | 2025-10-21 |  | 2027-09-16 |  | 0% | 0%
C205143 | 9 | Davidson |  |  | - | 16 SECTIONS OF SECONDARY ROADS. | 0 |  | 30.269 miles | J T RUSSELL & SONS INC | STATE FUNDED | Eric T. Goldston | 7046303220 | 2025-10-21 | 2026-03-16 | 2027-09-16 |  | 0% | 0%
C205145 | 13 | Yancey | M-0572E | None | SR-1102, SR-1112, SR-1184 | NC-197 | 21117254.55 | 1 | 30 miles | ARCHER WESTERN CONSTRUCTION LLC | ER24386 | Colby D. Justice | 8286589439 | 2026-01-22 | 2026-02-19 | 2027-03-01 |  | 5.49% | 5.49% | 2026-03-31 | 2026-04-24 08:10
C205146 | 14 | Henderson |  |  | US-176 | 1 SECTION OF US-176, 2 SECTIONS OF US-25, 1 SECTION OF US-64 , 1 SECTION OF NC-191 AND 13 SECTIONS OF SECONDARY ROADS. | 0 |  | 33.644 miles | APAC ATLANTIC INC ASHEVILLE DIVISION | STATE FUNDED | Patrick A. Eubanks | 8288917911 | 2025-11-18 |  | 2027-06-29 |  | 0% | 0%
C205147 | 12 | Cleveland |  |  | -, NC-18, SR-1162, SR-1188, SR-1654 | 1 SECTION OF NC-18, 1 SECTION OF NC-161, AND 8 SECTIONS OF S ECONDARY ROADS. | 0 |  | 17.85 miles | ASPHALT PAVING OF SHELBY INC | STATE FUNDED | Wesley S. Clary | 7044802080 | 2025-11-18 |  | 2027-06-29 |  | 0% | 0%
C205148 | 5 | Durham |  | Regional | NC-55 | 1 SECTION OF NC-55. | 3982213.25 | 3 | 9.774 miles | CARDINAL CIVIL CONTRACTING LLC | STATE FUNDED | James M. Nordan, PE | 9193174760 | 2025-11-18 | 2026-02-09 | 2027-06-29 |  | 8.86% | 8.86% | 2026-04-30 | 2026-05-12 09:10
C205149 | 10 | Mecklenburg |  |  | NC-49 | 4 SECTIONS OF NC-49. | 0 |  | 7.8 miles | BLYTHE BROTHERS ASPHALT CO LLC | STATE FUNDED | Michael W. Hedrick, PE | 9805230080 | 2025-12-16 |  | 2027-07-26 |  | 0% | 0%
C205151 | 13 | Yancey | M-0572G | Statewide | US-19W | US-19W. | 19375967.03 | 1 | 22 miles | SEMA ST JV NCDOT 19W LLC | ER24384 | Colby D. Justice | 8286589439 | 2026-02-17 | 2026-03-25 | 2027-05-15 |  | 7.5% | 7.5% | 2026-04-15 | 2026-04-29 09:10
C205152 | 9 | Forsyth | 15BPR.143 |  | US-52 | BRIDGE #330078 OVER I-40 ON US-52/US-311/NC-8. | 0 |  | 0.043 miles | APPLIED POLYMERICS INC | STATE FUNDED | Kevin R. Hedrick, PE | 3367477900 | 2026-02-17 |  | 2026-10-30 |  | 0% | 0%
C205154 | 10 | Union |  | None | NC-207, US-74 | 1 SECTION OF US-74, 1 SECTION OF NC-207, AND 9 SECTIONS OF S ECONDARY ROADS. | 5048583.8 | 3 | 14.38 miles | TRUEROCK CONSTRUCTION LLC | STATE FUNDED | Jake R. Koltiska | 7042185125 | 2025-11-18 | 2026-02-18 | 2027-06-29 |  | 22.74% | 22.74% | 2026-04-30 | 2026-05-11 09:10
C205155 | 8 | Moore |  | None | - | 1 SECTION OF NC-705, 1 SECTION OF NC-24W, AND 15 SECTIONS OF SECONDARY ROADS. | 4070491.22 | 2 | 24.296 miles | FSC II LLC DBA FRED SMITH COMPANY | STATE FUNDED | James A. Dietrich | 9109442344 | 2025-11-18 | 2026-03-25 | 2027-06-29 |  | 36.88% | 36.88% | 2026-05-07 | 2026-05-20 09:10
C205156 | 4 | Wilson | HI-0014 |  | US-264 | US-264 FROM WILSON CO LINE TO I-95. | 0 |  | 4.554 miles | S T WOOTEN CORPORATION | 4998501 | Logan S. Ennis | 2524592129 | 2026-03-17 |  | 2027-07-30 |  | 0% | 0%
C205161 | 8 | Chatham |  |  | NC-902 | 6 SECTIONS OF PRIMARY ROADS, AND 16 SECTIONS OF SECONDARY RO ADS. | 0 |  | 41.276 miles | CARDINAL CIVIL CONTRACTING LLC | STATE FUNDED | Jeremy B. Phillips | 9197769623 | 2026-01-20 |  | 2027-09-02 |  | 0% | 0%
C205162 | 5 | Wake |  |  | US-1 | 3 SECTIONS OF PRIMARY ROADS, AND 26 SECTIONS OF SECONDARY RO ADS. | 0 |  | 22.839 miles | FSC II LLC DBA FRED SMITH COMPANY | STATE FUNDED | David W. Conner II | 9197077370 | 2026-01-20 |  | 2027-09-02 |  | 0% | 0%
C205163 | 8 | Lee |  |  | - | 4 SECTIONS OF PRIMARY ROADS, AND 14 SECTIONS OF SECONDARY RO ADS. | 0 |  | 20.028 miles | HIGHLAND PAVING CO LLC | STATE FUNDED | Jeremy B. Phillips | 9197769623 | 2026-01-20 |  | 2027-09-02 |  | 0% | 0%
C205164 | 13 | Yancey | 1, 2, 3 |  | - | BRIDGE #990165, BRIDGE #990116 & BRIDGE #990234. | 0 |  | 0 miles | SMITH-ROWE, LLC | HELENE | Robert T. Cousins | 5403206428 | 2026-03-17 |  | 2028-08-01 |  | 0% | 0%
C205165 | 14 | Polk |  |  | US-176 | SITES 936-940, 942-944, 314, 316-321, 941: US-176 FROM 0.1 M N OF THOMPSON RD TO 0.8 M EAST OF BEAR CREEK LN. W03293 | 0 |  | 1.221 miles | SITE DEVELOPMENT CORPORATION | HELENE | Michael D. Patton | 8285862141 | 2026-03-24 |  | 2029-12-27 |  | 0% | 0%
C205166 | 8 | Hoke, Scotland |  |  | - | 1 SECTION OF US-401, 1 SECTION OF NC-79, AND 4 SECTIONS OF S ECONDARY ROADS. | 0 |  | 20.18 miles | FSC II LLC DBA FRED SMITH COMPANY | STATE FUNDED | James A. Dietrich | 9109442344 | 2026-02-17 | 2026-05-05 | 2027-09-30 |  | 0% | 0%
C205167 | 5 | Granville |  |  | -, SR-1124, SR-1125, SR-1138, SR-1150, SR-1215, SR-1307 | 10 SECTIONS OF SECONDARY ROADS. | 0 |  | 17.404 miles | SUNROCK INDUSTRIES LLC DBA CAROLINA SUNROCK LLC | STATE FUNDED | James M. Nordan, PE | 9193174760 | 2026-03-17 |  | 2027-10-27 |  | 0% | 0%
C205168 | 10 | Mecklenburg |  |  | - | 2 SECTIONS OF US-21, 1 SECTION OF NC-24, & 1 SECTION OF NC-5 1, AND 14 SECTIONS OF SECONDARY ROADS. | 0 |  | 13.6 miles | BLYTHE CONSTRUCTION INC | STATE FUNDED | Michael W. Hedrick, PE | 9805230080 | 2026-02-17 |  | 2027-09-30 |  | 0% | 0%
C205169 | 9 | Stokes |  |  | - | 2 SECTIONS OF NC-268, AND 3 SECTIONS OF SECONDARY ROADS. | 0 |  | 24.946 miles | APAC ATLANTIC INC THOMPSON ARTHUR DIVISION | STATE FUNDED | Nicholas C. Librandi | 3367477950 | 2026-02-17 |  | 2027-09-30 |  | 0% | 0%
C205170 | 9 | Rowan |  |  | US-29 | 1 SECTION OF US-29 S,1 SECTION US-29 N, AND 13 SECTIONS OF S ECONDARY ROADS. | 0 |  | 29.668 miles | J T RUSSELL & SONS INC | STATE FUNDED | Phillip Kelly Seitz, PE | 7046303200 | 2026-02-17 | 2026-05-29 | 2027-09-30 |  | 0% | 0%
C205171 | 12 | Catawba |  |  | - | 1 SECTION OF US-321 BUSINESS, AND 7 SECTIONS OF SECONDARY RO ADS. | 0 |  | 14.62 miles | MAYMEAD INC | STATE FUNDED | Travis R. Jordan | 7047482400 | 2026-02-17 |  | 2027-09-30 |  | 0% | 0%
C205172 | 12 | Iredell |  |  | US-70 | 1 SECTION OF US-70, AND 36 SECTIONS OF SECONDARY ROADS. | 0 |  | 28.872 miles | MAYMEAD INC | STATE FUNDED | Johnathan A. Barnette | 7048763947 | 2026-02-17 |  | 2027-09-30 |  | 0% | 0%
C205173 | 8 | Montgomery |  |  | - | 1 SECTION EACH OF US-220 ALT, NC-109, NC-134, & NC-731, AND 5 SECTIONS OF SECONDARY ROADS. | 0 |  | 14.416 miles | FSC II LLC DBA FRED SMITH COMPANY | STATE FUNDED | Joshua S. Brooks | 3363184020 | 2026-02-17 |  | 2027-09-30 |  | 0% | 0%
C205174 | 5 | Vance |  |  | - | 1 SECTION OF US-1 BUSINESS, AND 4 SECTIONS OF SECONDARY ROAD S. | 0 |  | 16.828 miles | SUNROCK INDUSTRIES LLC DBA CAROLINA SUNROCK LLC | STATE FUNDED |  | 0 | 2026-02-17 |  | 2027-09-30 |  | 0% | 0%
C205175 | 3 | Onslow | HS-2403AD, HS-2403T |  | -, NC-111, SR-1135, SR-1210, SR-1223, SR-1225, SR-1317 | 3 SECTIONS OF NC-111, 2 SECTIONS OF US-258, AND 6 SECTIONS O F SECONDARY ROADS. | 0 |  | 21.8 miles | ONSLOW GRADING & PAVING INC | STATE FUNDED | Bradley L. Haste | 9103475258 | 2026-03-17 |  | 2027-10-27 |  | 0% | 0%
C205176 | 8 | Richmond |  |  | - | 1 SECTION OF US-74, AND 7 SECTIONS OF SECONDARY ROADS. | 0 |  | 22.423 miles | BARNHILL CONTRACTING CO | STATE FUNDED | James A. Dietrich | 9109442344 | 2026-03-17 |  | 2027-10-27 |  | 0% | 0%
C205179 | 10 | Union |  |  | NC-205 | 1 SECTION OF NC-205, AND 9 SECTIONS OF SECONDARY ROADS. | 0 |  | 17.39 miles | TRUEROCK CONSTRUCTION LLC | STATE FUNDED | Jake R. Koltiska | 7042185125 | 2026-03-17 |  | 2027-10-27 |  | 0% | 0%
C205181 | 5 | Durham, Wake |  |  | US-15 | 1 SECTION OF US-15, AND 28 SECTIONS OF SECONDARY ROADS. | 0 |  | 13.514 miles | SUNROCK INDUSTRIES LLC DBA CAROLINA SUNROCK LLC | STATE FUNDED | James M. Nordan, PE | 9193174760 | 2026-03-17 |  | 2027-10-27 |  | 0% | 0%
DA00551 | 1 | Camden, Currituck, Dare, Gates |  | None | US-17 | VAR. ROADS, PARKING LOTS, ETC. IN CAMDEN, CURRITUCK, DARE (O BX), GATES, HYDE (OCRACOKE ISLAND), PASQUOTANK & PERQUIMANS | 960460 | 8 | 0 miles | B E SINGLETON & SONS INC | STATE FUNDED | Brandon J. Tatum | 2526216400 | 2022-11-02 | 2022-12-05 | 2023-12-31 | 2025-12-31 | 9.68% | 9.68% | 2025-06-26 | 2025-06-30 09:30
DA00553 | 1 | Bertie, Camden, Chowan, Currituck |  | None | - | DIVISION 1 COUNTIES | 488725 | 12 | 0 miles | B & L CONSTRUCTION ENTERPRISES INC | STATE FUNDED | Jason G. Davidson | 2524821857 | 2022-06-15 | 2022-07-01 | 2023-06-30 |  | 66.97% | 66.97% | 2023-06-30 | 2023-07-07 14:10
DA00554 | 1 | Bertie, Hertford, Northampton |  | None | SR-1221 | VARIOUS ROADS, PARKING LOTS, ETC. UPON REQUEST, (ID/IQ) | 699850 | 4 | 0 miles | FSC II LLC DBA FRED SMITH COMPANY | STATE FUNDED | Christopher Brad Johnson | 2525136030 | 2022-07-13 | 2022-08-15 | 2023-07-31 | 2025-07-31 | 10.43% | 10.43% | 2024-01-31 | 2024-02-09 09:10
DA00581 | 1 | Northampton |  | None | NC-35, SR-1126, SR-1307, SR-1329, SR-1388, US-158 | VARIOUS PRIMARY & SECONDARY ROUTES | 3535535 | 9 | 18.44 miles | FSC II LLC DBA FRED SMITH COMPANY | STATE FUNDED | Edwin W. Rose | 2525136030 | 2024-04-17 | 2025-01-28 | 2025-12-12 |  | 66.93% | 66.93% | 2026-04-30 | 2026-05-06 09:10
DA00600 | 1 | Northampton |  | None | NC-186 | VARIOUS SECTIONS OF PRIMARY ROUTES | 1828838 | 5 | 9.3 miles | FSC II LLC DBA FRED SMITH COMPANY | STATE FUNDED | Edwin W. Rose | 2525136030 | 2024-06-26 | 2025-08-14 | 2025-12-12 |  | 68.59% | 68.59% | 2026-02-28 | 2026-03-09 09:10
DA00604 | 1 | Dare, Hyde | BO-2401A | None | NC-12 | RODANTHE, SALVO, BUXTON, HATTERAS, & OCRACOKE | 309935 | 2 | 0 miles | EASTERN EARTHSCAPES & CONSTRUCTION LLC | 5093003 | Brandon J. Tatum | 2526216400 | 2024-10-16 | 2025-04-01 | 2026-05-01 |  | 73.06% | 73.06% | 2026-03-31 | 2026-04-06 08:10
DA00610 | 1 | Dare |  | Statewide | US-64 | 7 SECTIONS ALONG THE US-64 CORRIDOR | 2412000 | 7 | 4.26 miles | FSC II LLC DBA FRED SMITH COMPANY | STATE FUNDED | Brandon J. Tatum | 2526216400 | 2024-09-18 | 2025-04-07 | 2026-12-11 |  | 94.6% | 94.6% | 2026-04-30 | 2026-05-07 10:10
DA00612 | 1 | Camden, Pasquotank |  |  | SR-1164 | 15 SECTIONS OF SECONDARY ROADS | 0 |  | 8.276 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Brandon J. Tatum | 2526216400 | 2024-11-20 | 2026-03-15 | 2026-09-18 |  | 0% | 0%
DA00613 | 1 | Chowan, Gates, Perquimans |  | None | SR-1303 | VARIOUS SECONDARY ROUTES | 3763248.29 | 2 | 27.193 miles | C D ROSE CONSTRUCTION LLC | STATE FUNDED | Brandon J. Tatum | 2526216400 | 2024-12-04 | 2025-07-01 | 2026-09-18 |  | 18.22% | 18.22% | 2026-04-30 | 2026-05-11 09:10
DA00614 | 1 | Bertie, Hertford |  | Subregional | SR-VARI | VARIOUS ROUTES | 612774.32 | 1 | 14.094 miles | WHITEHURST PAVING CO INC | STATE FUNDED | Edwin W. Rose | 2525136030 | 2025-01-15 | 2026-04-02 | 2026-05-01 |  | 92.97% | 92.97% | 2026-04-30 | 2026-05-04 10:54
DA00616 | 1 | Washington |  | None | US-64 | 4 SECTIONS OF US-64 & 6 SECTIONS SECONDARY ROADS | 3583972.21 | 6 | 15.896 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Gerard E. Mombaerts | 2527896150 | 2025-03-05 | 2025-08-06 | 2026-11-20 |  | 91.87% | 91.87% | 2026-05-06 | 2026-05-15 08:10
DA00617 | 1 | Bertie, Martin |  | None | NC-11 | 2 SECTIONS OF NC-11 & 1 SECTION OF NC-903 | 3450222.73 | 5 | 15.169 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Gerard E. Mombaerts | 2527896150 | 2025-04-16 | 2025-10-21 | 2026-11-20 |  | 63.8% | 63.8% | 2026-02-28 | 2026-03-03 08:10
DA00618 | 1 | Northampton |  |  | NC-46 | VARIOUS ROUTES | 0 |  | 12.384 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Edwin W. Rose | 2525136030 | 2025-04-16 | 2026-05-06 | 2026-11-20 |  | 0% | 0%
DA00619 | 1 | Perquimans |  |  | - | 3 SECTIONS OF NC-37 & 3 SECONDARY ROADS | 0 |  | 11.318 miles | FSC II LLC DBA FRED SMITH COMPANY | STATE FUNDED | Brandon J. Tatum | 2526216400 | 2025-05-07 | 2025-10-15 | 2026-12-15 |  | 0% | 0%
DA00620 | 1 | Dare |  | Statewide | US-64 | 1 SECTION OF US-64 | 2654321 | 1 | 5.803 miles | FSC II LLC DBA FRED SMITH COMPANY | STATE FUNDED | Brandon J. Tatum | 2526216400 | 2025-05-21 | 2025-11-17 | 2026-12-15 |  | 45.07% | 45.07% | 2026-04-30 | 2026-05-12 09:10
DA00622 | 1 | Camden, Currituck |  |  | SR-VARI | 21 SECTIONS OF SECONDARY ROADS | 0 |  | 14.835 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Brandon J. Tatum | 2526216400 | 2025-05-21 | 2025-10-06 | 2026-12-15 |  | 0% | 0%
DA00623 | 1 | Bertie, Camden, Chowan, Currituck |  | Subregional | SR-VARI | VARIOUS LOCATIONS | 795243.2 | 6 | 142.934 miles | GOSHEN CONSTRUCTION LLC | STATE FUNDED | Gerard E. Mombaerts | 2527896150 | 2025-05-21 | 2025-10-15 | 2026-11-25 |  | 17.78% | 17.78% | 2026-04-30 | 2026-05-04 10:54
DA00624 | 1 | Hyde, Tyrrell | SS-6201R |  | - | 1 SECTION OF NC-94 & 3 SECTIONS OF SECONDARY ROADS | 0 |  | 16.15 miles | FSC II LLC DBA FRED SMITH COMPANY | STATE FUNDED | Gerard E. Mombaerts | 2527896150 | 2025-07-16 | 2026-05-05 | 2026-12-15 |  | 0% | 0%
DA00625 | 1 | Bertie, Martin |  | None | - | 4 SECTIONS OF PRIMARY & 14 SECTIONS OF SECONDARY ROADS | 2839412.17 | 3 | 18.57 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Gerard E. Mombaerts | 2527896150 | 2025-08-20 | 2025-12-12 | 2027-04-30 |  | 34.29% | 34.29% | 2026-04-15 | 2026-04-21 09:10
DA00632 | 1 | Dare | ER-5600AD |  | - | NAGS HEAD, NC (WHALEBONE JUNCTION) | 0 |  | 0 miles | RICHARD J CARLSON LLC DBA CARLSONS LANDSCAPING | 4630505 | Brandon J. Tatum | 2526216400 | 2025-02-19 |  | 2027-03-01 |  | 0% | 0%
DA00633 | 1 | Dare | ER-5600AE |  | US-158 | KITTY HAWK, NC | 0 |  | 0 miles | RICHARD J CARLSON LLC DBA CARLSONS LANDSCAPING | 4630506 | Brandon J. Tatum | 2526216400 | 2025-02-19 |  | 2027-05-15 |  | 0% | 0%
DA00636 | 1 | Tyrrell |  | Statewide | US-64 | US-64 & NC-94 IN COLUMBIA | 291767.75 | 2 | 0.068 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Gerard E. Mombaerts | 2527896150 | 2025-10-29 | 2026-03-25 | 2026-05-15 |  | 58.01% | 58.01% | 2026-04-30 | 2026-05-07 10:10
DA00637 | 1 | Camden, Dare, Gates, Pasquotank | BO-2401A | None | NC-12 | SOUTH MILLS, GATESVILLE, ELIZABETH CITY, HERTFORD, MANTEO, W AVES & AVON | 359090 | 3 | 0 miles | EASTERN EARTHSCAPES & CONSTRUCTION LLC | 5093003 | Brandon J. Tatum | 2526216400 | 2024-10-16 | 2025-04-01 | 2026-05-01 |  | 79.59% | 79.59% | 2026-04-30 | 2026-05-07 10:10
DA00639 | 1 | Camden, Chowan, Currituck, Perquimans | HS-2401C, HS-2401E, HS-2401G, HS-2401K, HS-2401O, HS-5401D | None | NC-11 | 28 SECTIONS OF PRIMARY ROADS | 805898.58 | 3 | 71.11 miles | PERFORMANCE SEALING & STRIPING LLC | 5097306 | Brandon J. Tatum | 2526216400 | 2025-04-16 | 2025-08-01 | 2025-12-12 |  | 42.77% | 42.77% | 2026-04-30 | 2026-05-11 09:10
DA00641 | 1 | Currituck, Hyde, Tyrrell, Washington | HS-2401, HS-2401L | None | - | DIVISION 1 COUNTIES | 1289800 | 7 | 0 miles | ALS OF NORTH CAROLINA LLC | STATE FUNDED | Jason G. Davidson | 2524821857 | 2025-01-29 | 2025-03-01 | 2027-01-31 |  | 10.37% | 10.37% | 2026-05-01 | 2026-05-05 08:10
DA00642 | 1 | Dare |  | None | US-64 | MANTEO | 892064 | 4 | 4.26 miles | C D ROSE CONSTRUCTION LLC | STATE FUNDED | Brandon J. Tatum | 2526216400 | 2025-01-29 | 2025-03-25 | 2025-05-22 |  | 87.98% | 87.98% | 2025-12-31 | 2026-01-09 10:10
DA00643 | 1 | Currituck, Dare, Pasquotank | HS-2401I, HS-2401J, HS-2401L, HS-2401M | None | - | ELIZABETH CITY, GRANDY, KITTY HAWK, KILL DEVILS HILL | 275364 | 5 | 0 miles | WHITLEY CONTRACTING INC | 5097311 | Brandon J. Tatum | 2526216400 | 2025-07-30 | 2025-09-22 | 2026-05-21 |  | 68.62% | 68.62% | 2026-04-15 | 2026-04-22 08:10
DA00644 | 1 | Hyde |  | Regional | NC-12 | NC-12 OCRACOKE ISLAND | 246722.5 | 2 | 1.348 miles | SAWYER & SONS CONSTRUCTION INC. | TBD | Brandon J. Tatum | 2526216400 | 2025-06-18 | 2025-07-28 | 2025-09-19 |  | 93.45% | 93.45% | 2025-09-15 | 2025-09-18 09:10
DA00647 | 1 | Martin |  | Subregional | SR-1510 | BRIDGE NO. 48 OVER LANIER SWAMP SR-1510 (MILL RD.) | 695570.27 | 4 | 0.108 miles | S&C CONSTRUCTION LLC | STATE FUNDED | Gerard E. Mombaerts | 2527896150 | 2025-10-15 | 2025-12-01 | 2026-07-15 |  | 91.11% | 91.11% | 2026-03-31 | 2026-04-08 08:10
DA00650 | 1 | Currituck |  | Regional | NC-615 | NC-615 KNOTTS ISLAND CAUSEWAY | 481956.75 | 2 | 3.61 miles | BARNHILL CONTRACTING CO | 5080401 | Brandon J. Tatum | 2526216400 | 2025-07-16 | 2025-10-13 | 2026-04-03 |  | 83.73% | 83.73% | 2026-04-15 | 2026-04-22 08:10
DA00651 | 1 | Chowan, Gates, Northampton, Tyrrell | HS-2401Q |  | - | 4 SECTIONS OF PRIMARY ROADS | 0 |  | 60.13 miles | PERFORMANCE SEALING & STRIPING LLC | 5097318 | Edwin W. Rose | 2525136030 | 2026-02-04 |  | 2026-12-15 |  | 0% | 0%
DA00652 | 1 | Chowan, Perquimans |  | Subregional | SR-VARI | 7 SECTIONS OF SECONDARY ROADS | 2218812 | 7 | 13.854 miles | FSC II LLC DBA FRED SMITH COMPANY | STATE FUNDED | Brandon J. Tatum | 2526216400 | 2025-09-17 | 2025-11-05 | 2026-11-06 |  | 91.82% | 91.82% | 2026-04-30 | 2026-05-11 09:10
DA00653 | 1 | Bertie, Hertford, Hyde, Northampton |  |  | SR-VARI | 11 SECTION OF SECONDARY ROADS | 0 |  | 29.996 miles | RILEY PAVING INC RILEY PAVING INC | STATE FUNDED | Gerard E. Mombaerts | 2527896150 | 2025-09-17 |  | 2026-11-06 |  | 0% | 0%
DA00654 | 1 | Northampton |  | None | NC-35 | 2 SECTIONS OF NC-35 & 6 SECTIONS OF SECONDARY ROADS | 2714000 | 3 | 19.942 miles | FSC II LLC DBA FRED SMITH COMPANY | STATE FUNDED | Edwin W. Rose | 2525136030 | 2025-12-17 | 2026-02-24 | 2027-07-30 |  | 42.71% | 42.71% | 2026-04-30 | 2026-05-06 09:10
DA00656 | 1 | Hertford |  |  | NC-VARI | 3 SECTIONS OF PRIMARY & 4 SECTIONS OF SECONDARY ROADS | 0 |  | 10.452 miles | C D ROSE CONSTRUCTION LLC | STATE FUNDED | Edwin W. Rose | 2525136030 | 2025-12-03 | 2026-03-16 | 2027-07-09 |  | 0% | 0%
DA00657 | 1 | Hyde, Tyrrell |  |  | US-264 | 1 SECTION OF US-264, 3 SECTIONS OF NC-45, 1 SECTION OF NC-94 , & 2 SECTIONS OF SECONDARY ROADS | 0 |  | 23.767 miles | FSC II LLC DBA FRED SMITH COMPANY | STATE FUNDED | Gerard E. Mombaerts | 2527896150 | 2026-01-21 | 2026-05-06 | 2027-08-27 |  | 0% | 0%
DA00658 | 1 | Bertie, Hertford |  |  | SR-1304 | 14 SECTIONS OF SECONDARY ROADS | 0 |  | 19.47 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Edwin W. Rose | 2525136030 | 2026-02-18 | 2026-05-04 | 2027-09-24 |  | 0% | 0%
DA00659 | 1 | Bertie, Hertford |  |  | NC-11 | 5 SECTIONS OF NC-11, 2 SECTIONS OF NC-305, AND 5 SECTIONS OF SECONDARY ROADS | 0 |  | 20.037 miles | FSC II LLC DBA FRED SMITH COMPANY | STATE FUNDED | Edwin W. Rose | 2525136030 | 2026-03-04 | 2026-06-01 | 2027-10-08 |  | 0% | 0%
DA00660 | 1 | Currituck |  |  | - | SR-1222 FROM NC-168 TO SR-1214 (GUINEA RD.) | 0 |  | 7.533 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Brandon J. Tatum | 2526216400 | 2026-03-18 |  | 2027-10-22 |  | 0% | 0%
DA00662 | 1 | Tyrrell, Washington |  |  | - | 3 SECTIONS OF NC-32, 1 SECTION OF NC-45, AND 7 SECTIONS OF S ECONDARY ROADS | 0 |  | 18.721 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Gerard E. Mombaerts | 2527896150 | 2026-04-01 |  | 2027-11-05 |  | 0% | 0%
DA00671 | 1 | Camden | ER-5600AB | Statewide | US-17 | DISMAL SWAMP VISITORS CENTER | 141892.75 | 1 | 0 miles | NATURAL CHOICE CONTRACTING LLC | 4630503 | Brandon J. Tatum | 2526216400 | 2025-09-03 | 2026-02-24 | 2027-04-30 |  | 70.94% | 70.94% | 2026-03-31 | 2026-04-07 09:10
DA00673 | 1 | Bertie | HB-0070 | Statewide | US-13 / | BRIDGE REHABILITATION, BRIDGES 070155, 070156, 070158, AND 0 70159 | 2798057.2 | 3 | 0.4 miles | LORR CONSTRUCTION INC | 5130801 | Gerard E. Mombaerts | 2527896150 | 2025-11-19 | 2026-02-23 | 2026-12-14 | 2026-12-21 | 41.64% | 41.64% | 2026-04-30 | 2026-05-07 10:10
DA00674 | 1 | Gates |  |  | SR-1116 | BRIDGE NO. 360007 ON SR 1116 (HARRELLS CHURCH RD) OVER COLE CREEK | 0 |  | 0.102 miles | S T WOOTEN CORPORATION | STATE FUNDED |  | 0 | 2026-04-01 | 2026-06-08 | 2027-02-03 |  | 0% | 0%
DA00675 | 1 | Dare |  | None | US-64 | DARE COUNTY REST AREA ON US-64 IN MANTEO, NC | 1423952 | 4 | 0 miles | A R CHESSON CONSTRUCTION CO INC | STATE FUNDED | Brandon J. Tatum | 2526216400 | 2025-11-05 | 2026-01-05 | 2026-05-15 |  | 41.44% | 41.44% | 2026-04-30 | 2026-05-11 09:10
DB00588 | 2 | Craven |  |  | US-17 | CRAVEN COUNTY | 0 |  | 3.34 miles | S T WOOTEN CORPORATION | STATE FUNDED | Brad T. McMannen, PE | 2526496520 | 2024-10-09 |  | 2026-12-15 |  | 0% | 0%
DB00589 | 2 | Carteret, Pamlico |  | None | SR-1307 | CARTERET AND PAMLICO COUNTY | 1867738.75 | 3 | 11.78 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Brad T. McMannen, PE | 2526496520 | 2025-03-26 | 2025-09-15 | 2027-03-15 |  | 53.38% | 53.38% | 2026-04-30 | 2026-05-07 10:10
DB00590 | 2 | Craven |  |  | - | CRAVEN COUNTY | 0 |  | 13.13 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Brad T. McMannen, PE | 2526496520 | 2024-10-09 |  | 2026-12-15 |  | 0% | 0%
DB00591 | 2 | Craven, Jones |  | None | SR-1004, SR-1143, SR-1144, SR-1166, SR-1176, SR-1186, SR-1187, SR-1188, SR-1189, SR-1244, SR-1328, SR-1335, SR-1340, SR-1344, SR-1345, SR-1426, SR-1445 | CRAVEN AND JONES COUNTY | 2966018.75 | 7 | 16.5 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Stanley L. Harrell | 2525270053 | 2025-03-26 | 2025-09-11 | 2027-03-15 |  | 77.04% | 77.04% | 2026-03-31 | 2026-04-09 09:10
DB00592 | 2 | Greene, Pitt |  | None | SR-1058, SR-1135, SR-1202, SR-1204, SR-1215, SR-1217, SR-1406, SR-1408 | GREENE AND PITT COUNTY | 3412298.25 | 5 | 13.45 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Stanley L. Harrell | 2525270053 | 2024-10-23 | 2025-02-28 | 2026-12-15 |  | 73.33% | 73.33% | 2026-04-15 | 2026-04-23 08:10
DB00593 | 2 | Lenoir |  | None | NC-903 | LENOIR COUNTY | 3485323.86 | 4 | 16.82 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Stanley L. Harrell | 2525270053 | 2025-04-23 | 2025-11-04 | 2027-03-15 |  | 10.22% | 10.22% | 2026-04-22 | 2026-04-29 09:10
DB00594 | 2 | Pitt |  |  | SR-1725, US-13 | PITT COUNTY | 0 |  | 13.98 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Jason B. Beasley | 2524392970 | 2026-02-25 | 2026-03-20 | 2027-11-27 |  | 0% | 0%
DB00595 | 2 | Pitt |  | None | SR-1128, SR-1143, SR-1432, SR-1433, SR-1434, SR-1530, SR-1544, SR-1588, SR-1727, SR-1728, SR-1905 | PITT COUNTY | 3591091 | 7 | 18.19 miles | FSC II LLC DBA FRED SMITH COMPANY | STATE FUNDED | Jason B. Beasley | 2524392970 | 2025-05-14 | 2025-07-08 | 2027-03-15 |  | 73.43% | 73.43% | 2026-01-31 | 2026-02-10 09:10
DB00597 | 2 | Pitt |  |  | SR-1415 | SR 1415 IN PITT COUNTY | 0 |  | 8.18 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Jason B. Beasley | 2524392970 | 2025-06-11 |  | 2027-03-15 |  | 0% | 0%
DB00609 | 2 | Lenoir | BP2-R027 | Subregional | SR-1578 | LENOIR BRIDGE 168 OVER BRIERY RUN ON SR 1578 | 1016106.8 | 7 | 0.088 miles | S T WOOTEN CORPORATION | STATE FUNDED | Stanley L. Harrell | 2525270053 | 2025-03-26 | 2025-05-21 | 2025-12-01 | 2026-08-05 | 85.65% | 85.65% | 2025-11-07 | 2025-11-18 09:10
DB00610 | 2 | Craven, Pamlico |  |  | NC-55 | NC 55 IN CRAVEN AND PAMLICO COUNTIES | 0 |  | 4.06 miles | S T WOOTEN CORPORATION | STATE FUNDED | Brad T. McMannen, PE | 2526496520 | 2025-09-24 |  | 2027-03-15 |  | 0% | 0%
DB00611 | 2 | Pamlico |  |  | NC-55 | NC 55 IN PAMLICO COUNTY | 0 |  | 5.73 miles | S T WOOTEN CORPORATION | STATE FUNDED | Brad T. McMannen, PE | 2526496520 | 2025-09-24 |  | 2027-03-15 |  | 0% | 0%
DB00612 | 2 | Craven |  | Statewide | US-70 | HAVELOCK, CRAVEN COUNTY | 2863629.35 | 2 | 9.15 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Brad T. McMannen, PE | 2526496520 | 2025-10-22 | 2026-03-30 | 2027-07-22 |  | 10.2% | 10.2% | 2026-04-30 | 2026-05-06 09:10
DB00613 | 2 | Pamlico |  |  | - | PAMLICO COUNTY | 0 |  | 12.47 miles | S T WOOTEN CORPORATION | STATE FUNDED | Brad T. McMannen, PE | 2526496520 | 2025-11-12 |  | 2027-08-12 |  | 0% | 0%
DB00614 | 2 | Pamlico |  |  | SR-1324 | PAMLICO COUNTY | 0 |  | 9.13 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Brad T. McMannen, PE | 2526496520 | 2025-10-22 |  | 2027-03-15 |  | 0% | 0%
DB00615 | 2 | Pitt |  | None | SR-1108, SR-1216, SR-1217, SR-1258, SR-1263, SR-1270, SR-1349, SR-1351, SR-1900 | PITT COUNTY | 3283823 | 3 | 13.83 miles | FSC II LLC DBA FRED SMITH COMPANY | STATE FUNDED | Stanley L. Harrell | 2525270053 | 2025-11-12 | 2026-02-10 | 2027-08-12 | 2027-08-14 | 33.14% | 33.14% | 2026-05-07 | 2026-05-15 08:10
DB00616 | 2 | Lenoir |  |  | SR-1102, SR-1103, SR-1109, SR-1709, SR-1710, SR-1711 | LENOIR COUNTY | 0 |  | 12.88 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Stanley L. Harrell | 2525270053 | 2026-03-11 |  | 2027-12-11 |  | 0% | 0%
DB00617 | 2 | Greene, Jones |  |  | SR-1110, SR-1146, SR-1148, SR-1335, SR-1336 | GREENE AND LENOIR COUNTIES | 0 |  | 15.76 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Stanley L. Harrell | 2525270053 | 2026-03-11 |  | 2027-12-11 |  | 0% | 0%
DB00618 | 2 | Craven |  |  | - | 23 SECTIONS OF SECONDARY ROADS | 0 |  | 12.95 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Brad T. McMannen, PE | 2526496520 | 2026-03-25 |  | 2027-12-25 |  | 0% | 0%
DB00620 | 2 | Pitt |  | Subregional | SR-1755 | PITT COUNTY | 3283823 | 2 | 10.05 miles | FSC II LLC DBA FRED SMITH COMPANY | STATE FUNDED | Jason B. Beasley | 2524392970 | 2025-11-12 | 2026-03-18 | 2027-08-12 | 2027-08-13 | 92.04% | 92.04% | 2026-04-30 | 2026-05-07 10:10
DB00622 | 2 | Carteret, Pamlico |  |  | - | 36 SECTIONS OF SECONDARY ROADS IN CARTERET COUNTY AND SR 131 7 IN PAMLICO COUNTY | 0 |  | 13.23 miles | S T WOOTEN CORPORATION | STATE FUNDED | Brad T. McMannen, PE | 2526496520 | 2026-04-08 |  | 2028-01-08 |  | 0% | 0%
DB00625 | 2 | Beaufort |  |  | - | GOOSE CREEK STATE PARK, BEAUFORT COUNTY | 0 |  | 0.279 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Jason B. Beasley | 2524392970 | 2026-01-14 | 2026-03-19 | 2026-04-03 |  | 0% | 0%
DB00627 | 2 | Craven |  |  | - | BRIDGE 240043 OVER SWIFT CREEK ON SR 1465 (BEAVER DAM ROAD) | 0 |  | 0.054 miles | SANFORD CONTRACTORS INC | STATE FUNDED | Stanley L. Harrell | 2525270053 | 2026-04-22 |  | 2026-12-28 |  | 0% | 0%
DB00630 | 2 | Pitt | HS-2402O | None | NC-43 | US 264 AT NC 43 | 100269.11 | 1 | 0 miles | RICK BOSTIC CONSTRUCTION & DEMOLITION INC | 5097416 | Jason B. Beasley | 2524392970 | 2026-03-25 | 2026-04-20 | 2026-06-20 |  | 2.91% | 2.91% | 2026-04-30 | 2026-05-18 08:10
DC00457 | 3 | New Hanover |  | None | SR-1521, SR-1574, SR-1576, US-421 | VARIOUS ROUTES IN NEW HANOVER COUNTY | 3999576.3 | 6 | 0 miles | HIGHLAND PAVING CO LLC | STATE FUNDED | Nathan H. Tew | 9103412000 | 2024-08-15 | 2024-10-29 | 2025-11-21 | 2025-12-01 | 83.42% | 83.42% | 2025-11-30 | 2025-12-09 09:10
DC00464 | 3 | Pender |  | None | NC-210, SR-1313, SR-1318, SR-1402, SR-1404, SR-1534, SR-1604, SR-1605, SR-1673, SR-1674, SR-1674E, SR-1684, SR-1685, SR-1741 | VARIOUS LOCATIONS THROUGHOUT PENDER COUNTY | 3062162.56 | 5 | 17.56 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Bradley L. Haste | 9103475258 | 2024-10-17 | 2025-04-03 | 2026-05-29 |  | 75.65% | 75.65% | 2026-04-30 | 2026-05-11 09:10
DC00471 | 3 | Brunswick |  | Subregional | NC-211 | SR 1528 (E. MOORE ST.) NORTH OF NC 211 OVER PRICE CREEK | 2411021.55 | 10 | 0.202 miles | SMITH-ROWE, LLC | 2024TC8 | Joshua T. Pratt | 9103989100 | 2024-11-07 | 2025-01-14 | 2025-11-12 | 2026-05-02 | 93.81% | 93.81% | 2025-12-12 | 2026-01-13 09:10
DC00472 | 3 | Duplin |  | None | NC-111N, NC-111S, SR-1343, SR-1353, SR-1365, SR-1375, SR-1736 | VARIOUS ROUTES IN DUPLIN COUNTY | 4064583.11 | 7 | 16.71 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Daniel F. Jones | 9106825100 | 2025-02-20 | 2025-06-06 | 2026-05-16 | 2026-05-17 | 86.48% | 86.48% | 2026-04-07 | 2026-04-20 09:10
DC00473 | 3 | New Hanover, Pender |  | None | SR-1329, SR-1330, SR-1336, SR-1394, SR-1572, SR-1941, SR-2018, SR-2042, SR-2053, SR-2054, SR-2094, SR-2095, SR-2096, SR-2108, SR-2152, SR-2153, SR-2154, SR-2171, SR-2216, SR-2245, SR-2262, SR-2265, SR-2320, SR-2321, SR-2630, SR-2722, SR-2862 | VARIOUS | 3303049.75 | 5 | 16.15 miles | BARNHILL CONTRACTING CO |  | Nathan H. Tew | 9103412000 | 2025-02-20 | 2025-04-07 | 2026-05-16 | 2026-05-21 | 60.79% | 60.79% | 2026-05-02 | 2026-05-15 08:10
DC00475 | 3 | Sampson | BP3-R006 | Subregional | SR-1214 | BRIDGE NO. 810085 OVER GREAT COHARIE OVERFLOW ON SR 1214 (BO YKIN BRIDGE ROAD) | 775764.72 | 6 | 0.152 miles | ES WAGNER COMPANY LLC | STATE FUNDED | Daniel F. Jones | 9106825100 | 2025-03-20 | 2025-07-08 | 2026-06-14 | 2026-06-19 | 91.92% | 91.92% | 2026-01-07 | 2026-01-22 08:10
DC00476 | 3 | Onslow |  | None | SR-1230, SR-1251, SR-1273, SR-1439, SR-1501, SR-1653, SR-1715, SR-1732, SR-1930, SR-1931, SR-1932, SR-1986, SR-1987, SR-2389 | VARIOUS ROUTES IN ONSLOW COUNTY | 3991131.48 | 8 | 19.41 miles | S T WOOTEN CORPORATION | STATE FUNDED | Bradley L. Haste | 9103475258 | 2025-04-17 | 2025-08-04 | 2026-08-28 | 2026-08-30 | 61.07% | 61.07% | 2026-04-30 | 2026-05-11 09:10
DC00482 | 3 | Onslow | U-6065 | Statewide | SR-1518, US-17 | US 17 (WILMINGTON HWY.) AT NC 172 (SNEADS FERRY RD.) AND US 17 AT SR 1518 (OLD FOLKSTONE RD.) INTERSECTIONS | 1806940.17 | 6 | 0.308 miles | MILITARY & FEDERAL CONSTRUCTION CO | 4748903 | Bradley L. Haste | 9103475258 | 2025-09-18 | 2025-11-03 | 2027-04-30 |  | 35.21% | 35.21% | 2026-04-30 | 2026-05-12 09:10
DC00484 | 3 | Duplin |  | None | SR-1105, SR-1123, SR-1162, SR-1179, SR-1311, SR-1320, SR-1345, SR-1372, SR-1416, SR-1909, SR-1922 | VARIOUS ROUTES IN DUPLIN COUNTY | 2875485.91 | 5 | 12.68 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Daniel F. Jones | 9106825100 | 2025-09-04 | 2025-10-24 | 2026-11-20 |  | 66.86% | 66.86% | 2026-04-15 | 2026-04-23 08:10
DC00485 | 3 | Onslow | HS-2403AE | None | SR-1112, SR-1144, SR-1145, SR-1150, SR-1151, SR-1152, SR-1164, SR-1179, SR-1267, SR-1438, SR-1471, SR-1507, SR-1510, SR-1523, SR-1535, SR-1647, SR-1689, SR-1702, SR-1802, SR-1803, SR-1854, SR-2201, SR-2307 | VARIOUS ROUTES IN ONSLOW COUNTY | 2938945.23 | 5 | 11.1 miles | S T WOOTEN CORPORATION | FEDERAL | Bradley L. Haste | 9103475258 | 2025-09-18 | 2025-11-10 | 2027-05-21 |  | 72.12% | 72.12% | 2026-04-30 | 2026-05-07 10:10
DC00486 | 3 | Brunswick |  |  | -, SR-1147, SR-1151, SR-1152, SR-1155, SR-1158, SR-1173, SR-1296 | VARIOUS LOCATIONS IN BRUNSWICK COUNTY | 0 |  | 10.1 miles | HIGHLAND PAVING CO LLC | STATE FUNDED | Nathan H. Tew | 9103412000 | 2025-10-02 |  | 2027-05-14 |  | 0% | 0%
DC00487 | 3 | Duplin, Onslow, Pender, Sampson | HS-2403B |  | - | VARIOUS LOCATIONS IN SAMPSON, DUPLIN, PENDER AND ONSLOW COUN TIES | 0 |  | 112.51 miles | MULLENS MARKINGS INC | 5097510 | Daniel F. Jones | 9106825100 | 2026-03-19 |  | 2027-08-13 |  | 0% | 0%
DC00488 | 3 | Sampson |  | None | SR-1277, SR-1289, SR-1296, SR-1356, SR-1749 | SAMPSON | 1934724.88 | 1 | 7.6 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Daniel F. Jones | 9106825100 | 2025-10-16 | 2026-03-13 | 2027-05-21 |  | 23.4% | 23.4% | 2026-04-22 | 2026-04-29 09:10
DC00489 | 3 | Onslow |  |  | -, SR-1203, SR-1204, SR-1207 | VARIOUS LOCATIONS THROUGHOUT DISTRICT 1 | 0 |  | 8.92 miles | SLURRY PAVERS INC | STATE FUNDED | Bradley L. Haste | 9103475258 | 2025-12-18 |  | 2027-02-05 |  | 0% | 0%
DC00490 | 3 | Duplin, Sampson |  |  | -, SR-1112, SR-1403, SR-1404, SR-1405, SR-1561 | DUPLIN & SAMPSON | 0 |  | 16.28 miles | WHITEHURST PAVING CO INC | STATE FUNDED | Daniel F. Jones | 9106825100 | 2025-12-18 |  | 2027-02-05 |  | 0% | 0%
DC00492 | 3 | New Hanover |  |  | -, NC-133, SR-1322 | VARIOUS ROUTES IN NEW HANOVER COUNTY | 0 |  | 16.26 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Nathan H. Tew | 9103412000 | 2025-12-18 |  | 2027-07-16 |  | 0% | 0%
DC00493 | 3 | Pender |  | None | SR-1324, SR-1411, SR-1412, SR-1423, SR-1433, SR-1437, SR-1510, SR-1514, SR-1672, US-1216 | VARIOUS LOCATIONS IN PENDER COUNTY | 3162838.69 | 3 | 19.03 miles | KING ASPHALT INC | STATE FUNDED | Bradley L. Haste | 9103475258 | 2025-11-20 | 2026-01-08 | 2027-06-25 |  | 35.1% | 35.1% | 2026-04-30 | 2026-05-13 08:10
DC00494 | 3 | Duplin | HS-2403C |  | NC-111 | NC - 111 IN DUPLIN COUNTY | 0 |  | 27.84 miles | PERFORMANCE SEALING & STRIPING LLC | 5097503 | Daniel F. Jones | 9106825100 | 2025-12-04 |  | 2027-01-15 |  | 0% | 0%
DC00496 | 3 | Duplin | HS-2403AX |  | - | VARIOUS ROUTES IN DUPLIN COUNTY | 0 |  | 47.49 miles | BARNHILL CONTRACTING CO | 5097551 | Daniel F. Jones | 9106825100 | 2026-04-16 |  | 2027-11-19 |  | 0% | 0%
DC00505 | 3 | New Hanover | W-5703C |  | US-421 | US 421 (CAROLINA BEACH ROAD) FROM S. COLLEGE ROAD TO APPROXI MATELY 200 FEET NORTH OF WILLOUGHBY PARK ROAD | 0 |  | 0.39 miles | CHATHAM CIVIL CONTRACTING LLC | HSIP-0421(091) | Joshua T. Pratt | 9103989100 | 2026-04-16 |  | 2028-04-15 |  | 0% | 0%
DD00455 | 4 | Johnston |  | Subregional | SR-1550, SR-1551 | WINSTON ROAD AT GUY ROAD | 811944.4 | 6 | 0.189 miles | LANIER CONSTRUCTION CO., INC. | STATE FUNDED | Jimmy L. Best | 9192091090 | 2025-08-26 | 2025-10-14 | 2026-11-20 | 2026-11-23 | 63.36% | 63.36% | 2026-04-30 | 2026-05-20 09:10
DD00457 | 4 | Johnston | HL-0127 | Statewide | SR-1553, US-70 | US-70 BUSINESS AT SHOTWELL ROAD | 3722878.96 | 15 | 0.558 miles | S T WOOTEN CORPORATION | 5126501 | Jimmy L. Best | 9192091090 | 2024-07-23 | 2024-11-07 | 2026-03-28 | 2026-09-29 | 87.19% | 87.19% | 2026-05-07 | 2026-05-19 08:10
DD00463 | 4 | Johnston |  | None | SR-1701, SR-1718, SR-1736, SR-1903, SR-1943, SR-2102, SR-2105, SR-2109, SR-2110, SR-2114, SR-2351, SR-2352, SR-2385 | 13 SECTIONS OF SECONDARY ROUTES | 3387163.43 | 6 | 32.35 miles | S T WOOTEN CORPORATION | STATE FUNDED | Jason M. Lee | 9197395300 | 2024-06-25 | 2025-10-24 | 2026-05-01 |  | 94.59% | 94.59% | 2026-04-30 | 2026-05-07 10:10
DD00472 | 4 | Wayne |  | None | SR-1516, SR-1517, SR-1521, SR-1574, SR-1616, SR-1719, SR-1770 | 7 SECTIONS OF SECONDARY ROUTES | 973596.83 | 3 | 13.91 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Jason M. Lee | 9197395300 | 2024-11-12 | 2025-09-08 | 2026-09-18 |  | 79.02% | 79.02% | 2026-05-07 | 2026-05-18 08:10
DD00477 | 4 | Johnston |  | Subregional | SR-1701 | BRIDGE 169 OVER BUFFALO CREEK ON SR 1701 (WENDELL RD) | 2040500 | 8 | 0.17 miles | SANFORD CONTRACTORS INC | STATE FUNDED | Jimmy L. Best | 9192091090 | 2025-08-12 | 2025-09-08 | 2026-12-02 |  | 80.44% | 80.44% | 2026-04-30 | 2026-05-15 08:10
DD00478 | 4 | Halifax, Nash |  | Subregional | SR-1506 | BRIDGE 77 ON AVENT RD/ITA RD OVER FISHING CREEK | 2016500 | 6 | 0.112 miles | SANFORD CONTRACTORS INC | STATE FUNDED | Logan S. Ennis | 2524592129 | 2025-09-23 | 2025-10-31 | 2027-01-26 |  | 62.85% | 62.85% | 2026-04-15 | 2026-04-21 09:10
DD00479 | 4 | Wayne |  |  | - | BRIDGE 219 OVER AYCOCK SWAMP | 0 |  | 0.152 miles | S T WOOTEN CORPORATION | STATE FUNDED | Jimmy L. Best | 9192091090 | 2026-02-24 |  | 2027-06-23 |  | 0% | 0%
DD00481 | 4 | Edgecombe, Wilson | HS-2004AB, HS-2004O | None | SR-1320, US-64B | AIRPORT BLVD AT CHELSEA DR & JETSTREAM DR AND RALEIGH ST AT FAIRVIEW RD/E. GRAND AVE | 777777 | 3 | 0.26 miles | TRAFFIC CONTROL DEVICES LLC | 1320011 | Logan S. Ennis | 2524592129 | 2024-11-12 | 2025-07-06 | 2025-11-27 | 2026-04-09 | 72.21% | 72.21% | 2026-02-28 | 2026-03-18 08:10
DD00482 | 4 | Halifax |  | None | NC-903, SR-1303, SR-1414, SR-1432, SR-1600 | 1 SECTION OF PRIMARY AND 4 SECTIONS OF SECONDARY ROUTES | 2233551.82 | 5 | 16.54 miles | BARNHILL CONTRACTING CO | STATE FUNDED | P. Gray Keeter, PE | 2525835861 | 2024-11-12 | 2025-04-28 | 2026-09-18 |  | 92.39% | 92.39% | 2026-03-31 | 2026-04-30 09:10
DD00483 | 4 | Halifax, Johnston, Nash, Northampton, Wayne, Wilson | HS-2004Y | None | I-587, I-795, I-95, US-117, US-264, US-301, US-64, US-70 | DIVISION WIDE PRIMARY AND INTERSTATE RAMPS | 1329562.4 | 4 | 0 miles | TMI SERVICES INC | 4930620 | Jason M. Lee | 9197395300 | 2024-11-12 | 2025-09-08 | 2026-11-20 |  | 44.41% | 44.41% | 2026-01-15 | 2026-02-09 08:10
DD00484 | 4 | Wilson |  | Statewide | US-301 | 4 SECTIONS OF US-301 NORTHBOUND AND SOUTHBOUND | 2504142.72 | 1 | 11.93 miles | S T WOOTEN CORPORATION | STATE FUNDED | Logan S. Ennis | 2524592129 | 2024-11-26 | 2026-04-22 | 2026-09-18 | 2026-10-03 | 31.31% | 31.31% | 2026-04-30 | 2026-05-11 09:10
DD00488 | 4 | Edgecombe |  | None | NC-42, SR-1109, SR-1162, SR-1169, SR-1225, SR-1413, SR-1414, SR-1533 | 1 SECTION OF NC-42 AND 8 SECTIONS OF SECONDARY ROUTES | 1791245.59 | 1 | 10.65 miles | BARNHILL CONTRACTING CO | STATE FUNDED | P. Gray Keeter, PE | 2525835861 | 2025-05-13 | 2026-04-27 | 2026-12-11 |  | 34.02% | 34.02% | 2026-04-30 | 2026-05-20 09:10
DD00489 | 4 | Nash |  | None | NC-58, SR-1114, SR-1137, SR-1143, SR-1524, SR-1544, SR-1703, SR-1913, SR-1973, SR-1974 | 2 SECTIONS OF PRIMARY ROUTES AND 9 SECTIONS OF SECONDARY ROU TES | 2576905.72 | 5 | 19.81 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Logan S. Ennis | 2524592129 | 2025-05-13 | 2025-07-21 | 2026-12-11 |  | 66.87% | 66.87% | 2026-03-31 | 2026-04-09 09:10
DD00491 | 4 | Wayne, Wilson |  | None | SR-1264, SR-1278, SR-1342, SR-1353, SR-1502, SR-1508, SR-1510, SR-1575, SR-1633, SR-1702, SR-1705, US-13 | 1 PRIMARY ROUTE AND 12 SECTIONS OF SECONDARY ROUTES. | 2813595 | 1 | 23.914 miles | S T WOOTEN CORPORATION | STATE FUNDED | Jason M. Lee | 9197395300 | 2025-05-13 | 2026-03-30 | 2026-12-11 |  | 42.52% | 42.52% | 2026-04-30 | 2026-05-12 09:10
DD00492 | 4 | Wilson |  | None | NC-111, SR-1002, SR-1426, SR-1542, SR-1683 | 1 SECTION OF NC-111 AND 4 SECTIONS OF SECONDARY ROUTES | 1712608 | 4 | 12.1 miles | FSC II LLC DBA FRED SMITH COMPANY | STATE FUNDED | Logan S. Ennis | 2524592129 | 2025-05-27 | 2025-07-15 | 2027-05-14 | 2027-05-21 | 85.64% | 85.64% | 2026-04-30 | 2026-05-11 09:10
DD00495 | 4 | Halifax |  | None | SR-1210, SR-1400, SR-1401, SR-1520 | 4 SECTIONS OF SECONDARY ROUTES | 2067000 | 3 | 16.37 miles | FSC II LLC DBA FRED SMITH COMPANY | STATE FUNDED | P. Gray Keeter, PE | 2525835861 | 2025-05-27 | 2025-09-02 | 2027-05-14 |  | 86.53% | 86.53% | 2025-11-30 | 2025-12-15 09:10
DD00496 | 4 | Johnston | HS-2404G | None | SR-1007, SR-1166, SR-1351 | 2 SECTIONS OF SECONDARY ROUTES AND 2 SECTIONS OF BROGDEN ROA D | 3516185.47 | 2 | 31.57 miles | FSC II LLC DBA FRED SMITH COMPANY | 5097608 | Jimmy L. Best | 9192091090 | 2026-01-27 | 2026-03-30 | 2027-09-03 |  | 24.94% | 24.94% | 2026-04-30 | 2026-05-08 09:10
DD00497 | 4 | Nash |  |  | -, SR-1328, SR-1423, SR-1510, SR-1931 | 6 SECTIONS OF SECONDARY ROUTES | 0 |  | 10.32 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Logan S. Ennis | 2524592129 | 2025-06-24 |  | 2027-05-14 |  | 0% | 0%
DD00498 | 4 | Wayne |  |  | -, SR-1002, SR-1006, SR-1333, SR-1335 | 1 SECTION OF PRIMARY ROUTE AND 9 SECTIONS OF SECONDARY ROUTE S | 0 |  | 27.23 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Jason M. Lee | 9197395300 | 2025-06-24 | 2026-04-30 | 2027-05-14 |  | 0% | 0%
DD00499 | 4 | Nash | HS-2404E |  | SR-1001 | VARIOUS SECONDARY ROUTES | 0 |  | 141.6 miles | PERFORMANCE SEALING & STRIPING LLC | 5097606 | Logan S. Ennis | 2524592129 | 2025-10-28 |  | 2026-12-11 |  | 0% | 0%
DD00500 | 4 | Nash |  | None | - | 1 PRIMARY ROUTE AND 7 SECONDARY ROUTES | 2763672 | 5 | 19.77 miles | FSC II LLC DBA FRED SMITH COMPANY | STATE FUNDED | Logan S. Ennis | 2524592129 | 2025-08-12 | 2025-11-12 | 2027-04-30 |  | 90.32% | 90.32% | 2026-03-31 | 2026-04-09 09:10
DD00501 | 4 | Edgecombe |  |  | NC-42 | 3 SECTIONS OF NC-42 AND 3 SECTIONS OF SECONDARY ROUTES | 0 |  | 11.48 miles | BARNHILL CONTRACTING CO | STATE FUNDED | P. Gray Keeter, PE | 2525835861 | 2025-09-23 |  | 2027-04-30 |  | 0% | 0%
DD00503 | 4 | Wilson |  |  | - | 2 SECTIONS OF PRIMARY ROUTE ON NC-581 | 0 |  | 13.17 miles | FSC II LLC DBA FRED SMITH COMPANY | STATE FUNDED | Logan S. Ennis | 2524592129 | 2026-01-27 |  | 2027-09-03 |  | 0% | 0%
DD00504 | 4 | Johnston | U-5943A | None | NC-42, SR-1003, SR-1004, SR-1525, SR-1550, SR-1552, SR-1553, SR-1560, US-70, US-70BUS | TOWN OF CLAYTON | 3563000 | 3 | 0 miles | TRAFFIC CONTROL DEVICES LLC | 4586202 | Jimmy L. Best | 9192091090 | 2025-09-09 | 2026-02-04 | 2026-09-10 |  | 17.86% | 17.86% | 2026-04-30 | 2026-05-20 09:10
DD00505 | 4 | Johnston | U-5943B | None | NC-42, SR-1003, SR-1004, SR-1553 | TOWN OF CLAYTON | 762850 | 1 | 0 miles | FULCHER ELECTRIC OF FAYETTEVILLE INC | 4586203 | Jimmy L. Best | 9192091090 | 2025-11-25 | 2026-04-28 | 2026-11-26 |  | 6.21% | 6.21% | 2026-04-30 | 2026-05-15 08:10
DD00506 | 4 | Halifax |  | Regional | NC-48 | 2 SECTIONS OF NC-48 PRIMARY ROUTE | 2222222.22 | 2 | 11.47 miles | FSC II LLC DBA FRED SMITH COMPANY | STATE FUNDED | P. Gray Keeter, PE | 2525835861 | 2025-12-09 | 2026-02-10 | 2026-12-11 |  | 35.2% | 35.2% | 2026-03-31 | 2026-05-11 09:10
DD00508 | 4 | Edgecombe |  |  | -, SR-1117, SR-1134, SR-1301, SR-1302, SR-1353, SR-1504 | 7 SECTIONS OF SECONDARY ROUTES | 0 |  | 4.49 miles | SLURRY PAVERS INC | STATE FUNDED | P. Gray Keeter, PE | 2525835861 | 2026-02-24 |  | 2027-08-20 |  | 0% | 0%
DD00509 | 4 | Halifax |  |  | SR-1123, SR-1143, SR-1144, SR-1145, SR-1146, SR-1147, SR-1827 | 7 SECTIONS OF SECONDARY ROUTES | 0 |  | 6.81 miles | BARNHILL CONTRACTING CO | STATE FUNDED | P. Gray Keeter, PE | 2525835861 | 2026-01-27 |  | 2027-03-05 |  | 0% | 0%
DD00511 | 4 | Johnston |  |  | -, SR-2509, US-70BUS | 4 SECTIONS OF US-70 ALT AND 2 SECTIONS OF SECONDARY ROUTES | 0 |  | 19.44 miles | FSC II LLC DBA FRED SMITH COMPANY | STATE FUNDED | Jimmy L. Best | 9192091090 | 2026-02-24 |  | 2027-08-20 |  | 0% | 0%
DD00512 | 4 | Johnston, Wayne | HS-2404B, HS-2404C |  | NC-210, NC-55 | 2 SECTIONS OF NC-210 IN JOHNSTON COUNTY & 2 SECTIONS OF NC-5 5 IN WAYNE COUNTY | 0 |  | 41.52 miles | ROADSAFE TRAFFIC SYSTEMS INC | 5097602 | Jimmy L. Best | 9192091090 | 2026-02-24 |  | 2026-12-11 |  | 0% | 0%
DD00514 | 4 | Wayne |  |  | - | 22 SECTIONS OF SECONDARY ROUTES | 0 |  | 9.31 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Jason M. Lee | 9197395300 | 2026-03-24 |  | 2027-09-24 |  | 0% | 0%
DD00515 | 4 | Nash |  |  | -, SR-1132, SR-1302, SR-1330, SR-1405, SR-1515 | 6 SECTIONS OF SECONDARY ROUTES | 0 |  | 9.05 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Logan S. Ennis | 2524592129 | 2026-03-24 |  | 2027-09-24 |  | 0% | 0%
DD00516 | 4 | Edgecombe |  |  | -, SR-1251 | 3 SECTIONS OF SECONDARY ROUTES | 0 |  | 8.14 miles | SLURRY PAVERS INC | STATE FUNDED | P. Gray Keeter, PE | 2525835861 | 2026-04-14 |  | 2027-10-08 |  | 0% | 0%
DE00353 | 5 | Wake | HL-0008C, HL-0008H | Regional | NC-50 | VARIOUS LOCATIONS IN WAKE CO | 1938091.85 | 10 | 0.349 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Niklaus C. Winkler | 9197339499 | 2025-04-23 | 2025-07-23 | 2026-11-09 |  | 72.96% | 72.96% | 2026-05-15 | 2026-05-20 09:10
DE00366 | 5 | Wake | U-6023 | Statewide | US-VARI | WAKE FOREST | 3600000 | 26 | 1 miles | ALS OF NORTH CAROLINA LLC | 0527020 | David B. Moore | 9192204600 | 2023-07-12 | 2023-08-15 | 2025-08-13 |  | 90.85% | 90.85% | 2026-03-31 | 2026-04-13 09:10
DE00379 | 5 | Wake | HL-0008L | Subregional | SR-1010, SR-1386 | SR 1010 (TEN TEN ROAD) AT SR 1386 (GRAHAM NEWTON/BELLS LAKE ROAD) | 2519833 | 8 | 0.31 miles | CARDINAL CIVIL CONTRACTING LLC | STATE FUNDED | Niklaus C. Winkler | 9197339499 | 2025-05-14 | 2025-08-27 | 2026-11-22 | 2027-03-18 | 64% | 64% | 2026-04-15 | 2026-04-22 08:10
DE00384 | 5 | Person |  |  | -, SR-1121, SR-1338, SR-1339, SR-1406, SR-1594 | VARIOUS LOCATIONS IN PERSON COUNTY | 0 |  | 7.129 miles | RILEY PAVING INC RILEY PAVING INC | STATE FUNDED | Joshua L. Kellen | 2524920111 | 2024-09-11 | 2026-05-13 | 2026-09-30 |  | 0% | 0%
DE00385 | 5 | Franklin, Vance, Warren |  | Subregional | SR-1002, SR-1106, SR-1225, SR-1234, SR-1240, SR-1246, SR-1333, SR-1350, SR-1370, SR-1379, SR-1423, SR-1500, SR-1504, SR-1537, SR-1555, SR-1556, SR-1616, SR-1639 | SECONDARY ROUTES IN FRANKLIN VANCE AND WARREN COUNTIES | 1205395.24 | 1 | 22.942 miles | RILEY PAVING INC RILEY PAVING INC | STATE FUNDED | Joshua L. Kellen | 2524920111 | 2025-01-08 | 2026-02-18 | 2026-09-15 |  | 11.65% | 11.65% | 2026-03-15 | 2026-03-26 09:10
DE00393 | 5 | Wake | HL-0008F | Subregional | SR-1006, SR-1010 | SR 1006 (OLD STAGE ROAD) AT SR 1010 (TEN TEN ROAD) | 2433235 | 7 | 0.165 miles | CARDINAL CIVIL CONTRACTING LLC | 4936724 | Alexander S. Griffis | 9198358200 | 2025-08-13 | 2025-10-03 | 2026-12-01 |  | 79.17% | 79.17% | 2026-04-30 | 2026-05-11 09:10
DE00394 | 5 | Franklin, Granville, Wake |  | Subregional | SR-VARI | 54 SECTIONS OF PRIMARY & SECONDARY ROUTES IN FRANKLIN GRANVI LLE AND WAKE COUNTIES | 2214966.2 | 2 | 16.472 miles | SUNROCK INDUSTRIES LLC DBA CAROLINA SUNROCK LLC | STATE FUNDED | David B. Moore | 9192204600 | 2025-06-11 | 2026-01-08 | 2027-05-15 |  | 8.17% | 8.17% | 2026-02-28 | 2026-03-06 09:10
DE00396 | 5 | Wake | HL-0008Q |  | SR-1386, SR-1390 | SR 1390 (OPTIMIST FARM RD) AND SR 1386 (BELLS LAKE RD) | 0 |  | 0.225 miles | TRIANGLE GRADING & PAVING INC | STATE FUNDED | Alexander S. Griffis | 9198358200 | 2026-04-08 | 2026-05-06 | 2027-06-07 |  | 0% | 0%
DE00397 | 5 | Wake | HS-2005G, HS-2005K, HS-2005Q | Subregional | SR-1142, SR-2036, SR-2108, SR-2214, SR-2215, US-401 | VARIOUS LOCATIONS IN WAKE COUNTY | 857857 | 5 | 0.03 miles | TRAFFIC CONTROL DEVICES LLC | 401312 | Alexander S. Griffis | 9198358200 | 2024-12-11 | 2025-06-16 | 2025-08-29 | 2025-11-10 | 90.5% | 90.5% | 2025-12-22 | 2026-01-13 09:10
DE00404 | 5 | Warren |  | Statewide | US-401 | US 401 MAIN ST AT US 158 BUS MACON ST | 644900 | 5 | 0.061 miles | FSC II LLC DBA FRED SMITH COMPANY | STATE FUNDED | David B. Moore | 9192204600 | 2025-04-23 | 2025-06-09 | 2026-02-28 |  | 91.82% | 91.82% | 2025-12-31 | 2026-01-15 09:10
DE00405 | 5 | Wake |  |  | - | BRIDGE NO 911473 OVER CRABTREE CREEK ON S. TURKEY CREEK TRAI L WILLIAM B. UMSTEAD STATE PARK | 0 |  | 0.023 miles | FSC II LLC DBA FRED SMITH COMPANY | STATE FUNDED | Niklaus C. Winkler | 9197339499 | 2026-04-08 |  | 2027-03-08 |  | 0% | 0%
DE00412 | 5 | Person |  | Subregional | SR-1176 | SR 1176 NEWTON PLEASANT LOOP RD | 577775 | 3 | 0.1 miles | FSC II LLC DBA FRED SMITH COMPANY | DF18405.2073017 | James M. Nordan, PE | 9193174760 | 2025-09-04 | 2025-10-13 | 2026-05-25 |  | 89.89% | 89.89% | 2025-12-31 | 2026-01-13 09:10
DE00417 | 5 | Warren |  | Subregional | SR-1509 | BRIDGE NO 16 OVER BENS CREEK ON SR 1509 ODELL LITTLETON ROAD | 1107900 | 5 | 0.364 miles | SANFORD CONTRACTORS INC | STATE FUNDED | David B. Moore | 9192204600 | 2025-10-22 | 2025-12-08 | 2027-12-08 |  | 60.42% | 60.42% | 2026-04-30 | 2026-05-15 08:10
DE00420 | 5 | Franklin, Warren |  | Statewide | US-401 | US-401 FROM NC-39 TO BEGIN C&G | 2578450.7 | 1 | 17.703 miles | SUNROCK INDUSTRIES LLC DBA CAROLINA SUNROCK LLC | STATE FUNDED | David B. Moore | 9192204600 | 2025-10-22 | 2026-01-14 | 2026-11-30 |  | 5.76% | 5.76% | 2026-01-31 | 2026-02-11 08:10
DE00422 | 5 | Wake |  | Subregional | SR-1160 | SR 1160 OLIVE CHAPEL RD OVER BEAVER CREEK | 2152317.43 | 4 | 0.138 miles | RALPH HODGE CONSTRUCTION COMPANY | STATE FUNDED | Natalia I. Arbelaez | 9198358200 | 2025-11-03 | 2025-11-25 | 2026-11-10 |  | 78.5% | 78.5% | 2026-03-31 | 2026-04-10 09:10
DE00423 | 5 | Franklin |  |  | SR-VARI | VARIOUS ROUTES IN FRANKLIN COUNTY | 0 |  | 14.002 miles | S T WOOTEN CORPORATION | STATE FUNDED |  | 0 | 2025-12-10 |  | 2027-07-12 |  | 0% | 0%
DE00424 | 5 | Granville | HB-0072 | Subregional | SR-1629 | BRIDGE NO 199 OVER FORD CREEK ON SR 1629 FLAT ROCK ROAD | 1176773.1 | 1 | 0.126 miles | S T WOOTEN CORPORATION | 5160901 | James M. Nordan, PE | 9193174760 | 2025-12-10 | 2026-04-13 | 2027-04-21 |  | 14.32% | 14.32% | 2026-04-30 | 2026-05-12 09:10
DE00425 | 5 | Franklin |  | None | NC-39, NC-98, SR-1101 | SOUTHERN FRANKLIN COUNTY | 2397695.82 | 1 | 25.284 miles | FSC II LLC DBA FRED SMITH COMPANY | STATE FUNDED | David B. Moore | 9192204600 | 2025-12-10 | 2026-04-23 | 2027-07-10 |  | 7.25% | 7.25% | 2026-04-30 | 2026-05-12 09:10
DE00426 | 5 | Wake |  |  | - | VARIOUS ROUTES IN SOUTHERN WAKE COUNTY | 0 |  | 23.317 miles | BARNHILL CONTRACTING CO | STATE FUNDED | David W. Conner II | 9197077370 | 2026-01-28 |  | 2027-08-28 |  | 0% | 0%
DE00427 | 5 | Person |  |  | - | VARIOUS ROUTES IN PERSON COUNTY | 0 |  | 8.33 miles | SUNROCK INDUSTRIES LLC DBA CAROLINA SUNROCK LLC | STATE FUNDED | James M. Nordan, PE | 9193174760 | 2026-02-25 |  | 2027-09-25 |  | 0% | 0%
DE00432 | 5 | Warren |  |  | - | VARIOUS ROUTES IN WARREN COUNTY | 0 |  | 13.91 miles | SUNROCK INDUSTRIES LLC DBA CAROLINA SUNROCK LLC | STATE FUNDED |  | 0 | 2026-04-22 |  | 2027-11-22 |  | 0% | 0%
DF00417 | 6 | Harnett | SS-6206AE | Regional | NC-210 | VARIOUS | 2097240.36 | 9 | 10.2 miles | S T WOOTEN CORPORATION | STATE FUNDED | Donavon Hunt | 9103640608 | 2022-11-02 | 2024-05-30 | 2024-06-30 | 2025-09-25 | 94.3% | 94.3% | 2025-06-30 | 2025-07-17 08:10
DF00449 | 6 | Cumberland | W-5806C | Subregional | SR-1615 | SR 1615 AT TAMARACK DRICE AND LANDAU ROAD | 2683561.7 | 17 | 0.189 miles | JYMCO CONSTRUCTION COMPANY INC | 1615(003) | Spencer G. Shoffner, PE | 9103640607 | 2023-09-20 | 2024-04-03 | 2025-11-28 | 2025-12-23 | 77.32% | 77.32% | 2026-03-15 | 2026-05-05 08:10
DF00461 | 6 | Cumberland |  | Regional | NC-53 | NC 53 & NC 87 | 2578201.89 | 3 | 10.32 miles | HIGHLAND PAVING CO LLC | STATE FUNDED | Spencer G. Shoffner, PE | 9103640607 | 2023-12-20 | 2025-10-09 | 2025-07-25 |  | 67.88% | 67.88% | 2026-04-30 | 2026-05-11 09:10
DF00462 | 6 | Cumberland |  | None | - | VARIOUS | 2329072.4 | 4 | 6.74 miles | HIGHLAND PAVING CO LLC | STATE FUNDED | Spencer G. Shoffner, PE | 9103640607 | 2023-12-20 | 2025-04-28 | 2025-07-25 |  | 93.85% | 93.85% | 2025-09-30 | 2025-10-08 08:10
DF00468 | 6 | Columbus |  |  | -, NC-211, SR-1843 | VARIOUS | 0 |  | 13.6 miles | HIGHLAND PAVING CO LLC | STATE FUNDED | Jason A. Johnson | 9107886300 | 2024-02-21 |  | 2025-09-26 | 2026-05-22 | 0% | 0%
DF00469 | 6 | Robeson |  | Subregional | SR-1303 | STRUCTURE 40 OVER RICHLAND SWAMP | 844134.44 | 8 | 0.185 miles | THE TARA GROUP OF LUMBERTON INC | STATE FUNDED | Joseph M. Parker, Jr., PLS | 9103640600 | 2024-09-18 | 2025-04-22 | 2026-04-24 |  | 93.24% | 93.24% | 2026-01-22 | 2026-02-03 08:10
DF00470 | 6 | Bladen, Cumberland, Harnett, Robeson | HS-2006H, HS-2006M, HS-2006W, HS-2006Y, SS-6006BE, SS-6206AH | None | NC-24 | VARIOUS ROUTES | 1927560 | 9 | 76.05 miles | PERFORMANCE SEALING & STRIPING LLC | 0024(093) | Donavon Hunt | 9103640608 | 2024-03-20 | 2024-06-18 | 2025-04-30 |  | 92.47% | 92.47% | 2025-11-15 | 2025-11-19 09:10
DF00472 | 6 | Robeson |  | None | SR-1181, SR-1340, SR-1500, SR-1513, SR-1643, SR-1654, SR-1655, SR-1716, SR-1727, SR-1808, SR-1996, SR-2020, SR-2021, SR-2022 | VARIOUS | 3190698.55 | 7 | 5.08 miles | JOHNSON BROTHERS UTILITY & PAVING COMPANY INC | STATE FUNDED | Joseph M. Parker, Jr., PLS | 9103640600 | 2024-03-06 | 2025-03-07 | 2025-10-03 |  | 88.47% | 88.47% | 2026-04-30 | 2026-05-05 08:10
DF00475 | 6 | Harnett | SS-6206AJ | None | - | VARIOUS | 3178981.79 | 8 | 22.08 miles | HIGHLAND PAVING CO LLC | STATE FUNDED | Donavon Hunt | 9103640608 | 2024-04-03 | 2025-02-25 | 2025-11-07 | 2025-11-22 | 94.55% | 94.55% | 2025-11-30 | 2026-01-02 09:10
DF00484 | 6 | Cumberland |  | Subregional | SR-1414 | STRUCTURE 245 OVER BRANSON CREEK ON SR 1414 (RAEFORD ROAD) | 1072179.5 | 10 | 22.299 miles | MOUNTAIN CREEK CONTRACTORS INC | STATE FUNDED | Spencer G. Shoffner, PE | 9103640607 | 2024-12-04 | 2025-04-14 | 2026-02-12 | 2026-04-09 | 90.3% | 90.3% | 2025-11-22 | 2025-12-04 09:10
DF00485 | 6 | Columbus | BN-0006 | Statewide | US-701 | NC 701 BUSINESS FROM WEST OF LYNWOOD NORRIS ROAD TO US 701 B YPASS | 192050 | 5 | 0.2 miles | MORGAN TRUCKING & GENERAL CONSTRUCTION INC | 5114101 | Jason A. Johnson | 9107886300 | 2025-01-15 | 2025-03-11 | 2026-02-13 | 2026-04-14 | 91.94% | 91.94% | 2026-02-16 | 2026-02-18 09:10
DF00489 | 6 | Cumberland |  | Subregional | SR-2046 | STRUCTURE 250208 OVER TURNBULL CREEK | 1171711 | 4 | 90.057 miles | FSC II LLC DBA FRED SMITH COMPANY | STATE FUNDED | Spencer G. Shoffner, PE | 9103640607 | 2025-02-05 | 2025-06-16 | 2025-11-21 | 2026-04-06 | 91.74% | 91.74% | 2025-10-15 | 2025-10-22 08:10
DF00492 | 6 | Bladen |  | None | SR-1003, SR-1133, SR-1134, SR-1135, SR-1136, SR-1137, SR-1138, SR-1139, SR-1141, SR-1142, SR-1143, SR-1144, SR-1166, SR-1168, SR-1170, SR-1171, SR-1172, SR-1174, SR-1175, SR-1194 | VARIOUS | 1894510.08 | 3 | 46.36 miles | WHITEHURST PAVING CO INC | STATE FUNDED | Jason A. Johnson | 9107886300 | 2024-10-16 | 2024-12-17 | 2026-06-01 |  | 6.72% | 6.72% | 2025-02-28 | 2025-03-07 09:10
DF00493 | 6 | Bladen, Columbus, Cumberland, Harnett | BO-2406A | None | NC-130, NC-210, NC-211, NC-217, NC-41, NC-410, NC-53, NC-55, NC-71, NC-82, NC-87, SR-1121, SR-1140, SR-1145, SR-1300, SR-1301, SR-1303, SR-1425, SR-1574, SR-1700, SR-2442, SR-2835, US-301, US-701, US-74 | VARIOUS | 688923 | 6 | 0 miles | EASTERN EARTHSCAPES & CONSTRUCTION LLC | 5093503 | Jason A. Johnson | 9107886300 | 2024-09-18 | 2025-07-09 | 2026-10-23 |  | 52.85% | 52.85% | 2026-02-22 | 2026-03-05 09:10
DF00496 | 6 | Robeson |  | None | SR-1801, SR-1802, SR-1803, SR-1804, SR-1805, SR-1827, SR-1920, SR-1923, SR-1936, SR-2307, SR-2308, SR-2309, SR-2328, SR-2329, SR-2330, SR-2331 | VARIOUS | 1521087.12 | 2 | 0 miles | JOHNSON BROTHERS UTILITY & PAVING COMPANY INC | STATE FUNDED | Joseph M. Parker, Jr., PLS | 9103640600 | 2024-10-16 | 2026-03-24 | 2026-04-24 |  | 29.15% | 29.15% | 2026-04-30 | 2026-05-05 08:10
DF00500 | 6 | Robeson | HS-2006I | Regional | NC-710 | NC 710 AT SR 1340 (PROSPECT ROAD) | 2067600 | 4 | 0.193 miles | FSC II LLC DBA FRED SMITH COMPANY | 0710(042) | Joseph M. Parker, Jr., PLS | 9103640600 | 2025-06-04 | 2025-08-04 | 2026-06-19 | 2026-06-26 | 90.69% | 90.69% | 2025-12-31 | 2026-01-07 09:10
DF00501 | 6 | Bladen, Columbus, Robeson | HS-2046J, HS-2406A, HS-2406G, HS-2406L | None | NC-130, NC-87, US-301, US-701 | VARIOUS | 1415147 | 5 | 79.865 miles | TRP CONSTRUCTION GROUP LLC | HSIP-5097801 | Jason A. Johnson | 9107886300 | 2025-02-05 | 2025-07-29 | 2026-03-13 | 2026-04-12 | 84.53% | 84.53% | 2026-03-31 | 2026-04-14 15:19
DF00502 | 6 | Bladen | HS-2406HA |  | NC-87 | NC 87 FROM SR 1725 TO DIVIDED HIGHWAY(MP 10.42 TO MP 23.07) | 0 |  | 25.14 miles | HIGHLAND PAVING CO LLC | STATE FUNDED | Kenneth L. Clark | 9107885300 | 2025-03-05 |  | 2026-10-16 |  | 0% | 0%
DF00504 | 6 | Columbus |  | None | SR-1104, SR-1112, SR-1115, SR-1943 | VARIOUS | 1883752.5 | 4 | 0 miles | S T WOOTEN CORPORATION | STATE FUNDED | Kenneth L. Clark | 9107885300 | 2025-02-05 | 2026-01-16 | 2026-08-14 |  | 93.32% | 93.32% | 2026-04-30 | 2026-05-06 09:10
DF00506 | 6 | Robeson |  |  | -, SR-1121, SR-1123, SR-1153, SR-1166, SR-1168, SR-1169, SR-1172, SR-1173, SR-1174, SR-1175, SR-1179, SR-1184, SR-1187, SR-1188, SR-1189, SR-1200, SR-1212, SR-1217, SR-1218, SR-1219 | VARIOUS | 0 |  | 0 miles | RILEY PAVING INC RILEY PAVING INC | STATE FUNDED | Brice Bell, PE | 9107020630 | 2025-02-19 |  | 2026-09-18 |  | 0% | 0%
DF00509 | 6 | Cumberland |  |  | SR-VAR | VARIOUS | 0 |  | 11.21 miles | HIGHLAND PAVING CO LLC | STATE FUNDED | Lee R. Hines, Jr., PE | 9103640601 | 2025-03-26 |  | 2026-10-23 |  | 0% | 0%
DF00512 | 6 | Cumberland | W-5706U | Subregional | SR-1404 | SR 1404 (HAY ST/MORGANTON RD) AT THE INTERSECTION OF SR 3578 (FT BRAGG RD), OAKRIDGE AVE & HIGHLAND AVE | 305299 | 1 | 0 miles | FULCHER ELECTRIC OF FAYETTEVILLE INC | HSIP-1404(017) | Spencer G. Shoffner, PE | 9103640607 | 2025-03-05 | 2025-06-12 | 2025-06-30 |  | 64.41% | 64.41% | 2025-07-15 | 2025-07-21 09:10
DF00513 | 6 | Robeson | SS-6206AM |  | NC-211 | NC 211 FROM I-95 PROJECT I-6064/I-5879 TO SR 1524 | 0 |  | 13.69 miles | JOHNSON BROTHERS UTILITY & PAVING COMPANY INC | STATE FUNDED | Brice Bell, PE | 9107020630 | 2025-04-23 |  | 2026-11-13 |  | 0% | 0%
DF00514 | 6 | Cumberland |  | None | - | ROCK MERRITT AVE FROM NORTH OF BUTNER RD TO NORTH OF BOXCAR ST | 2390597.08 | 4 | 1.147 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Spencer G. Shoffner, PE | 9103640607 | 2025-09-17 | 2026-01-14 | 2027-04-30 | 2027-05-16 | 33.42% | 33.42% | 2026-05-07 | 2026-05-15 08:10
DF00515 | 6 | Harnett |  |  | SR-VAR | VARIOUS | 0 |  | 16.88 miles | JOHNSON BROTHERS UTILITY & PAVING COMPANY INC | STATE FUNDED | Lee R. Hines, Jr., PE | 9103640601 | 2025-04-23 |  | 2026-11-13 |  | 0% | 0%
DF00516 | 6 | Cumberland |  | Subregional | SR-1843 | STRUCTURE 150 OVER BUCK CREEK ON SR 1843 (MAGNOLIA CHURCH RO AD) | 536157.62 | 3 | 0.132 miles | THE TARA GROUP OF LUMBERTON INC | STATE FUNDED | Spencer G. Shoffner, PE | 9103640607 | 2025-06-18 | 2025-12-01 | 2026-10-16 |  | 88.22% | 88.22% | 2026-04-07 | 2026-04-15 08:10
DF00518 | 6 | Cumberland |  | Subregional | SR-1108 | SR 1108 (LAKEWOOD DRIVE) AT TOWBRIDGE ROAD | 1168574.3 | 6 | 0.26 miles | HIGHLAND PAVING CO LLC | STATE FUNDED | Spencer G. Shoffner, PE | 9103640607 | 2025-06-04 | 2025-10-22 | 2026-11-13 |  | 76.23% | 76.23% | 2026-04-22 | 2026-04-30 09:10
DF00520 | 6 | Bladen | HN-0025 | Regional | NC-410 | NC 410 / NC 131 AT NC 211 BYPASS | 2068271.65 | 8 | 0.305 miles | BMCO CONSTRUCTION INC | 5131501 | Jason A. Johnson | 9107886300 | 2025-07-16 | 2025-08-29 | 2027-02-19 | 2027-02-26 | 85.31% | 85.31% | 2026-04-15 | 2026-05-01 09:10
DF00522 | 6 | Columbus |  | Subregional | SR-1818 | STRUCTURE 271 OVER MILL CREEK ON SR 1818 (NEILS EDDY ROAD) | 832628.12 | 2 | 0.148 miles | THE TARA GROUP OF LUMBERTON INC | STATE FUNDED | Jason A. Johnson | 9107886300 | 2025-09-17 | 2026-01-08 | 2026-11-06 |  | 11.23% | 11.23% | 2026-04-07 | 2026-04-21 09:10
DF00524 | 6 | Bladen, Columbus, Cumberland | HS-2406C, HS-2406D, HS-2406E, HS-2406F, HS-2406O, HS-2406P, HS-2406Q | None | US-401 | US 401, US 701 & NC 410 | 1100000 | 7 | 0 miles | ALS OF NORTH CAROLINA LLC | 5097815 | Spencer G. Shoffner, PE | 9103640607 | 2025-08-20 | 2025-10-27 | 2026-03-20 |  | 76.28% | 76.28% | 2026-05-07 | 2026-05-18 08:10
DF00525 | 6 | Bladen, Columbus, Cumberland | HS-2406I | None | US-74 | VARIOUS LOCATIONS ON I-95, US 74, US 301, US 401, NC 24, NC 87 & SR 1007 | 321540 | 1 | 0 miles | BULLINGTON CONSTRUCTION INC | 5097809 | Jason A. Johnson | 9107886300 | 2025-08-20 | 2026-01-12 | 2026-03-20 | 2026-04-19 | 72.8% | 72.8% | 2026-01-31 | 2026-02-10 09:10
DF00526 | 6 | Bladen | HS-2406HB |  | NC-87 | NC 87 FROM COLUMBUS COUNTY TO SR 1725 | 0 |  | 20.86 miles | KING ASPHALT INC | STATE FUNDED | Barry W. Gelezinsky | 9107886300 | 2025-09-03 |  | 2026-11-27 |  | 0% | 0%
DF00528 | 6 | Cumberland |  |  | SR-VAR | Various | 0 |  | 13.18 miles | HIGHLAND PAVING CO LLC | STATE FUNDED | Lee R. Hines, Jr., PE | 9103640601 | 2025-10-01 |  | 2027-05-07 |  | 0% | 0%
DF00529 | 6 | Columbus |  |  | NC-410, SR-1005, SR-1125, SR-1301, SR-1302, SR-1303 | NC 410 AND VARIOUS SR ROUTES | 0 |  | 4.697 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Barry W. Gelezinsky | 9107886300 | 2025-09-17 |  | 2027-04-16 |  | 0% | 0%
DF00530 | 6 | Columbus |  |  | -, SR-1166, SR-1170, SR-1209, SR-1549, SR-1551 | VARIOUS | 0 |  | 7.219 miles | S T WOOTEN CORPORATION | STATE FUNDED | Barry W. Gelezinsky | 9107886300 | 2025-10-01 |  | 2027-05-07 |  | 0% | 0%
DF00531 | 6 | Robeson | SS-6206BC |  | NC-211 | NC 211 FROM SR 1770 TO 0.77 MILES NW OF SR 1505 | 0 |  | 13.9 miles | JOHNSON BROTHERS UTILITY & PAVING COMPANY INC | STATE FUNDED | Brice Bell, PE | 9107020630 | 2025-09-17 |  | 2026-11-06 |  | 0% | 0%
DF00532 | 6 | Robeson |  | None | SR-2208, SR-2218, SR-2236, SR-2248, SR-2280, SR-2282, SR-2283, SR-2285, SR-2327, SR-2337, SR-2338, SR-2339, SR-2466 | VARIOUS | 3763149.65 | 2 | 22.21 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Brice Bell, PE | 9107020630 | 2025-10-01 | 2026-02-09 | 2026-11-13 |  | 11.65% | 11.65% | 2026-04-22 | 2026-04-27 08:10
DF00533 | 6 | Harnett |  |  | - | VARIOUS | 0 |  | 0 miles | JOHNSON BROTHERS UTILITY & PAVING COMPANY INC | STATE FUNDED | Lee R. Hines, Jr., PE | 9103640601 | 2025-11-05 | 2026-05-01 | 2027-06-11 |  | 0% | 0%
DF00534 | 6 | Robeson |  |  | -, SR-1155, SR-2435, SR-2459, SR-2517 | VARIOUS | 0 |  | 36.55 miles | WHITEHURST PAVING CO INC | STATE FUNDED | Brice Bell, PE | 9107020630 | 2025-10-01 |  | 2027-05-07 |  | 0% | 0%
DF00535 | 6 | Columbus |  |  | -, SR-1317, SR-1356, SR-1401, SR-1402, SR-1403, SR-1404, SR-1405, SR-1408, SR-1411, SR-1412, SR-1413, SR-1414, SR-1415, SR-1416, SR-1417, SR-1418, SR-1423, SR-1442, SR-1448 | VARIOUS | 0 |  | 40.58 miles | RILEY PAVING INC RILEY PAVING INC | STATE FUNDED | Barry W. Gelezinsky | 9107886300 | 2025-10-15 |  | 2027-05-21 |  | 0% | 0%
DF00536 | 6 | Cumberland |  | None | SR-1709, SR-1732, SR-1800, SR-1801, SR-1803, SR-1804, SR-1805, SR-1806, SR-1807, SR-1811, SR-1812, SR-1813, SR-1814, SR-1817, SR-1856, SR-1857, SR-1858, SR-1859, SR-1875, SR-1902, SR-1936 | VARIOUS | 168218.75 | 3 | 25.96 miles | GOSHEN CONSTRUCTION LLC | STATE FUNDED | Lee R. Hines, Jr., PE | 9103640601 | 2025-10-01 | 2026-01-05 | 2026-05-29 |  | 54.53% | 54.53% | 2026-04-22 | 2026-04-27 08:10
DF00537 | 6 | Cumberland, Harnett |  |  | - | VARIOUS | 0 |  | 13.04 miles | HIGHLAND PAVING CO LLC | STATE FUNDED | Lee R. Hines, Jr., PE | 9103640601 | 2025-10-15 | 2026-05-01 | 2026-11-20 |  | 0% | 0%
DF00538 | 6 | Cumberland |  |  | - | STRUCTURE 29 AT BUCK CREEK ON SR 1850 | 0 |  | 36.907 miles | ROADWORKS CONSTRUCTION COMPANY LLC | STATE FUNDED | Spencer G. Shoffner, PE | 9103640607 | 2026-01-21 | 2026-05-01 | 2027-05-21 |  | 0% | 0%
DF00540 | 6 | Columbus | HN-0023 |  | US-701 | US 701 BUSINESS (MADISON ST) AT SR 1916 (LEE ST) & SR 1953 ( FRANKLIN ST) | 0 |  | 0 miles | HIGHLAND PAVING CO LLC | 5117301 | Jason A. Johnson | 9107886300 | 2026-02-18 |  | 2026-12-31 |  | 0% | 0%
DF00541 | 6 | Robeson | HN-0020 |  | NC-71 | NC 71 AT SR 1312 (OXENDINE SCHOOL RD / RED HILL RD) | 0 |  | 0 miles | BARNHILL CONTRACTING CO | 5117001 | Joseph M. Parker, Jr., PLS | 9103640600 | 2026-02-18 | 2026-05-19 | 2027-05-14 |  | 0% | 0%
DF00543 | 6 | Bladen | HS-2406N |  | NC-87 | NC 87 AT NC 131 | 0 |  | 0 miles | FULCHER ELECTRIC OF FAYETTEVILLE INC | 5097814 | Jason A. Johnson | 9107886300 | 2026-02-04 | 2026-03-31 | 2026-06-05 |  | 0% | 0%
DF00544 | 6 | Bladen |  | None | SR-1003, SR-1100, SR-1107, SR-1109, SR-1110, SR-1111, SR-1112, SR-1113, SR-1114, SR-1115, SR-1116, SR-1117, SR-1118, SR-1148, SR-1150, SR-1151, SR-1153, SR-1196, SR-1200, SR-1207, SR-1209, SR-1212, SR-1221, SR-1224, SR-1230, SR-1231, SR-1233, SR-1338, SR-1339, SR-1359 | VARIOUS | 2279284.39 | 2 | 48.892 miles | RILEY PAVING INC RILEY PAVING INC | STATE FUNDED | Barry W. Gelezinsky | 9107886300 | 2026-01-07 | 2026-03-04 | 2027-08-06 |  | 7.02% | 7.02% | 2026-04-15 | 2026-04-20 09:10
DF00546 | 6 | Columbus |  |  | -, NC-211, SR-1001 | VARIOUS | 0 |  | 0 miles | S T WOOTEN CORPORATION | STATE FUNDED | Barry W. Gelezinsky | 9107886300 | 2026-03-04 |  | 2027-10-08 |  | 0% | 0%
DF00547 | 6 | Bladen, Columbus |  |  | -, SR-1540 | VARIOUS | 0 |  | 19.067 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Barry W. Gelezinsky | 9107886300 | 2026-03-18 |  | 2027-10-22 |  | 0% | 0%
DF00548 | 6 | Bladen, Columbus, Cumberland, Harnett |  |  | - | VARIOUS | 0 |  | 0 miles | THORN CREEK MARKERS LLC | STATE FUNDED | Donavon Hunt | 9103640608 | 2026-03-18 |  | 2026-10-23 |  | 0% | 0%
DF00549 | 6 | Cumberland |  |  | - | VARIOUS | 0 |  | 0 miles | HIGHLAND PAVING CO LLC | STATE FUNDED | Lee R. Hines, Jr., PE | 9103640601 | 2026-04-01 |  | 2027-11-05 |  | 0% | 0%
DF00550 | 6 | Cumberland |  |  | - | VARIOUS | 0 |  | 0 miles | WHITEHURST PAVING CO INC | STATE FUNDED | Lee R. Hines, Jr., PE | 9103640601 | 2026-04-01 |  | 2027-11-05 |  | 0% | 0%
DF00551 | 6 | Harnett |  |  | - | VARIOUS | 0 |  | 0 miles | S T WOOTEN CORPORATION | STATE FUNDED | Lee R. Hines, Jr., PE | 9103640601 | 2026-04-15 |  | 2027-11-19 |  | 0% | 0%
DF00552 | 6 | Robeson |  |  | -, NC-710, SR-1003, SR-1103, SR-1104, SR-1170 | VARIOUS | 0 |  | 14.48 miles | FSC II LLC DBA FRED SMITH COMPANY | STATE FUNDED | Brice Bell, PE | 9107020630 | 2026-05-06 |  | 2027-12-03 |  | 0% | 0%
DG00613 | 7 | Alamance | U-6017 | Regional | NC-54 | INTERSECTION IMPROVEMENTS AT NC 54 (EAST HARDEN ST) & NC 49 (EAST ELM ST) IN GRAHAM | 4750539.93 | 18 | 0.274 miles | TRIANGLE GRADING & PAVING INC | STATE FUNDED | Bobby J. Howell | 3365706830 | 2024-04-18 | 2024-05-22 | 2025-11-11 | 2026-02-09 | 94.37% | 94.37% | 2025-11-30 | 2025-12-16 08:10
DG00636 | 7 | Guilford | U-5850 | Subregional | SR-1007 | SR 1007(RANDLEMAN RD) FROM ELMSLEY DR TO GLENDALE DR IN GREE NSBORO | 3856392.5 | 2 | 0.371 miles | ATLANTIC CONTRACTING COMPANY INC | STATE FUNDED | Leland J. Barber, PE | 3364877080 | 2025-08-21 | 2025-11-18 | 2027-06-11 |  | 10.59% | 10.59% | 2026-05-07 | 2026-05-14 09:10
DG00641 | 7 | Caswell |  | Subregional | SR-1147 | TWENTY-FOUR SECONDARY ROADS | 1402303.5 | 2 | 32.207 miles | WHITEHURST PAVING CO INC | STATE FUNDED | Jacob B. Harris, PE | 3365206060 | 2024-10-17 | 2025-09-03 | 2026-05-13 |  | 83.82% | 83.82% | 2026-04-30 | 2026-05-08 09:10
DG00643 | 7 | Guilford |  | Statewide | US-158 | SECTIONS OF US 158 E, NC 68 E, NC 68 W & FOURTEEN SECONDARY ROADS | 4499245.1 | 9 | 1.19 miles | APAC ATLANTIC INC THOMPSON ARTHUR DIVISION | STATE FUNDED | Leland J. Barber, PE | 3364877080 | 2024-11-07 | 2025-06-18 | 2026-06-04 |  | 34.85% | 34.85% | 2026-04-30 | 2026-05-06 09:10
DG00644 | 7 | Guilford |  | Regional | NC-62 | ONE PRIMARY AND 36 SECONDARY ROADS | 3267881.92 | 4 | 16.33 miles | VECELLIO & GROGAN INC DBA SHARPE BROTHERS | STATE FUNDED | Jacob T. Crews, PE | 3363751774 | 2025-03-20 | 2025-07-08 | 2026-10-16 |  | 60.54% | 60.54% | 2025-12-31 | 2026-01-08 09:10
DG00645 | 7 | Rockingham |  | Regional | NC-700 | TWO PRIMARY AND TWO SECONDARY ROADS | 4321244.53 | 6 | 12.08 miles | APAC ATLANTIC INC THOMPSON ARTHUR DIVISION | STATE FUNDED | Jacob B. Harris, PE | 3365206060 | 2025-04-03 | 2025-06-16 | 2026-10-30 | 2026-11-03 | 59.56% | 59.56% | 2026-04-30 | 2026-05-18 08:10
DG00646 | 7 | Alamance |  | Subregional | SR-1101 | THIRTY-FOUR SECONDARY ROADS | 1377215.56 | 1 | 31.54 miles | WHITEHURST PAVING CO INC | STATE FUNDED | Bobby J. Howell | 3365706830 | 2025-04-17 | 2026-04-14 | 2026-05-14 |  | 58.77% | 58.77% | 2026-04-30 | 2026-05-12 09:10
DG00648 | 7 | Alamance, Caswell, Rockingham |  | Subregional | SR-1615 | TWENTY-SIX SECONDARY ROADS | 1522999.1 | 1 | 35.143 miles | WAUGH ASPHALT INC | STATE FUNDED | Jacob B. Harris, PE | 3365206060 | 2025-05-01 | 2026-03-30 | 2026-05-28 |  | 83.23% | 83.23% | 2026-04-30 | 2026-05-07 10:10
DG00649 | 7 | Rockingham |  | Subregional | SR-1107 | FOURTY-NINE SECONDARY ROADS | 1608989.26 | 2 | 34.401 miles | CAROLINA ROAD SOLUTIONS LLC | STATE FUNDED | Jacob B. Harris, PE | 3365206060 | 2025-05-01 | 2025-06-24 | 2026-05-28 |  | 58.54% | 58.54% | 2026-04-30 | 2026-05-18 08:10
DG00650 | 7 | Forsyth, Guilford |  |  | SR-1553 | THIRTY-SEVEN SECONDARY ROADS | 0 |  | 15.269 miles | WAUGH ASPHALT INC | STATE FUNDED | Leland J. Barber, PE | 3364877080 | 2025-06-05 | 2026-05-05 | 2026-07-08 |  | 0% | 0%
DG00655 | 7 | Alamance | U-3109A(L), U-3109B(L) | Regional | NC-119 | I-40/I-85 AT NC 119 GRAHAM | 303245.42 | 5 | 0 miles | NATURAL CHOICE CONTRACTING LLC | STATE FUNDED | Bobby J. Howell | 3365706830 | 2024-11-07 | 2024-12-17 | 2028-07-31 |  | 94.4% | 94.4% | 2025-04-30 | 2025-05-05 10:10
DG00657 | 7 | Caswell |  | Regional | NC-62 | TWO PRIMARY AND ONE SECONDARY ROAD | 3810505.17 | 5 | 38.98 miles | FSC II LLC DBA FRED SMITH COMPANY | STATE FUNDED | Jacob B. Harris, PE | 3365206060 | 2025-02-20 | 2025-07-22 | 2026-03-19 |  | 93.8% | 93.8% | 2026-01-13 | 2026-01-23 08:10
DG00658 | 7 | Orange | BL-0044 | Regional | NC-54 | NC 54 FROM WESTBROOK DR IN CARRBORO TO W OF US15/501/NC 86 I NTCHG IN CHAPEL HILL | 2332332 | 1 | 0 miles | FSC II LLC DBA FRED SMITH COMPANY | 4999801 | Bobby J. Howell | 3365706830 | 2025-09-05 | 2026-02-18 | 2027-06-01 |  | 5.63% | 5.63% | 2026-05-07 | 2026-05-19 08:10
DG00659 | 7 | Rockingham | B-5722 | Subregional | SR-1169 | BRIDGE NO. 277 OVER BIG BEAVER CREEK ISLAND ON SR 1169 (ISLA ND DRIVE) | 1966459.99 | 6 | 0 miles | SMITH-ROWE, LLC | BRZ-1169(003) | Jacob B. Harris, PE | 3365206060 | 2025-06-26 | 2025-08-08 | 2026-06-15 |  | 94.26% | 94.26% | 2026-01-15 | 2026-02-09 08:10
DG00661 | 7 | Rockingham |  | Subregional | SR-1002 | BRIDGE NO 18 OVER THE HAW RIVER ON SR 1002(SCALESVILLE RD) | 1057566.2 | 3 | 0.114 miles | APAC ATLANTIC INC THOMPSON ARTHUR DIVISION | STATE FUNDED | Leland J. Barber, PE | 3364877080 | 2025-11-20 | 2026-01-12 | 2026-12-18 | 2026-12-20 | 32.27% | 32.27% | 2026-04-22 | 2026-04-28 09:10
DG00662 | 7 | Rockingham |  | Statewide | US-29 | US 29 - 72" CROSSLINE PIPE CULVERT REHABILITATION NEAR A TRI BUTARY FOR LICK FOR CREEK | 2338841.67 | 3 | 0 miles | SMITH-ROWE, LLC | STATE FUNDED | Jacob B. Harris, PE | 3365206060 | 2025-03-20 | 2025-04-17 | 2026-04-30 |  | 90.15% | 90.15% | 2026-01-31 | 2026-03-04 09:10
DG00663 | 7 | Rockingham | BP7-C001 | Subregional | SR-1785 | EXISTING CULVERT ON SR 1785(CHURCH ST) | 2279670.5 | 8 | 0 miles | ATLANTIC CONTRACTING COMPANY INC | STATE FUNDED | Jacob B. Harris, PE | 3365206060 | 2025-06-19 | 2025-08-14 | 2026-05-04 |  | 66.19% | 66.19% | 2026-04-30 | 2026-05-11 09:10
DG00665 | 7 | Caswell, Orange |  | Regional | NC-119 | ONE PRIMARY ROUTE IN CASWELL AND TWO PRIMARY ROUTES IN ORANG E COUNTY | 2280594.2 | 1 | 6.43 miles | SUNROCK INDUSTRIES LLC DBA CAROLINA SUNROCK LLC | STATE FUNDED | Bobby J. Howell | 3365706830 | 2025-08-07 | 2026-02-17 | 2026-09-03 |  | 1.51% | 1.51% | 2026-04-15 | 2026-04-20 09:10
DG00666 | 7 | Rockingham |  |  | - | 45 SECONDARY ROUTES IN ROCKINGHAM COUNTY | 0 |  | 40.55 miles | WHITEHURST PAVING CO INC | STATE FUNDED | Jacob B. Harris, PE | 3365206060 | 2025-08-07 |  | 2026-09-04 |  | 0% | 0%
DG00667 | 7 | Alamance, Caswell |  |  | SR-1580 | FIFTY-FIVE SECONDARY ROADS IN ALAMANCE AND TWO SECONDARY RO ADS IN CASWELL COUNTY | 0 |  | 42.87 miles | WHITEHURST PAVING CO INC | STATE FUNDED | Bobby J. Howell | 3365706830 | 2025-08-07 | 2026-05-11 | 2026-09-04 |  | 0% | 0%
DG00668 | 7 | Caswell |  | Subregional | SR-1146 | THREE SECONDARY ROADS IN CASWELL COUNTY | 2362221.55 | 2 | 14.96 miles | FSC II LLC DBA FRED SMITH COMPANY | STATE FUNDED | Jacob B. Harris, PE | 3365206060 | 2025-09-18 | 2026-03-23 | 2027-04-30 |  | 86.91% | 86.91% | 2026-04-30 | 2026-05-12 09:10
DG00669 | 7 | Guilford |  | Subregional | SR-2819 | NINE SECONDARY ROADS IN GUILFORD COUNTY | 3049975.83 | 1 | 14.96 miles | VECELLIO & GROGAN INC DBA SHARPE BROTHERS | STATE FUNDED | Jacob T. Crews, PE | 3363751774 | 2025-10-02 | 2026-03-26 | 2027-04-30 |  | 2.03% | 2.03% | 2026-04-30 | 2026-05-08 09:10
DG00670 | 7 | Alamance, Caswell |  |  | SR-1901 | THREE SECONDARY ROADS IN ALAMANCE COUNTY AND ELEVEN SECONDAR Y ROADS IN CASWELL COUNTY | 0 |  | 21.79 miles | WHITEHURST PAVING CO INC | STATE FUNDED | Bobby J. Howell | 3365706830 | 2026-02-05 |  | 2027-03-05 |  | 0% | 0%
DG00671 | 7 | Guilford |  |  | - | THREE PRIMARY AND TWENTY TWO SECONDARY ROADS IN GUILFORD COU NTY | 0 |  | 13.72 miles | APAC ATLANTIC INC THOMPSON ARTHUR DIVISION | STATE FUNDED | Leland J. Barber, PE | 3364877080 | 2026-02-05 |  | 2027-09-05 |  | 0% | 0%
DG00673 | 7 | Guilford | I-5964, W-5807A |  | - | SR 2526(SUMMIT AVE) AT US 70(WENDOVER AVE) EAST EXIT AND ON RAMP; I-40/I85 BUS/SOUTH ELM EUGENGE INTERCHANGE IMPROVEMENT | 0 |  | 0.22 miles | LITTLE MOUNTAIN BUILDERS OF CATAWBA COUNTY LLC | 0040109 | Jacob T. Crews, PE | 3363751774 | 2025-12-18 | 2026-04-22 | 2027-06-14 |  | 0% | 0%
DG00675 | 7 | Rockingham |  | Subregional | SR-2670 | BRIDGE NO 280 OVER LITTLE TROUBLESOME CREEK ON SR 2670(SOUTH SCALES STR) | 2236409.09 | 4 | 0.005 miles | MOUNTAIN CREEK CONTRACTORS INC | STATE FUNDED | Jacob B. Harris, PE | 3365206060 | 2025-11-20 | 2026-01-05 | 2026-12-18 | 2026-12-23 | 47.59% | 47.59% | 2026-04-30 | 2026-05-06 09:10
DG00676 | 7 | Guilford |  | Regional | NC-150 | ONE PRIMARY AND THIRTY-THREE SECONDARY ROADS IN GUILFORD COU NTY | 3593196.4 | 2 | 16.37 miles | BLYTHE CONSTRUCTION INC | STATE FUNDED | Leland J. Barber, PE | 3364877080 | 2025-09-18 | 2025-10-15 | 2027-04-30 |  | 49.92% | 49.92% | 2025-11-30 | 2025-12-04 09:10
DG00677 | 7 | Guilford |  | Subregional | SR-1820 | SKEET CLUB ROAD (SR 1820) | 352342 | 3 | 0 miles | CHAMPION LANDSCAPES INC | STATE FUNDED | Leland J. Barber, PE | 3364877080 | 2025-12-18 | 2026-01-29 | 2028-12-15 |  | 31.14% | 31.14% | 2026-04-22 | 2026-04-30 09:10
DG00683 | 7 | Orange |  |  | SR-1336 | BRIDGE NO 011 OVER ENO RIVER ON SR 1336 (HALLS MILL RD) | 0 |  | 0.161 miles | SMITH-ROWE, LLC | STATE FUNDED | Bobby J. Howell | 3365706830 | 2026-04-16 |  | 2027-10-30 |  | 0% | 0%
DG00685 | 7 | Rockingham |  | Regional | NC-87 | INTERSECTION OF BRIDGE ST (OLD STATE HWY 87) AND BOONE RD/WA SHINGTON ST (OLD STATE HWY 770) IN EDEN | 4321368.64 | 1 | 0.238 miles | APAC ATLANTIC INC THOMPSON ARTHUR DIVISION | STATE FUNDED | Jacob B. Harris, PE | 3365206060 | 2026-02-19 | 2026-04-16 | 2027-12-30 |  | 4.03% | 4.03% | 2026-04-30 | 2026-05-08 09:10
DH00571 | 8 | Randolph | BO-2408A | None | NC-42 | VARIOUS | 440967 | 4 | 0 miles | EASTERN EARTHSCAPES & CONSTRUCTION LLC | 5093703 | Cary A. Fine, PE | 7049834400 | 2024-12-10 | 2025-08-19 | 2026-02-01 |  | 90.83% | 90.83% | 2025-12-31 | 2026-01-07 09:10
DH00573 | 8 | Randolph |  | Subregional | SR-1005 | BRIDGE #162 OVER BRUSH CREEK ON SR 1005 (LANES MILL ROAD) | 2533314.38 | 1 | 0.263 miles | SMITH-ROWE, LLC | STATE FUNDED | Joshua S. Brooks | 3363184020 | 2025-11-25 | 2026-03-30 | 2027-03-24 |  | 2.79% | 2.79% | 2026-04-15 | 2026-04-29 09:10
DH00577 | 8 | Montgomery, Moore |  | None | - | BRIDGE #26 OVER DROWNING CREEK ON SR 1124/SR 1531 (DERBY ROA D) | 1311690.93 | 9 | 0.248 miles | DELLINGER INC | STATE FUNDED | James A. Dietrich | 9109442344 | 2025-03-25 | 2025-05-20 | 2026-05-14 |  | 94.08% | 94.08% | 2026-03-12 | 2026-03-18 08:10
DH00578 | 8 | Hoke |  | None | - | BRIDGE #39 AND BRIDGE #40 OVER BIG MARSH SWAMP ON SR 1436 (B ALFOUR ROAD) | 1538404.26 | 9 | 0.328 miles | THE TARA GROUP OF LUMBERTON INC | STATE FUNDED | James A. Dietrich | 9109442344 | 2025-03-11 | 2025-06-03 | 2026-06-25 |  | 92.51% | 92.51% | 2026-04-07 | 2026-04-15 08:10
DH00582 | 8 | Chatham | W-5808B | None | US-421 | 1/2 MILE NORTH OF US421 & NC902. 1/2 MILE SOUTH OF SR2000& S R2109 | 1459541 | 8 | 1.1 miles | FSC II LLC DBA FRED SMITH COMPANY | W-5808B | Jeremy B. Phillips | 9197769623 | 2025-05-27 | 2025-08-07 | 2025-12-15 |  | 85.26% | 85.26% | 2026-03-31 | 2026-04-16 08:10
DH00584 | 8 | Montgomery | BO-2408D | None | NC-134, NC-24BUS, SR-1005, SR-1333, SR-1383, SR-1403 | VARIOUS | 524720 | 4 | 0 miles | EASTERN EARTHSCAPES & CONSTRUCTION LLC | BO-2408D | Joshua S. Brooks | 3363184020 | 2025-05-13 | 2025-10-21 | 2026-06-30 |  | 89.78% | 89.78% | 2026-01-31 | 2026-02-09 08:10
DH00585 | 8 | Montgomery | BO-2408E | None | NC-109, NC-211, NC-73, NC-731, SR-1108, SR-1517, US-220ALT | VARIOUS | 185618 | 2 | 0 miles | EASTERN EARTHSCAPES & CONSTRUCTION LLC | BO-2408E | Joshua S. Brooks | 3363184020 | 2025-05-13 | 2026-02-09 | 2026-06-30 |  | 92.69% | 92.69% | 2026-03-31 | 2026-04-07 09:10
DH00586 | 8 | Montgomery | BO-2408F | None | - | VARIOUS | 346790 | 2 | 0 miles | EASTERN EARTHSCAPES & CONSTRUCTION LLC | 5093708 | Joshua S. Brooks | 3363184020 | 2025-06-10 | 2026-03-26 | 2026-06-30 |  | 89.23% | 89.23% | 2026-04-30 | 2026-05-08 09:10
DH00587 | 8 | Chatham, Lee |  | None | SR-1380 | VARIOUS | 1695891.7 | 5 | 0 miles | WAUGH ASPHALT INC | STATE FUNDED | Jeremy B. Phillips | 9197769623 | 2025-05-27 | 2025-10-21 | 2026-09-30 |  | 65.13% | 65.13% | 2026-04-30 | 2026-05-07 10:10
DH00592 | 8 | Randolph |  | None | SR-2863 | BRIDGE #305 OVER MEADOW CREEK ON SR 2863 (UNION GROVE CHURCH ROAD) | 712125.85 | 3 | 0.089 miles | NJR GROUP INC | STATE FUNDED | Joshua S. Brooks | 3363184020 | 2025-08-26 | 2026-02-09 | 2026-12-26 |  | 61.69% | 61.69% | 2026-04-30 | 2026-05-06 09:10
DH00593 | 8 | Chatham, Lee, Moore, Scotland | BO-2408C | None | SR-1739 | VARIOUS | 807661.87 | 2 | 0 miles | EASTERN EARTHSCAPES & CONSTRUCTION LLC | BO-2408C | Jeremy B. Phillips | 9197769623 | 2025-07-22 | 2026-03-02 | 2026-06-30 |  | 51.35% | 51.35% | 2026-04-30 | 2026-05-12 09:10
DH00594 | 8 | Moore |  |  | - | NC 2 (MIDLAND ROAD AND SR 2035 (MIDLAND ROAD) | 0 |  | 0 miles | S T WOOTEN CORPORATION | STATE FUNDED | James A. Dietrich | 9109442344 | 2025-09-23 |  | 2026-11-30 |  | 0% | 0%
DH00596 | 8 | Richmond |  | None | - | VARIOUS SECONDARY ROUTES | 954654.19 | 2 | 18.26 miles | WAUGH ASPHALT INC | STATE FUNDED | James A. Dietrich | 9109442344 | 2025-10-28 | 2026-02-23 | 2026-11-30 |  | 34.46% | 34.46% | 2026-03-31 | 2026-04-06 08:10
DH00597 | 8 | Chatham |  | None | NC-751 | VARIOUS | 1124530.9 | 2 | 0 miles | FSC II LLC DBA FRED SMITH COMPANY | STATE FUNDED | Jeremy B. Phillips | 9197769623 | 2025-12-09 | 2026-02-10 | 2026-11-30 |  | 8.94% | 8.94% | 2026-03-15 | 2026-04-07 09:10
DH00598 | 8 | Hoke | BO-2408I |  | - | VARIOUS | 0 |  | 0 miles | EASTERN EARTHSCAPES & CONSTRUCTION LLC | 5093711/DH00598 | James A. Dietrich | 9109442344 | 2026-02-10 |  | 2026-11-30 |  | 0% | 0%
DH00599 | 8 | Hoke, Scotland |  |  | - | VARIOUS | 0 |  | 0 miles | WHITEHURST PAVING CO INC | STATE FUNDED | James A. Dietrich | 9109442344 | 2026-02-10 |  | 2026-11-30 |  | 0% | 0%
DH00601 | 8 | Montgomery |  |  | - | VARIOUS | 0 |  | 0 miles | WAUGH ASPHALT INC | STATE FUNDED | Joshua S. Brooks | 3363184020 | 2026-02-10 |  | 2026-11-30 |  | 0% | 0%
DH00603 | 8 | Scotland | HS-2008E |  | US-74 | US 74 AT NC 144 | 0 |  | 0 miles | BARNHILL CONTRACTING CO | 0074253 | James A. Dietrich | 9109442344 | 2026-04-14 |  | 2027-06-30 |  | 0% | 0%
DH00607 | 8 | Randolph |  |  | - | VARIOUS | 0 |  | 0 miles | WAUGH ASPHALT INC | STATE FUNDED | Joshua S. Brooks | 3363184020 | 2026-03-24 |  | 2026-12-01 |  | 0% | 0%
DI00329 | 9 | Rowan | HE-0009 | Regional | NC-152 | NC 152 FROM EAST OF I-85/US 601 INTERCHANGE TO 800' WEST OF SR 2648(TIMBERFIELD TRAIL) | 4150391 | 12 | 0.435 miles | PERFORMANCE MANAGED CONSTRUCTION INC | STATE FUNDED | Phillip Kelly Seitz, PE | 7046303200 | 2024-11-13 | 2025-03-21 | 2026-05-15 | 2026-09-04 | 72.44% | 72.44% | 2026-04-30 | 2026-05-11 09:10
DI00332 | 9 | Davie, Forsyth | I-0911A(L) | Statewide | I-40 | I-40, WEST OF 801 IN DAVIE COUNTY TO EAST OF SR 1101(HARPER RD) IN FORSYTH COUNTY | 1049198.15 | 13 | 4.07 miles | COUNTRY BOY LANDSCAPING INC | STATE FUNDED | Nicholas C. Librandi | 3367477950 | 2023-08-23 | 2023-09-25 | 2025-05-30 | 2026-05-30 | 92.1% | 92.1% | 2025-12-31 | 2026-01-07 09:10
DI00350 | 9 | Rowan | W-5709E | Regional | NC-153 | NC 153(RICE ST) AT SR 1197(CANNON FARM RD/MOUNT MORIAH CH RD ) IN CHINA GROVE | 2542800.86 | 12 | 0.128 miles | NJR GROUP INC | HSIP-0153(007) | Phillip Kelly Seitz, PE | 7046303200 | 2024-08-28 | 2025-03-28 | 2026-05-21 | 2026-08-23 | 87.53% | 87.53% | 2026-04-30 | 2026-05-15 08:10
DI00352 | 9 | Forsyth | U-2579B(L) | Regional | NC-74 | WINSTON SALEM NORTHERN BELTWAY(NC 74 FUTURE I-74) FROM US 42 1 TO US 52 | 2432485.7 | 15 | 13.5 miles | COUNTRY BOY LANDSCAPING INC | STATE FUNDED | Scott A. Jones | 9197072400 | 2024-08-28 | 2024-10-14 | 2028-09-29 |  | 45.56% | 45.56% | 2026-03-31 | 2026-04-13 09:10
DI00360 | 9 | Davie |  | Statewide | US-64 | ONE PRIMARY AND FOUR SECONDARY ROUTES IN DAVIE COUNTY | 4645895.1 | 3 | 19.605 miles | APAC ATLANTIC INC THOMPSON ARTHUR DIVISION | STATE FUNDED | Eric T. Goldston | 7046303220 | 2024-09-25 | 2025-11-04 | 2026-10-30 |  | 43.51% | 43.51% | 2026-04-30 | 2026-05-19 08:10
DI00361 | 9 | Stokes |  | Statewide | US-52 | US NORTH AND SOUTHBOUND IN STOKES CO FROM LITTLE YADKIN RIVE R BRIDGES(#29 & 30) TO THE SURRY CO LINE | 4943449.32 | 2 | 5.895 miles | APAC ATLANTIC INC THOMPSON ARTHUR DIVISION | STATE FUNDED | Kevin R. Hedrick, PE | 3367477900 | 2024-10-23 | 2026-03-22 | 2026-08-14 |  | 53.22% | 53.22% | 2026-04-30
DI00365 | 9 | Forsyth | HS-2409A | Regional | NC-150 | INTERSECTION OF NC 150 AND SR 2983(FISHEL ROAD) | 1018919 | 5 | 0.251 miles | ATLANTIC CONTRACTING COMPANY INC | 5098101 | Scott A. Jones | 9197072400 | 2025-02-26 | 2025-07-18 | 2026-03-19 | 2026-03-29 | 87.91% | 87.91% | 2026-01-20 | 2026-01-22 08:10
DI00367 | 9 | Stokes |  | Subregional | SR-1941 | SIX SECONDARY ROUTES IN STOKES COUNTY | 3962603.39 | 4 | 17.544 miles | APAC ATLANTIC INC THOMPSON ARTHUR DIVISION | STATE FUNDED | Nicholas C. Librandi | 3367477950 | 2025-02-26 | 2025-09-26 | 2026-08-28 |  | 50.7% | 50.7% | 2026-04-15 | 2026-04-20 09:10
DI00368 | 9 | Forsyth | U-2579DA | Statewide | I-74 | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION (FUTURE I-74 ); FROM US 311 TO SR 2211 (BAUX MOUNTAIN ROAD) | 4458549.43 | 5 | 0.515 miles | SMITH-ROWE, LLC | 3483901 | Nicholas C. Librandi | 3367477950 | 2025-06-25 | 2025-07-28 | 2027-02-26 |  | 37.11% | 37.11% | 2026-04-15 | 2026-04-29 09:10
DI00371 | 9 | Rowan | BP9.R012 | Subregional | SR-1004 | REPLACE BRIDGE #108 ON SR 1004 (STOKES FERRY RD) OVER TUCKER TOWN RESERVOIR | 4105055.24 | 6 | 0.173 miles | SMITH-ROWE, LLC | STATE FUNDED | Eric T. Goldston | 7046303220 | 2025-10-22 | 2025-12-01 | 2027-04-27 |  | 48.45% | 48.45% | 2026-05-02 | 2026-05-18 08:10
DI00373 | 9 | Forsyth | HS-2409C | Subregional | SR-1725 | SR 1725(UNIVERSITY PARKWAY/CHERRYST) AT WEST 14TH STREET IN WINSTON SALEM | 367767.5 | 3 | 0.034 miles | ATLANTIC CONTRACTING COMPANY INC | 5098102 | Kevin R. Hedrick, PE | 3367477900 | 2025-09-24 | 2025-11-24 | 2026-04-30 | 2026-06-29 | 61.06% | 61.06% | 2026-04-30 | 2026-05-20 09:10
DI00375 | 9 | Davie |  |  | US-601 | THREE SECTIONS OF PRIMARY AND TWO SECTIONS OF SECONDARY ROUT ES IN DAVIE COUNTY | 0 |  | 16.086 miles | APAC ATLANTIC INC THOMPSON ARTHUR DIVISION | STATE FUNDED | Eric T. Goldston | 7046303220 | 2025-09-24 |  | 2027-10-29 |  | 0% | 0%
DI00376 | 9 | Forsyth |  |  | - | VARIOUS ROUTES IN FORSYTH COUNTY, 32 SECTIONS OF SECONDARY R OUTES. | 0 |  | 7.19 miles | WAUGH ASPHALT INC | STATE FUNDED | Kevin R. Hedrick, PE | 3367477900 | 2025-12-10 |  | 2026-10-30 |  | 0% | 0%
DI00377 | 9 | Rowan |  |  | - | 18 SECTIONS OF SECONDARY ROUTES IN ROWAN COUNTY AND 32 SECTI ONS OF CITY STREETS IN SALISBURY | 0 |  | 20.58 miles | CAROLINA ROAD SOLUTIONS LLC | STATE FUNDED | Phillip Kelly Seitz, PE | 7046303200 | 2025-11-12 |  | 2026-10-30 |  | 0% | 0%
DI00378 | 9 | Rowan | BP9.R096 | Subregional | SR-1547 | BRIDGE 790254 OVER KERR CREEK ON SR 1547 (CALDWELL ROAD) | 1236890.39 | 1 | 0.112 miles | SMITH-ROWE, LLC | STATE FUNDED | Eric T. Goldston | 7046303220 | 2026-02-25 | 2026-04-06 | 2027-02-01 |  | 21.66% | 21.66% | 2026-04-30 | 2026-05-18 08:10
DI00379 | 9 | Davie |  |  | - | VARIOUS ROUTES IN DAVIE COUNTY, 48 SECTIONS OF SECONDARY ROU TES | 0 |  | 8.21 miles | SLURRY PAVERS INC | STATE FUNDED | Phillip Kelly Seitz, PE | 7046303200 | 2025-11-12 |  | 2026-10-30 |  | 0% | 0%
DI00380 | 9 | Davidson |  |  | - | 38 SECTIONS OF SECONDARY ROUTES IN DAVIDSON COUNTY AND 15 SE CTIONS OF STREETS IN THE TOWN OF DENTON | 0 |  | 16.32 miles | WAUGH ASPHALT INC | STATE FUNDED | Eric T. Goldston | 7046303220 | 2025-12-10 |  | 2026-10-30 |  | 0% | 0%
DI00381 | 9 | Stokes |  |  | SR-1649 | 5 SECTIONS OF SECONDARY ROUTES IN STOKES COUNTY | 0 |  | 13.65 miles | WHITEHURST PAVING CO INC | STATE FUNDED | Nicholas C. Librandi | 3367477950 | 2026-01-28 |  | 2026-10-30 |  | 0% | 0%
DI00382 | 9 | Davidson, Davie, Rowan | HS-2409D, HS-2409F, HS-2409G, HS-2409H, HS-2409I, HS-2409J |  | SR-1741 | SR 1741 DAVIDSON COUNTY, NC 152 ROWAN COUNTY, US 64, US 601, NC 801, US 158 DAVIE COUNTY | 0 |  | 45.364 miles | TRP CONSTRUCTION GROUP LLC | 5098109 | Eric T. Goldston | 7046303220 | 2026-01-28 |  | 2026-06-16 |  | 0% | 0%
DJ00459 | 10 | Cabarrus | I-3802AA | Statewide | I-85 | I-85 FROM NC 73 TO THE ROWAN COUNTY LINE | 2192192 | 18 | 8 miles | TRAFFIC CONTROL DEVICES LLC | NHIMF-085-2(80)55 | Michael Mariano | 7049834380 | 2023-02-15 | 2023-09-05 | 2025-01-26 | 2025-02-25 | 73.27% | 73.27% | 2026-03-31 | 2026-04-09 09:10
DJ00487 | 10 | Cabarrus |  | None | SR-1169, SR-1461, SR-2372, SR-2373, SR-2389, SR-2390, SR-2707, SR-2708, SR-2709, SR-2720, SR-2721, SR-2817, SR-2925, SR-2926, SR-2927, SR-2928, SR-2929, SR-2930, SR-2931, SR-2932, SR-2933, SR-2934, SR-2935, SR-2936, SR-2941, SR-2942, SR-2943, SR-2944, SR-2945, SR-2946, SR-2947, SR-2948, SR-2949, SR-2950, SR-2951, SR-2952, SR-2953, SR-2954 | 38 SECONDARY ROADS IN VARIOUS LOCATIONS | 2686439.47 | 2 | 9.22 miles | NJR GROUP INC | STATE FUNDED | Michael Mariano | 7049834380 | 2024-03-06 | 2026-03-03 | 2025-10-11 |  | 68.32% | 68.32% | 2026-04-30 | 2026-05-13 08:10
DJ00496 | 10 | Anson |  | None | US-52, US-74 | 1 SECTION OF US 74, 1 SECTION OF US 52 AND 2 SECONDARY ROADS | 3550377.15 | 10 | 9.13 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Jake R. Koltiska | 7042185125 | 2023-11-15 | 2024-05-06 | 2025-10-12 | 2025-10-14 | 88.69% | 88.69% | 2025-06-26 | 2025-06-30 09:30
DJ00512 | 10 | Cabarrus |  | None | SR-1431, SR-2429, SR-2882 | 3 SECONDARY ROADS IN VARIOUS LOCATIONS | 2311942.76 | 6 | 9.02 miles | NJR GROUP INC | STATE FUNDED | Bradley S. Eagle | 7049834380 | 2024-03-20 | 2025-04-01 | 2025-11-11 |  | 84.54% | 84.54% | 2025-11-30 | 2025-12-10 09:10
DJ00513 | 10 | Mecklenburg |  | None | NC-24, SR-1009, SR-1477, SR-1494, SR-1540, SR-1561, SR-2373, SR-4979 | 2 SECTIONS OF NC 24 AND 7 SECTIONS OF SECONDARY ROADS | 3414885.3 | 4 | 7.33 miles | BLYTHE CONSTRUCTION INC | STATE FUNDED | Michael W. Hedrick, PE | 9805230080 | 2024-03-06 | 2025-08-10 | 2025-10-17 | 2026-09-05 | 50.24% | 50.24% | 2026-04-30 | 2026-05-11 09:10
DJ00531 | 10 | Anson |  | None | SR-1003 | 33 SECONDARY ROUTES IN VARIOUS LOCATIONS | 730463.04 | 2 | 71.28 miles | CAROLINA ROAD SOLUTIONS LLC | STATE FUNDED | Jake R. Koltiska | 7042185125 | 2024-09-18 | 2025-09-24 | 2026-05-29 |  | 92.68% | 92.68% | 2025-11-30 | 2025-12-22 09:10
DJ00532 | 10 | Mecklenburg |  | None | NC-160 | 1 SECTION OF NC 73, 2 SECTIONS OF NC 160 AND 5 SECTIONS OF S ECONDARY ROADS | 3632297.55 | 2 | 9.09 miles | BLYTHE CONSTRUCTION INC | STATE FUNDED | Michael W. Hedrick, PE | 9805230080 | 2024-11-06 | 2026-03-01 | 2026-06-09 |  | 57.36% | 57.36% | 2026-04-30 | 2026-05-11 09:10
DJ00533 | 10 | Anson |  | Statewide | US-52, US-74 | 1 SECTION OF US 74 WB AND 2 SECTIONS OF US 52 NB | 2556842.22 | 4 | 6.39 miles | J T RUSSELL & SONS INC | STATE FUNDED | Jake R. Koltiska | 7042185125 | 2024-10-16 | 2025-07-31 | 2026-10-05 |  | 76.69% | 76.69% | 2025-12-31 | 2026-02-20 09:10
DJ00534 | 10 | Mecklenburg |  | None | NC-115 | 4 SECTIONS OF NC 115 AND 3 SECTIONS OF SECONDARY ROADS | 3831698.69 | 6 | 9.17 miles | BLYTHE BROTHERS ASPHALT CO LLC | STATE FUNDED | Michael W. Hedrick, PE | 9805230080 | 2025-01-15 | 2025-06-23 | 2026-08-14 | 2026-08-21 | 75.35% | 75.35% | 2026-03-31 | 2026-04-15 08:10
DJ00535 | 10 | Stanly |  | None | NC-205, SR-1719, US-52 | 1 SECTION OF US 52, 1 SECTION OF NC 742/NC 205, AND SR 1719 (FALLS RD) | 1231552.75 | 5 | 2.5 miles | J T RUSSELL & SONS INC | STATE FUNDED | Bradley S. Eagle | 7049834380 | 2024-12-04 | 2025-10-03 | 2026-10-07 |  | 93.14% | 93.14% | 2026-04-30 | 2026-05-07 10:10
DJ00540 | 10 | Cabarrus |  |  | SR-1132, SR-1600, US-601 | 1 SECTION OF US 601 AND 4 SECTIONS OF VARIOUS SECONDARY ROUT ES | 0 |  | 9.2 miles | NJR GROUP INC | STATE FUNDED | Bradley S. Eagle | 7049834380 | 2024-12-04 |  | 2026-10-07 |  | 0% | 0%
DJ00542 | 10 | Union |  | None | US-742, US-75 | NC 75, NC 742, & 6 SECONDARY ROADS - SR 2136, SR 1121, SR 17 51, SR 1003, SR 1134, SR 3515 | 3563909.01 | 4 | 11.39 miles | TRUEROCK CONSTRUCTION LLC | STATE FUNDED | Jake R. Koltiska | 7042185125 | 2024-12-18 | 2026-01-13 | 2026-11-02 | 2026-11-22 | 73.33% | 73.33% | 2026-04-30 | 2026-05-11 09:10
DJ00543 | 10 | Mecklenburg |  | None | SR-2442 | 10 SECTIONS OF SECONDARY ROADS | 2509421.32 | 1 | 7.43 miles | BLYTHE CONSTRUCTION INC | STATE FUNDED | Michael W. Hedrick, PE | 9805230080 | 2025-02-05 | 2026-03-11 | 2026-09-07 |  | 2.06% | 2.06% | 2026-04-30 | 2026-05-11 09:10
DJ00546 | 10 | Union | BP10-R008 | Subregional | SR-2102 | BRIDGE #890146 OVER LITTLE RICHARDSON CREEK ON SR 2102 (MEDL IN ROAD) | 1080932.75 | 5 | 0.122 miles | NJR GROUP INC | STATE FUNDED | Jake R. Koltiska | 7042185125 | 2025-03-05 | 2025-11-03 | 2026-10-09 | 2026-10-16 | 19.15% | 19.15% | 2026-03-31 | 2026-04-09 09:10
DJ00549 | 10 | Stanly |  | None | SR-1258, US-52 | 3 SECTIONS OF US 52 AND 1 SECTION OF NEWT RD (SR 1258) | 1798603.42 | 3 | 3.73 miles | J T RUSSELL & SONS INC | STATE FUNDED | Bradley S. Eagle | 7049834380 | 2025-01-15 | 2026-01-07 | 2026-10-07 |  | 86.36% | 86.36% | 2026-04-30 | 2026-05-12 09:10
DJ00553 | 10 | Mecklenburg |  | None | NC-49 | 6 SECTIONS OF PRIMARY AND SECONDARY ROADS | 4063501.62 | 6 | 6.65 miles | BLYTHE BROTHERS ASPHALT CO LLC | STATE FUNDED | Michael W. Hedrick, PE | 9805230080 | 2025-04-02 | 2025-06-16 | 2026-11-05 |  | 46.32% | 46.32% | 2026-04-30 | 2026-05-14 09:10
DJ00554 | 10 | Cabarrus |  | None | SR-1146, SR-1147, SR-1430, SR-1621, SR-1706, SR-1947 | 8 SECONDARY ROADS IN VARIOUS LOCATIONS | 3224113.78 | 1 | 7.43 miles | NJR GROUP INC | STATE FUNDED | Bradley S. Eagle | 7049834380 | 2025-03-05 | 2025-06-24 | 2026-10-07 |  | 2.91% | 2.91% | 2025-10-23 | 2025-11-03 09:10
DJ00556 | 10 | Anson, Union | BO-2410C | None | US-52 | VARIOUS | 431010 | 6 | 0 miles | EAST CONSTRUCTION COMPANY LLC | 5093905 | Jake R. Koltiska | 7042185125 | 2025-03-19 | 2025-05-14 | 2026-03-09 |  | 89.34% | 89.34% | 2026-03-31 | 2026-04-15 08:10
DJ00557 | 10 | Union |  | None | SR-3489 | 25 SECTIONS OF VARIOUS SECONDARY ROADS | 3966059.65 | 4 | 11.52 miles | TRUEROCK CONSTRUCTION LLC | STATE FUNDED | Jake R. Koltiska | 7042185125 | 2025-02-19 | 2026-01-08 | 2026-10-23 | 2026-11-12 | 27.37% | 27.37% | 2026-04-30 | 2026-05-11 09:10
DJ00559 | 10 | Union |  | None | SR-1525, SR-1533, SR-1534, SR-1547 | 10 SECTIONS OF VARIOUS SECONDARY ROADS | 3269300.35 | 8 | 11.78 miles | TRUEROCK CONSTRUCTION LLC | STATE FUNDED | Jake R. Koltiska | 7042185125 | 2025-03-19 | 2025-07-10 | 2026-10-30 |  | 80% | 80% | 2026-03-31 | 2026-04-06 08:10
DJ00560 | 10 | Cabarrus |  | None | SR-1132, SR-1430 | 7 SECTIONS OF SECONDARY ROADS | 3314770.58 | 6 | 11.62 miles | J T RUSSELL & SONS INC | STATE FUNDED | Bradley S. Eagle | 7049834380 | 2025-03-19 | 2025-10-01 | 2026-10-13 | 2026-10-20 | 70.3% | 70.3% | 2026-04-30 | 2026-05-08 09:10
DJ00561 | 10 | Cabarrus | HL-0157 |  | I-85 | I-85 AND GEORGE LILES PARKWAY (SR 1430) INTERCHANGE | 0 |  | 0.64 miles | TRAFFIC CONTROL DEVICES LLC | 5169801 | Bradley S. Eagle | 7049834380 | 2025-09-17 | 2026-03-30 | 2026-10-30 |  | 0% | 0%
DJ00567 | 10 | Union | BP10-C009 | Subregional | SR-2131 | REPLACEMENT OF STRUCTURE 890402 OVER BRANCH OF RICHARDSON CR EEK ON SR 2131 (TROY MEDLIN ROAD) | 642126.16 | 5 | 0.099 miles | SMITH-ROWE, LLC | STATE FUNDED | Jake R. Koltiska | 7042185125 | 2025-06-18 | 2025-08-12 | 2027-01-13 | 2027-01-17 | 90.38% | 90.38% | 2026-01-31 | 2026-02-11 08:10
DJ00570 | 10 | Mecklenburg | HS-2010E | Regional | NC-49 | INTERSECTION OF SOUTH TRYON ST (NC 49) & GENERAL DRIVE & INT ERSECTION OF SOUTH TRYON ST (NC 49) & NEVADA BLVD (SR 1347) | 1246430.1 | 6 | 0.08 miles | LITTLE MOUNTAIN BUILDERS OF CATAWBA COUNTY LLC | 0049040 | Yanwei Ma | 7048475006 | 2025-06-18 | 2025-08-18 | 2026-04-17 | 2026-07-02 | 83.73% | 83.73% | 2026-04-30 | 2026-05-15 08:10
DJ00571 | 10 | Cabarrus | BP10-C011 | Subregional | SR-1524 | REPLACEMENT OF CULVERT ON SR-1524 (N. SCALYBARK TRAIL) | 1369251.85 | 3 | 0.061 miles | NJR GROUP INC | STATE FUNDED | Michael W. Hedrick, PE | 9805230080 | 2025-10-01 | 2025-11-03 | 2026-11-02 |  | 50.37% | 50.37% | 2026-04-30 | 2026-05-08 09:10
DJ00574 | 10 | Union | U-5703B | Statewide | US-74 | INTERSECTION OF US 74, JAMES HAMILTON RD AND SR 1514 (ROCKY RIVER RD) AT MYERS RD | 2188674.1 | 8 | 0.56 miles | EFFICIENT DEVELOPMENTS LLC | STATE FUNDED | Jake R. Koltiska | 7042185125 | 2025-08-20 | 2025-09-22 | 2026-10-23 | 2027-01-09 | 76.28% | 76.28% | 2026-04-30 | 2026-05-07 10:10
DJ00575 | 10 | Stanly | EB-5857 | Regional | NC-200 | NC 200 FROM N. LOVE CHAPEL RD. TO CARMEL RD. IN STANFIELD | 992101.4 | 4 | 0.89 miles | TRUEROCK CONSTRUCTION LLC | 0200413 | Bradley S. Eagle | 7049834380 | 2025-09-17 | 2025-12-10 | 2026-12-31 | 2027-02-20 | 56.08% | 56.08% | 2026-04-30 | 2026-05-11 09:10
DJ00576 | 10 | Mecklenburg |  |  | - | 16 SECTIONS OF VARIOUS SECONDARY ROUTES | 0 |  | 2.99 miles | PAVEMENT TECHNOLOGY INC | STATE FUNDED | Michael W. Hedrick, PE | 9805230080 | 2025-12-17 | 2026-06-01 | 2026-12-29 |  | 0% | 0%
DJ00577 | 10 | Union | SM-6110F | Statewide | US-74 | INTERSECTION OF US HWY 74 AND HAYES ROAD (SR 1379) | 1392692.83 | 3 | 0.21 miles | NJR GROUP INC | STATE FUNDED | Jake R. Koltiska | 7042185125 | 2025-08-20 | 2025-10-19 | 2026-06-17 | 2026-06-28 | 91.42% | 91.42% | 2026-01-31 | 2026-02-17 09:10
DJ00578 | 10 | Stanly |  |  | -, SR-1100, SR-1145, SR-1943, SR-2026 | 15 SECONDARY ROUTES AT VARIOUS LOCATIONS | 0 |  | 21.15 miles | CAROLINA ROAD SOLUTIONS LLC | STATE FUNDED | Bradley S. Eagle | 7049834380 | 2025-10-15 |  | 2027-04-15 |  | 0% | 0%
DJ00579 | 10 | Anson |  |  | - | 15 SECONDARY ROUTES AT VARIOUS LOCATIONS | 0 |  | 21.45 miles | CAROLINA ROAD SOLUTIONS LLC | STATE FUNDED | Jake R. Koltiska | 7042185125 | 2025-10-01 |  | 2027-04-15 |  | 0% | 0%
DJ00580 | 10 | Anson |  |  | -, NC-742, SR-1138, US-74 | NC 742, 2 SECTIONS OF US 74 AND 2 SECONDARY ROADS | 0 |  | 10.14 miles | BARNHILL CONTRACTING CO | STATE FUNDED | Jake R. Koltiska | 7042185125 | 2025-10-01 |  | 2027-04-01 |  | 0% | 0%
DJ00581 | 10 | Stanly | R-2530BA | Regional | NC-2427 | NC 24/27 | 31636 | 1 | 4.4 miles | HICKORY SEALING AND STRIPING INC | STATE FUNDED | Bradley S. Eagle | 7049834380 | 2025-12-17 | 2026-03-24 | 2026-06-01 |  | 44.57% | 44.57% | 2026-03-31 | 2026-04-02 08:10
DJ00582 | 10 | Stanly |  | None | SR-2625 | 1 SECTION OF US 52, 2 SECTIONS OF NC 740 AND 6 SECONDARY ROU TES | 3288964.43 | 1 | 12.33 miles | J T RUSSELL & SONS INC | STATE FUNDED | Bradley S. Eagle | 7049834380 | 2025-11-05 | 2026-04-20 | 2027-05-17 |  | 12.04% | 12.04% | 2026-04-30 | 2026-05-08 09:10
DJ00583 | 10 | Cabarrus | BP10-R047 |  | - | SR 2408 (GOLD HILL ROAD) OVER DUTCH BUFFALO CREEK | 0 |  | 0.267 miles | NJR GROUP INC | STATE FUNDED | Bradley S. Eagle | 7049834380 | 2025-11-05 | 2025-12-15 | 2027-06-15 |  | 0% | 0%
DJ00584 | 10 | Cabarrus |  |  | -, NC-73, SR-1006 | NC 24/27, 2 SECTIONS OF NC 73 AND 4 SECONDARY ROUTES | 0 |  | 11.44 miles | NJR GROUP INC | STATE FUNDED | Bradley S. Eagle | 7049834380 | 2025-12-03 |  | 2027-06-07 |  | 0% | 0%
DJ00585 | 10 | Cabarrus | BP10-R055 | Subregional | SR-2625 | BRIDGE NO. 120292 OVER LITTLE MEADOW CREEK ON SR-2625 (MAUNE Y RD.) | 799491.7 | 3 | 0.077 miles | EASTERN STRUCTURES LLC | STATE FUNDED | Bradley S. Eagle | 7049834380 | 2025-12-03 | 2026-02-11 | 2027-01-12 |  | 58.91% | 58.91% | 2026-04-30 | 2026-05-05 08:10
DJ00588 | 10 | Mecklenburg |  |  | - | US 521 AND VARIOUS SECONDARY ROADS | 0 |  | 9.02 miles | KING ASPHALT INC | STATE FUNDED | Michael W. Hedrick, PE | 9805230080 | 2026-03-18 |  | 2027-09-18 |  | 0% | 0%
DJ00590 | 10 | Cabarrus |  |  | -, NC-73, SR-1507, SR-1622, SR-2000 | 2 SECTIONS OF US 29, 3 SECTIONS OF NC 73 AND 3 SECTIONS OF S ECONDARY ROADS | 0 |  | 9.63 miles | NJR GROUP INC | STATE FUNDED | Bradley S. Eagle | 7049834380 | 2026-03-18 |  | 2027-09-18 |  | 0% | 0%
DJ00591 | 10 | Stanly | BP10-R021 |  | SR-1954 | REPLACE BRIDGE NO. 830095 OVER LITTLE CREEK ON SR 1954 (OLD AQUADALE ROAD) | 0 |  | 0.082 miles | NJR GROUP INC | STATE FUNDED | Bradley S. Eagle | 7049834380 | 2026-03-18 |  | 2027-07-27 |  | 0% | 0%
DK00260 | 11 | Ashe |  | Subregional | SR-1339 | SR 1339 (ROARING BRANCH ROAD) FROM SR 1340 (WEST MILL CREEK ROAD) TO SR 1332 (JACK JONES ROAD) | 2035868.5 | 29 | 0.77 miles | PADCO EXCAVATING INC | STATE FUNDED | Christopher S. Pipes | 3369039170 | 2023-04-20 | 2023-08-04 | 2025-04-15 | 2026-03-20 | 73.73% | 73.73% | 2026-04-15 | 2026-04-23 08:10
DK00329 | 11 | Watauga | R-2566BB | Regional | NC-105 | SR 1568 (OLD SHULLS MILL ROAD) FROM NC 105 TO WEST OF SR 155 7 (SHULLS MILL ROAD) | 1692370.93 | 6 | 0.321 miles | TRI-COUNTY PAVING INC |  | Lance K. Byrd, PE | 8282686022 | 2025-06-19 | 2025-09-02 | 2026-12-03 |  | 88.83% | 88.83% | 2026-04-30 | 2026-05-04 10:54
DK00332 | 11 | Watauga |  | Subregional | SR-1137 | SR 1137 (JUSTUS RD) FROM END OF PAVEMENT TO END OF MAINTENAN CE | 3404887.56 | 38 | 1.29 miles | PADCO EXCAVATING INC | STATE FUNDED | Lance K. Byrd, PE | 8282686022 | 2022-06-16 | 2022-07-28 | 2024-07-31 | 2027-09-22 | 93.75% | 93.75% | 2026-03-06 | 2026-04-07 09:10
DK00345 | 11 | Watauga |  | Subregional | SR-1227, SR-1233 | BRIDGE #94008 ON SR 1227 (NORTH FORK ROAD) AND CULVERT #9423 07 ON SR 1233 OVER NORTH FORK CREEK | 2299945.37 | 15 | 0.125 miles | IKECO CONSTRUCTION INC | STATE FUNDED | Lance K. Byrd, PE | 8282686022 | 2023-11-16 | 2024-03-04 | 2026-03-29 | 2026-10-03 | 48.25% | 48.25% | 2026-04-14 | 2026-04-27 08:10
DK00371 | 11 | Caldwell |  | Statewide | US-321- | 3 SECTIONS OF PRIMARY ROUTES IN CALDWELL COUNTY | 1130300 | 3 | 3.99 miles | MAYMEAD INC | STATE FUNDED | Lance K. Byrd, PE | 8282686022 | 2023-10-19 | 2024-07-01 | 2025-12-01 |  | 88.02% | 88.02% | 2024-12-31 | 2025-03-04 07:10
DK00372 | 11 | Caldwell |  | Subregional | SR-1106 | 10 SECTIONS OF SECONDARY ROADS IN CALDWELL COUNTY | 2817903.93 | 6 | 12.48 miles | MAYMEAD INC | STATE FUNDED | Lance K. Byrd, PE | 8282686022 | 2023-10-19 | 2024-02-22 | 2025-12-01 |  | 72.41% | 72.41% | 2024-12-31 | 2025-03-04 07:10
DK00375 | 11 | Avery, Caldwell, Watauga |  | Subregional | SR-VARI | 30 SECTIONS OF SECONDARY ROUTES | 1673695.38 | 4 | 29.17 miles | MAYMEAD INC | STATE FUNDED | Lance K. Byrd, PE | 8282686022 | 2024-02-15 | 2024-07-09 | 2024-10-01 |  | 89.73% | 89.73% | 2025-01-31 | 2025-06-25 08:10
DK00377 | 11 | Avery |  | None | SR-VAR | 7 SECTIONS OF SECONDARY ROUTES IN AVERY COUNTY | 2196489.45 | 6 | 9.16 miles | MAYMEAD INC | STATE FUNDED | Lance K. Byrd, PE | 8282686022 | 2024-03-21 | 2024-07-15 | 2025-12-01 |  | 93.77% | 93.77% | 2026-03-31 | 2026-04-10 09:10
DK00378 | 11 | Watauga |  | Subregional | SR-VARI | 7 SECTIONS OF SECONDARY ROUTES IN WATAUGA COUNTY | 2798000.48 | 5 | 10.3 miles | MAYMEAD INC | STATE FUNDED | Lance K. Byrd, PE | 8282686022 | 2024-03-21 | 2024-07-12 | 2025-12-01 |  | 92.35% | 92.35% | 2025-10-31 | 2026-03-10 09:10
DK00389 | 11 | Watauga |  | Subregional | SR-1351 | REPLACE BRIDGE 940089 ON SR 1351 (CASTLE FORD ROAD) OVER SOU TH FORK NEW RIVER | 1753651.47 | 11 | 0.085 miles | SMITH-ROWE, LLC | STATE FUNDED | Lance K. Byrd, PE | 8282686022 | 2023-12-07 | 2024-03-27 | 2025-04-17 | 2026-04-21 | 56.36% | 56.36% | 2026-04-30 | 2026-05-19 08:10
DK00391 | 11 | Surry | R-5910 | Statewide | US-21 | INTERSECTION OF US 21 BUSINESS (NORTH BRIDGE STREET) & NC 26 8 (CC CAMP ROAD) | 1973823.62 | 13 | 145.145 miles | SMITH-ROWE, LLC | 0021036 | Benjamin D. Whitaker | 3368354241 | 2023-12-07 | 2025-02-14 | 2025-10-11 | 2026-10-16 | 91.79% | 91.79% | 2026-03-31 | 2026-04-17 09:10
DK00396 | 11 | Alleghany |  | Regional | NC-18 | 1 SECTION OF NC 18 | 1398811.4 | 3 | 6.15 miles | MAYMEAD INC | STATE FUNDED | Benjamin D. Whitaker | 3368354241 | 2024-09-19 | 2025-03-17 | 2026-12-01 |  | 80.02% | 80.02% | 2026-04-30 | 2026-05-08 09:10
DK00399 | 11 | Caldwell |  |  | US-321 | 6 SECTIONS OF PRIMARY ROUTES IN CALDWELL COUNTY | 0 |  | 8.58 miles | MAYMEAD INC | STATE FUNDED | Lance K. Byrd, PE | 8282686022 | 2024-10-17 |  | 2026-12-01 |  | 0% | 0%
DK00401 | 11 | Caldwell |  |  | US-VARI | 7 SECTIONS OF SECONDARY ROUTES IN CALDWELL COUNTY | 0 |  | 5.63 miles | J T RUSSELL & SONS INC | STATE FUNDED | Lance K. Byrd, PE | 8282686022 | 2024-10-17 |  | 2026-12-01 |  | 0% | 0%
DK00403 | 11 | Alleghany, Caldwell, Surry, Wilkes |  | Subregional | SR-VARI | 30 SECTIONS OF PRIMARY AND SECONDARY ROUTES IN ALLEGHANY, CA LDWELL, SURRY, AND WILKES COUNTY | 1856190.61 | 3 | 23.06 miles | SLURRY PAVERS INC |  | Christopher S. Pipes | 3369039170 | 2025-04-17 | 2025-10-07 | 2026-11-01 |  | 83.4% | 83.4% | 2026-04-30 | 2026-05-08 09:10
DK00404 | 11 | Yadkin |  |  | US-421 | US 421 IN YADKIN COUNTY | 0 |  | 8.93 miles | MAYMEAD INC DBA CARL ROSE & SONS PAVING LLC | STATE FUNDED | Benjamin D. Whitaker | 3368354241 | 2025-01-16 |  | 2026-12-01 |  | 0% | 0%
DK00405 | 11 | Surry |  |  | - | 4 SECTIONS OF NC 268 IN SURRY COUNTY | 0 |  | 0 miles | MAYMEAD INC DBA CARL ROSE & SONS PAVING LLC | STATE FUNDED | Benjamin D. Whitaker | 3368354241 | 2024-01-16 |  | 2026-12-01 |  | 0% | 0%
DK00406 | 11 | Surry |  | Subregional | SR-VARI | 5 SECTIONS OF SECONDARY ROUTES IN SURRY COUNTY | 2482743.85 | 1 | 0 miles | MAYMEAD INC DBA CARL ROSE & SONS PAVING LLC | STATE FUNDED | Benjamin D. Whitaker | 3368354241 | 2024-01-16 | 2025-07-30 | 2026-12-01 |  | 6.4% | 6.4% | 2025-07-31 | 2025-08-18 09:10
DK00407 | 11 | Avery |  | Subregional | SR-1370 | SR 1370 (AVERY COUNTY HIGH SCHOOL ROAD) | 24925 | 1 | 0.1 miles | MORETZ PAVING INC | HELENE | Lance K. Byrd, PE | 8282686022 | 2024-10-22 | 2024-10-24 | 2024-10-30 |  | 83.8% | 83.8% | 2024-10-30 | 2025-03-27 08:10
DK00409 | 11 | Ashe |  |  | - | 1 SECTION OF NC 163 AND 6 SECTIONS OF SECONDARY ROUTES IN AS HE COUNTY | 0 |  | 7.64 miles | MAYMEAD INC | STATE FUNDED | Christopher S. Pipes | 3369039170 | 2025-03-20 | 2026-03-15 | 2026-12-01 |  | 0% | 0%
DK00410 | 11 | Avery, Watauga |  |  | US-VARI | 1 PRIMARY ROUTE AND 6 SECONDARY ROUTES IN AVERY AND WATAUGA COUNTY | 0 |  | 6.54 miles | MAYMEAD INC | STATE FUNDED | Lance K. Byrd, PE | 8282686022 | 2025-03-20 |  | 2026-12-01 |  | 0% | 0%
DK00411 | 11 | Watauga |  | Subregional | SR-VARI | 3 SECTIONS OF PRIMARY ROUTES AND 4 SECTIONS OF SECONDARY ROU TES IN WATAUGA COUNTY | 2906200.48 | 6 | 6.31 miles | MAYMEAD INC | STATE FUNDED | Lance K. Byrd, PE | 8282686022 | 2025-03-20 | 2025-05-22 | 2026-12-01 |  | 63.73% | 63.73% | 2025-12-31 | 2026-03-09 09:10
DK00412 | 11 | Wilkes |  |  | NC-16 | 8 SECTIONS OF PRIMARY ROUTES IN WILKES COUNTY | 0 |  | 0 miles | MAYMEAD INC DBA CARL ROSE & SONS PAVING LLC |  | Christopher S. Pipes | 3369039170 | 2025-04-17 | 2026-03-15 | 2026-12-01 |  | 0% | 0%
DK00413 | 11 | Wilkes |  | Subregional | SR-VARI | 8 SECTIONS OF SECONDARY ROUTES IN WILKES COUNTY | 2495230.66 | 4 | 11.41 miles | MAYMEAD INC DBA CARL ROSE & SONS PAVING LLC |  | Christopher S. Pipes | 3369039170 | 2025-04-17 | 2025-11-07 | 2026-12-01 |  | 66.79% | 66.79% | 2026-04-15 | 2026-04-21 09:10
DK00414 | 11 | Yadkin |  | Subregional | SR-VARI | 12 SECTIONS OF SECONDARY ROUTES IN YADKIN COUNTY | 2797416 | 3 | 9.99 miles | MAYMEAD INC DBA CARL ROSE & SONS PAVING LLC |  | Benjamin D. Whitaker | 3368354241 | 2025-04-17 | 2026-02-15 | 2026-12-01 |  | 12.34% | 12.34% | 2026-04-30 | 2026-05-06 09:10
DK00415 | 11 | Ashe, Avery, Caldwell, Watauga |  | Subregional | SR-VARI | 71 SECTIONS OF SECONDARY ROUTES IN ASHE, AVERY, CALDWELL AND WATAUGA COUNTY | 1971028.45 | 6 | 29.48 miles | MAYMEAD INC | STATE FUNDED | Lance K. Byrd, PE | 8282686022 | 2025-03-20 | 2025-05-01 | 2025-11-01 |  | 88.36% | 88.36% | 2025-11-01 | 2026-03-10 09:10
DK00416 | 11 | Ashe |  | Subregional | SR-1552 | BRIDGE 040121 ON SR 1552 (WILLIE BROWN ROAD) | 2650763.38 | 12 | 0 miles | JAMES R VANNOY & SONS CONSTRUCTION COMPANY INC | HELENE | Lance K. Byrd, PE | 8282686022 | 2025-01-09 | 2025-02-03 | 2026-10-27 | 2026-11-01 | 92.21% | 92.21% | 2026-02-28 | 2026-03-10 09:10
DK00420 | 11 | Avery, Watauga |  | Regional | NC-105, | STRUCTURE BP-006-2064 ON NC 184 AND STRUCTURE 940738 ON NC 1 05 | 5119502 | 7 | 0 miles | BLYTHE DEVELOPMENT LLC | HELENE | Lance K. Byrd, PE | 8282686022 | 2025-01-23 | 2025-03-03 | 2026-11-30 |  | 21% | 21% | 2026-04-30 | 2026-05-19 08:10
DK00421 | 11 | Watauga |  | Subregional | SR-1214 | BRIDGE 940095, BRIDGE 940178, BRIDGE 940258 | 4097197 | 13 | 0 miles | R E BURNS & SONS CO INC | DF18311.2095276.PR | Lance K. Byrd, PE | 8282686022 | 2025-01-23 | 2025-03-03 | 2026-12-31 | 2027-01-02 | 47.37% | 47.37% | 2026-04-15 | 2026-04-23 08:10
DK00423 | 11 | Watauga |  | Subregional | SR-1541 | SR 1541 (PAYNE BRANCH ROAD) FROM SR 1547 0.81 MILES | 3496628.02 | 13 | 0.81 miles | JAMES R VANNOY & SONS CONSTRUCTION COMPANY INC | STATE FUNDED | Lance K. Byrd, PE | 8282686022 | 2025-02-20 | 2025-03-26 | 2027-03-25 | 2027-03-27 | 88.46% | 88.46% | 2026-04-30 | 2026-05-04 10:54
DK00424 | 11 | Avery | B-5835 | Subregional | SR-1306 | REPLACE BRIDGE NO. 125 OVER ELK RIVER ON SR 1306 (HICKS HOLL OW ROAD) | 1934650.87 | 5 | 0.064 miles | JAMES R VANNOY & SONS CONSTRUCTION COMPANY INC | 4578801 | Lance K. Byrd, PE | 8282686022 | 2025-10-16 | 2025-12-01 | 2027-11-01 |  | 47.33% | 47.33% | 2026-04-30 | 2026-05-07 10:10
DK00425 | 11 | Ashe |  | Regional | NC-88 | SLOPE FAILURE REPAIR ON NC 88 IN ASHE COUNTY | 481000 | 5 | 0.1 miles | GALLIHER GRADING CORPORATION |  | Christopher S. Pipes | 3369039170 | 2025-03-20 | 2025-08-04 | 2026-04-30 |  | 58.1% | 58.1% | 2026-03-31 | 2026-04-14 15:19
DK00427 | 11 | Wilkes |  | Subregional | SR-1952 | REPLACEMENT OF BRIDGE 960280 OVER CAMP BRANCH ON SR 1952 (OA K RIDGE CHURCH ROAD) | 1581659.05 | 7 | 0.133 miles | SMITH-ROWE, LLC |  | Christopher S. Pipes | 3369039170 | 2025-06-19 | 2025-09-30 | 2026-12-31 | 2027-01-01 | 68.05% | 68.05% | 2026-04-15 | 2026-04-22 08:10
DK00428 | 11 | Wilkes |  | Subregional | SR-1363 | BRIDGE 960110 OVER NORTH PRONG LEWIS FORK CREEK ON SR 1363 ( WALSH ROAD) | 1629751.51 | 1 | 0.028 miles | SMITH-ROWE, LLC |  | Christopher S. Pipes | 3369039170 | 2025-07-17 | 2025-10-17 | 2027-02-24 |  | 6.73% | 6.73% | 2026-04-30 | 2026-05-11 09:10
DK00430 | 11 | Ashe | HB-0048 |  | - | BRIDGE 343 ON SR 1606 (DOUBLE SPRINGS CHURCH ROAD) OVER CRAN BERRY CREEK | 0 |  | 0.046 miles | MBI BUILDERS, LLC | FBRG111 | Benjamin D. Whitaker | 3368354241 | 2026-04-16 |  | 2027-05-17 |  | 0% | 0%
DK00431 | 11 | Ashe |  | Subregional | SR-1169 | BRIDGE #040156 OVER W. FORK PINE SWAMP ON SR 1163 (PINE SWAM P ROAD) | 2022817.69 | 3 | 0.166 miles | SMITH-ROWE, LLC |  | Christopher S. Pipes | 3369039170 | 2025-09-18 | 2026-01-16 | 2027-04-20 |  | 29.76% | 29.76% | 2026-04-30 | 2026-05-11 09:10
DK00432 | 11 | Wilkes |  | Subregional | SR-1939 | WILKES 221 ON SR 1939 (BILLINGS HILL CHURCH ROAD) OVER SPARK S CREEK | 1483884.8 | 8 | 0.143 miles | EASTERN STRUCTURES LLC |  | Christopher S. Pipes | 3369039170 | 2025-07-17 | 2025-09-12 | 2027-02-23 |  | 41.14% | 41.14% | 2026-04-15 | 2026-04-23 08:10
DK00433 | 11 | Avery |  | Subregional | SR-1370 | STRUCTURE REPLACEMENT OF PIPE NO. 006-2255 ON SR 1370 (AVERY COUNTY HIGH SCHOOL ROAD) OVER KENTUCKY CREEK | 2531791.91 | 1 | 0.089 miles | JAMES R VANNOY & SONS CONSTRUCTION COMPANY INC |  | Lance K. Byrd, PE | 8282686022 | 2026-02-19 | 2026-04-20 | 2027-03-16 |  | 5.15% | 5.15% | 2026-04-30 | 2026-05-08 09:10
DK00434 | 11 | Watauga |  | Subregional | SR-1139 | BRIDGE #940058 OVER BEECH CREEK ON SR 1139 (KELLERSVILLE ROA D) | 2188031.6 | 7 | 0.045 miles | IKECO CONSTRUCTION INC |  | Lance K. Byrd, PE | 8282686022 | 2025-08-21 | 2025-10-02 | 2027-03-30 |  | 15.43% | 15.43% | 2026-04-30 | 2026-05-06 09:10
DK00435 | 11 | Watauga |  |  | SR-1339 | REPLACE BRIDGE 187 ON SR 1339 (HOPEWELL CHURCH ROAD) OVER ME AT CAMP CREEK | 0 |  | 0.028 miles | BELUCA LLC |  | Lance K. Byrd, PE | 8282686022 | 2026-03-19 | 2026-05-07 | 2027-04-21 |  | 0% | 0%
DK00436 | 11 | Caldwell |  | Subregional | SR-1358 | REPLACE BRIDGE NO. 161 ON SR 1358 (EDGEMONT CHURCH PL) OVER WILSON CREEK | 1641926.67 | 1 | 0.11 miles | JAMES R VANNOY & SONS CONSTRUCTION COMPANY INC |  | Lance K. Byrd, PE | 8282686022 | 2025-12-18 | 2026-04-17 | 2027-04-05 | 2027-04-12 | 5.64% | 5.64% | 2026-04-30 | 2026-05-04 10:54
DK00437 | 11 | Watauga |  |  | SR-1113 | STRUCTURE #940322 ON SR 1113 (BAIRDS CREEK ROAD) OVER UPPER LAUREL FORK CREEK | 0 |  | 0.047 miles | JAMES R VANNOY & SONS CONSTRUCTION COMPANY INC |  | Lance K. Byrd, PE | 8282686022 | 2025-11-20 |  |  |  | 0% | 0%
DK00438 | 11 | Avery |  |  | - | REPLACE BRIDGE #050030 ON SR 1321 (CURTIS CREEK ROAD) OVER C URTIS CREEK | 0 |  | 0.069 miles | TRIANGLE GRADING & PAVING INC |  | Lance K. Byrd, PE | 8282686022 | 2026-02-19 | 2026-04-29 | 2027-04-13 |  | 0% | 0%
DK00439 | 11 | Ashe |  | Subregional | SR-1577 | CULVERT # BP-005-2831 ON SR 1577 (JAKE BLACKBURN ROAD) OVER LITTLE PHOENIX CREEK | 1558044.49 | 3 | 0.05 miles | JAMES R VANNOY & SONS CONSTRUCTION COMPANY INC |  | Christopher S. Pipes | 3369039170 | 2025-12-18 | 2026-02-17 | 2027-05-17 |  | 38.24% | 38.24% | 2026-05-15
DK00440 | 11 | Watauga |  |  | - | BRIDGE 940023 OVER BEAVERDAM CREEK ON SR 1211 (PHILLIPS BRAN CH ROAD) | 0 |  | 0.052 miles | WHALEY CONSTRUCTION LLC |  | Lance K. Byrd, PE | 8282686022 | 2026-03-19 | 2026-05-18 | 2027-06-09 |  | 0% | 0%
DK00441 | 11 | Ashe |  | Subregional | SR-1317 | REPLACE BRIDGE NO. 262 ON SR 1317 (RICH HILL ROAD) | 1081810.07 | 2 | 0.031 miles | JAMES R VANNOY & SONS CONSTRUCTION COMPANY INC |  | Christopher S. Pipes | 3369039170 | 2025-11-20 | 2026-03-11 | 2027-04-06 |  | 29.96% | 29.96% | 2026-04-30 | 2026-05-07 10:10
DK00442 | 11 | Yadkin | HN-0028 | Subregional | SR-1711 | ROUNDABOUTS ON SR 1711 (SPEER BRIDGE ROAD) AT US 421 INTERCH ANGE | 1396620.75 | 9 | 0.121 miles | TRIANGLE GRADING & PAVING INC | 5145801 | Benjamin D. Whitaker | 3368354241 | 2025-06-19 | 2025-08-18 | 2026-12-31 |  | 66.72% | 66.72% | 2026-04-30 | 2026-05-12 09:10
DK00444 | 11 | Watauga |  |  | US-221 | 1 SECTION OF US 221/US 421 AND 4 SECTIONS OF SECONDARY ROUTE S IN WATAUGA COUNTY | 0 |  | 0 miles | MAYMEAD INC | STATE FUNDED | Lance K. Byrd, PE | 8282686022 | 2025-09-18 | 2026-03-04 | 2027-04-21 |  | 0% | 0%
DK00445 | 11 | Alleghany, Surry, Yadkin |  |  | SR-VARI | 39 SECTIONS OF SECONDARY ROUTES IN DISTRICT 1 | 0 |  | 41.64 miles | CAROLINA ROAD SOLUTIONS LLC | STATE FUNDED | Benjamin D. Whitaker | 3368354241 | 2025-11-20 | 2026-05-15 | 2026-10-01 |  | 0% | 0%
DK00446 | 11 | Wilkes |  |  | US-421 | 11 SECTIONS OF PRIMARY ROUTES IN WILKES COUNTY | 0 |  | 0 miles | MAYMEAD INC | STATE FUNDED | Christopher S. Pipes | 3369039170 | 2025-10-16 |  | 2027-06-01 |  | 0% | 0%
DK00447 | 11 | Wilkes |  |  | SR-1325 | 8 SECTIONS OF SECONDARY ROUTES IN WILKES COUNTY | 0 |  | 0 miles | MAYMEAD INC | STATE FUNDED | Christopher S. Pipes | 3369039170 | 2025-10-16 |  | 2027-06-01 |  | 0% | 0%
DK00448 | 11 | Yadkin |  |  | US-421 | 2 SECTIONS OF US 421, 4 SECTIONS OF US 421 RAMPS, AND 2 SECT IONS OF SECONDARY ROUTES IN YADKIN COUNTY | 0 |  | 26.8 miles | MAYMEAD INC | STATE FUNDED | Benjamin D. Whitaker | 3368354241 | 2025-11-20 |  | 2027-05-20 |  | 0% | 0%
DK00449 | 11 | Alleghany |  |  | NC-18 | 1 SECTION OF PRIMARY ROUTE AND 3 SECTIONS OF SECONDARY ROUTE S IN ALLEGHANY COUNTY | 0 |  | 5.38 miles | MAYMEAD INC | STATE FUNDED | Benjamin D. Whitaker | 3368354241 | 2025-11-20 |  | 2027-05-20 |  | 0% | 0%
DK00450 | 11 | Avery |  |  | SR-VARI | 13 SECTIONS OF SECONDARY ROUTES IN AVERY COUNTY | 0 |  | 6.059 miles | MAYMEAD INC |  | Lance K. Byrd, PE | 8282686022 | 2026-03-19 |  | 2027-10-20 |  | 0% | 0%
DK00453 | 11 | Ashe |  |  | - | REPLACE BRIDGE NO. 040474 ON SR 1193 (LEWIS ROAD) OVER BUFFA LO CREEK | 0 |  | 0.072 miles | JAMES R VANNOY & SONS CONSTRUCTION COMPANY INC |  | Christopher S. Pipes | 3369039170 | 2026-02-19 | 2026-05-08 | 2027-04-07 |  | 0% | 0%
DK00461 | 11 | Wilkes |  |  | NC-115 | NORTH WILKESBORO | 0 |  | 0 miles | LOCKE LANE CONSTRUCTION INC |  | Christopher S. Pipes | 3369039170 | 2026-03-05 |  | 2026-12-31 |  | 0% | 0%
DK00463 | 11 | Ashe |  |  | SR-VARI | 18 SECTIONS OF SECONDARY ROUTES IN ASHE COUNTY | 0 |  | 13.15 miles | MAYMEAD INC | STATE FUNDED | Christopher S. Pipes | 3369039170 | 2026-02-19 |  | 2027-09-20 |  | 0% | 0%
DK00464 | 11 | Ashe, Wilkes |  |  | SR-VARI | 69 SECTIONS OF SECONDARY ROUTES IN ASHE AND WILKES COUNTIES | 0 |  | 31.85 miles | MAYMEAD INC | STATE FUNDED | Christopher S. Pipes | 3369039170 | 2026-02-19 | 2026-05-04 | 2026-10-01 |  | 0% | 0%
DK00465 | 11 | Ashe | HB-0051 |  | SR-1159 | BRIDGE #040466 OVER SOUTH FORK NEW RIVER ON SR 1159 (BOGGS R OAD) | 0 |  | 0.094 miles | JAMES R VANNOY & SONS CONSTRUCTION COMPANY INC | FBRG111 | Lance K. Byrd, PE | 8282686022 | 2026-04-16 |  | 2028-03-20 |  | 0% | 0%
DK00468 | 11 | Avery, Caldwell, Watauga |  |  | SR-1126 | 32 SECTIONS OF SECONDARY ROUTES | 0 |  | 23.41 miles | MAYMEAD INC | STATE FUNDED | Lance K. Byrd, PE | 8282686022 | 2026-01-15 | 2026-04-01 | 2026-10-01 |  | 0% | 0%
DK00469 | 11 | Caldwell |  |  | US-VARI | 8 SECTIONS OF PRIMARY AND SECONDARY ROUTES IN CALDWELL COUNT Y | 0 |  | 10.15 miles | MAYMEAD INC |  | Lance K. Byrd, PE | 8282686022 | 2026-03-19 |  | 2027-10-20 |  | 0% | 0%
DK00470 | 11 | Surry |  |  | US-601 | 1 SECTION OF US 601 N. (ROCKFORD STREET) IN SURRY COUNTY | 0 |  | 3.85 miles | MAYMEAD INC | STATE FUNDED | Benjamin D. Whitaker | 3368354241 | 2026-04-16 |  | 2027-11-16 |  | 0% | 0%
DK00471 | 11 | Surry |  |  | SR-VARI | 18 SECTIONS OF SECONDARY ROUTES IN SURRY COUNTY | 0 |  | 16.67 miles | MAYMEAD INC | STATE FUNDED | Benjamin D. Whitaker | 3368354241 | 2026-04-16 |  | 2027-11-16 |  | 0% | 0%
DK00474 | 11 | Wilkes | HS-2411G |  | US-421 | 2 SECTIONS OF US 421 IN WILKES COUNTY | 0 |  | 3.147 miles | MAYMEAD INC | 5098305 | Christopher S. Pipes | 3369039170 | 2026-03-19 |  | 2026-07-14 |  | 0% | 0%
DK00475 | 11 | Caldwell | HS-2411D |  | US-321 | 3 SECTIONS OF US 321 IN CALDWELL COUNTY | 0 |  | 8.19 miles | TRP CONSTRUCTION GROUP LLC | 5098304 | Lance K. Byrd, PE | 8282686022 | 2026-03-19 | 2026-05-19 | 2026-06-30 |  | 0% | 0%
DL00306 | 12 | Iredell | B-5394 | Subregional | SR-1832 | BRIDGE NO. 279 ON SR 1832 (EAGLE MILL RD) | 2707792.65 | 6 | 0.294 miles | EASTERN STRUCTURES LLC | STATE FUNDED | Justin T. Johnson | 7043806050 | 2025-09-23 | 2025-12-03 | 2027-10-15 |  | 30.29% | 30.29% | 2026-05-15
DL00338 | 12 | Alexander |  | Subregional | SR-1150 | SR 1108, SR 1110, SR 1150, SR 1235, SR 1409, SR 1422 | 2148174.15 | 7 | 13.174 miles | MAYMEAD INC | STATE FUNDED | Johnathan A. Barnette | 7048763947 | 2024-11-12 | 2025-03-27 | 2026-08-14 | 2026-08-15 | 57.84% | 57.84% | 2026-02-28 | 2026-03-12 08:10
DL00340 | 12 | Lincoln |  |  | NC-16 | NC 16 & 4 SECTIONS OF SECONDARY ROADS | 0 |  | 14.56 miles | BLYTHE CONSTRUCTION INC | STATE FUNDED | Travis R. Jordan | 7047482400 | 2024-11-26 |  | 2026-08-14 |  | 0% | 0%
DL00341 | 12 | Gaston |  | Regional | NC-279 | NC 279 & 4 SECTIONS OF SECONDARY ROADS | 3209568.8 | 4 | 9.34 miles | BLYTHE CONSTRUCTION INC | STATE FUNDED | Wesley S. Clary | 7044802080 | 2024-12-10 | 2025-10-06 | 2026-08-14 |  | 64.68% | 64.68% | 2026-03-31 | 2026-04-20 09:10
DL00342 | 12 | Gaston |  |  | - | VARIOUS SECONDARY ROUTES | 0 |  | 4.42 miles | ASPHALT PAVING OF SHELBY INC | STATE FUNDED | Wesley S. Clary | 7044802080 | 2025-02-25 | 2025-04-01 | 2026-08-28 |  | 0% | 0%
DL00346 | 12 | Cleveland, Gaston, Lincoln |  |  | SR-2142 | VARIOUS SECONDARY ROUTES | 0 |  | 11.89 miles | ASPHALT PAVING OF SHELBY INC | STATE FUNDED | Wesley S. Clary | 7044802080 | 2024-11-26 |  | 2026-06-19 |  | 0% | 0%
DL00348 | 12 | Iredell | U-5780, W-5601U | Regional | NC-150 | Intersection of NC 150 and SR 2399 Wiggins Rd, U-5780 and In tersection of NC 150 & NC 152, W-5601U | 3896135.33 | 7 | 0.2 miles | NJR GROUP INC | HSIP-150(38) | Justin T. Johnson | 7043806050 | 2025-03-25 | 2025-07-01 | 2026-12-14 |  | 51.15% | 51.15% | 2026-04-30 | 2026-05-06 09:10
DL00349 | 12 | Catawba |  | Subregional | SR-1139 | BRIDGE NO. 55 ON SR 1139 | 2273300 | 11 | 0.1 miles | R E BURNS & SONS CO INC | FEDERAL | Eric W. Conner | 8284686260 | 2025-02-25 | 2025-03-20 | 2027-10-01 | 2027-10-13 | 55.33% | 55.33% | 2026-04-20 | 2026-04-23 08:10
DL00351 | 12 | Lincoln | R-5712 | Regional | NC-16 | INTERSECTION OF NC 16 & SR 1439 / SR 1387 | 3940979 | 1 | 0.263 miles | KEMP SIGMON CONSTRUCTION CO INC | STATE FUNDED | Eric W. Conner | 8284686260 | 2025-06-24 | 2025-11-11 | 2027-04-30 |  | 1.1% | 1.1% | 2025-11-11 | 2025-11-14 09:10
DL00352 | 12 | Alexander | U-6041 | Statewide | US-64 | US 64/90 AT SR 1124 | 1498092.5 | 2 | 0.189 miles | SHAUN LACKEY EXCAVATING LLC | 4697901 | Justin T. Johnson | 7043806050 | 2025-06-24 | 2026-03-02 | 2026-12-01 |  | 27.16% | 27.16% | 2026-04-30 | 2026-05-11 09:10
DL00353 | 12 | Iredell |  | Subregional | SR-1512 | BRIDGE 254 ON SR 1512 | 1506516.1 | 9 | 0.092 miles | R E BURNS & SONS CO INC | STATE FUNDED | Justin T. Johnson | 7043806050 | 2025-07-22 | 2025-08-25 | 2027-03-01 |  | 89.11% | 89.11% | 2026-04-30 | 2026-05-07 10:10
DL00354 | 12 | Cleveland | W-5712A | Regional | NC-180 | INTERSECTION OF NC 180 & SR 2202 | 4990442.87 | 7 | 0.294 miles | SITE DEVELOPMENT CORPORATION | HSIP-0180(006) | Eric W. Conner | 8284686260 | 2025-07-08 | 2025-09-22 | 2027-05-14 | 2027-10-23 | 43.46% | 43.46% | 2026-04-22 | 2026-04-29 09:10
DL00356 | 12 | Alexander |  |  | SR-1337 | SR 1337, SR 1302, SR 1628, SR 1637 | 0 |  | 6.16 miles | MAYMEAD INC | STATE FUNDED | Johnathan A. Barnette | 7048763947 | 2025-08-12 |  | 2027-04-30 |  | 0% | 0%
DL00358 | 12 | Gaston |  |  | -, SR-1905, US-321 | VARIOUS PRIMARY & SECONDARY ROUTES | 0 |  | 8.4 miles | ASPHALT PAVING OF SHELBY INC | STATE FUNDED | Wesley S. Clary | 7044802080 | 2025-09-09 |  | 2027-04-30 |  | 0% | 0%
DL00359 | 12 | Lincoln |  |  | - | SR 1197 & SR 1371 | 0 |  | 4.87 miles | MAYMEAD INC | STATE FUNDED | Travis R. Jordan | 7047482400 | 2025-09-09 |  | 2027-04-30 |  | 0% | 0%
DL00360 | 12 | Catawba |  |  | SR-1003 | SR 1003, SR1833, SR 1885 | 0 |  | 10.54 miles | MAYMEAD INC | STATE FUNDED | Travis R. Jordan | 7047482400 | 2025-10-14 |  | 2027-05-19 |  | 0% | 0%
DL00361 | 12 | Iredell |  | Subregional | SR-1125 | 24 SECTIONS OF SECONDARY ROADS | 3247705.22 | 1 | 17.1 miles | MAYMEAD INC | STATE FUNDED | Johnathan A. Barnette | 7048763947 | 2025-10-14 | 2026-04-09 | 2027-05-19 |  | 5.87% | 5.87% | 2026-04-30 | 2026-05-11 09:10
DL00364 | 12 | Iredell | SM-5712C |  | NC-3 | NC 3 AT SR 1142 | 0 |  | 0.293 miles | NJR GROUP INC | STATE FUNDED | Justin T. Johnson | 7043806050 | 2025-11-25 |  | 2027-04-30 |  | 0% | 0%
DL00365 | 12 | Cleveland |  |  | -, SR-1325 | SR 1325 & SR 2221 | 0 |  | 5.72 miles | ASPHALT PAVING OF SHELBY INC | STATE FUNDED | Wesley S. Clary | 7044802080 | 2025-10-28 |  | 2026-12-02 |  | 0% | 0%
DL00366 | 12 | Gaston |  |  | - | SR 1918 & SR 1919 | 0 |  | 3.39 miles | BLYTHE CONSTRUCTION INC | STATE FUNDED | Wesley S. Clary | 7044802080 | 2025-10-28 | 2026-05-13 | 2026-12-02 |  | 0% | 0%
DL00367 | 12 | Alexander |  |  | NC-16 | NC 16, NC 127, SR 1348 | 0 |  | 13.19 miles | MAYMEAD INC | STATE FUNDED | Johnathan A. Barnette | 7048763947 | 2025-12-09 |  | 2027-07-17 |  | 0% | 0%
DL00368 | 12 | Catawba |  |  | - | VARIOUS SECONDARY ROADS | 0 |  | 22.39 miles | SLURRY PAVERS INC | STATE FUNDED | Travis R. Jordan | 7047482400 | 2026-01-13 |  | 2026-11-13 |  | 0% | 0%
DL00369 | 12 | Lincoln |  |  | NC-16 | NC 16 & 2 SECTIONS OF SECONDARY ROADS | 0 |  | 12.63 miles | MAYMEAD INC | STATE FUNDED | Travis R. Jordan | 7047482400 | 2025-11-25 |  | 2027-07-02 |  | 0% | 0%
DL00370 | 12 | Gaston |  |  | - | SR 1416, SR 2200, SR 2209, SR 2278, SR 2519 | 0 |  | 4.94 miles | ASPHALT PAVING OF SHELBY INC | STATE FUNDED | Wesley S. Clary | 7044802080 | 2025-12-09 |  | 2027-07-15 |  | 0% | 0%
DL00371 | 12 | Alexander, Catawba |  |  | SR-1328 | VARIOUS SECONDARY ROUTES | 0 |  | 6.73 miles | J T RUSSELL & SONS INC | STATE FUNDED | Travis R. Jordan | 7047482400 | 2026-03-10 |  | 2027-07-30 |  | 0% | 0%
DL00372 | 12 | Cleveland, Gaston |  |  | -, SR-1202, SR-1203, SR-1204, SR-1206, SR-1207, SR-1411, SR-1431, SR-1619, SR-2426, SR-2427 | VARIOUS SECONDARY ROADS | 0 |  | 21.64 miles | SLURRY PAVERS INC | STATE FUNDED | Wesley S. Clary | 7044802080 | 2026-02-10 |  | 2026-11-13 |  | 0% | 0%
DL00373 | 12 | Gaston |  |  | -, SR-1800, SR-1923, SR-2000, SR-2048 | NC 275 & 8 SECTIONS OF SECONDARY ROADS | 0 |  | 13.4 miles | BLYTHE CONSTRUCTION INC | STATE FUNDED | Wesley S. Clary | 7044802080 | 2026-02-24 |  | 2027-09-30 |  | 0% | 0%
DL00374 | 12 | Alexander, Iredell |  |  | SR-1515 | VARIOUS SECONDARY ROUTES | 0 |  | 30.846 miles | CAROLINA ROAD SOLUTIONS LLC | STATE FUNDED | Johnathan A. Barnette | 7048763947 | 2026-03-10 |  | 2026-11-13 |  | 0% | 0%
DL00377 | 12 | Cleveland |  | Subregional | SR-2017 | CULVERT NO 220043 CARRYING LITTLE PERSIMMON CREEK UNDER SR 2 017 | 688499.75 | 1 | 0.084 miles | SHAUN LACKEY EXCAVATING LLC | STATE FUNDED | Anne Burwell Schley, PE | 7044805580 | 2025-12-09 | 2026-03-30 | 2026-11-13 |  | 41.4% | 41.4% | 2026-04-30 | 2026-05-11 09:10
DL00380 | 12 | Cleveland |  |  | SR-1529 | BRIDGE 262 OVER BROAD RIVER ON SR 1529 | 0 |  | 0.274 miles | R E BURNS & SONS CO INC | HELENE | Eric W. Conner | 8284686260 | 2026-03-24 |  | 2027-10-29 |  | 0% | 0%
DM00387 | 13 | Burke | HA-0001 | None | - | NEW ACCESS ROAD INTO BURKE INDUSTRIAL PARK | 1741687.7 | 7 | 0 miles | CRW LAND SERVICES LLC | 1311019 | Travis J. Henley | 8286527848 | 2025-05-28 | 2025-10-21 | 2026-06-30 | 2026-07-30 | 88.54% | 88.54% | 2026-04-22 | 2026-05-18 08:10
DM00391 | 13 | Madison |  | Subregional | SR-1460 | BRIDGE 552 OVER BIG LAUREL CREEK ON SR-1460 (ACCESS RD) | 1337452.75 | 8 | 0.109 miles | BUCKEYE BRIDGE LLC | STATE FUNDED | Colby D. Justice | 8286589439 | 2025-07-16 | 2025-08-04 | 2027-04-13 | 2027-04-15 | 93.62% | 93.62% | 2026-04-30 | 2026-05-13 08:10
DM00393 | 13 | Buncombe | BP13-R013 |  | - | BRIDGE 100692 OVER ADKINS BRANCH ON SR-1768 (OLD BURNSVILLE RD) | 0 |  | 0.138 miles | R E BURNS & SONS CO INC | STATE FUNDED | Colby D. Justice | 8286589439 | 2026-02-18 | 2026-05-11 | 2027-11-10 |  | 0% | 0%
DM00403 | 13 | Rutherford |  | Subregional | SR-1576 | OVER PUZZLE CREEK ON SR-1576 (E. CHURCH ST) | 2235875 | 5 | 0.36 miles | KEMP SIGMON CONSTRUCTION CO INC | STATE FUNDED | Travis J. Henley | 8286527848 | 2025-10-15 | 2025-12-09 | 2027-05-03 |  | 73.63% | 73.63% | 2026-04-30 | 2026-05-12 09:10
DM00424 | 13 | Buncombe | U-3301WM | None | NC-63 | NC-63 EAST OF SR-1378 (OLD NEWFOUND RD) | 112090.61 | 21 | 0 miles | B H GRANING LANDSCAPES INC | STATE FUNDED | Thomas R. Veazey | 8282980080 | 2023-09-06 | 2024-01-22 | 2027-03-31 |  | 64.92% | 64.92% | 2026-02-15 | 2026-03-02 10:10
DM00428 | 13 | McDowell | BP13-R026 |  | - | BRIDGE 194 OVER LIMEKILN CREEK ON SR-1559 (GOOD ROAD) | 0 |  | 0.194 miles | ROCK CREEK GRADING LLC | STATE FUNDED | Travis J. Henley | 8286527848 | 2025-12-03 | 2026-02-16 | 2027-04-12 |  | 0% | 0%
DM00429 | 13 | Burke | BP13-R033 | Subregional | SR-1116 | SR-1116 (JEETER CARSWELL RD) OVER DOUBLE BRANCH | 882393.69 | 4 | 0.33 miles | R E BURNS & SONS CO INC | STATE FUNDED | Travis J. Henley | 8286527848 | 2025-11-19 | 2026-01-05 | 2027-04-30 |  | 91.88% | 91.88% | 2026-04-30 | 2026-05-13 08:10
DM00431 | 13 | Madison |  | Subregional | SR-1515 | OVER MIDDLEFORK CREEK ON SR-1515 (BUCKNER BRANCH RD) | 1355271.2 | 6 | 0 miles | BUCKEYE BRIDGE LLC | STATE FUNDED | Colby D. Justice | 8286589439 | 2025-10-01 | 2025-10-28 | 2027-04-23 |  | 46.63% | 46.63% | 2026-04-22 | 2026-05-04 10:54
DM00435 | 13 | Buncombe |  | None | -, NC-9, US-74A | VARIOUS PRIMARY AND SECONDARY ROUTES | 3578874.55 | 13 | 0 miles | BRYANTS LAND & DEVELOPMENT INDUSTRIES INC | STATE FUNDED | Thomas R. Veazey | 8282980080 | 2023-10-18 | 2024-03-04 | 2025-05-30 | 2025-11-26 | 93.23% | 93.23% | 2026-04-07 | 2026-04-21 09:10
DM00436 | 13 | Buncombe |  | None | US-19 | VARIOUS SECONDARY ROUTES | 2511240 | 10 | 0 miles | APAC ATLANTIC INC DBA HARRISON CONSTRUCTION COMPANY | STATE FUNDED | Thomas R. Veazey | 8282980080 | 2023-11-15 | 2024-06-24 | 2025-09-26 | 2025-10-17 | 91.83% | 91.83% | 2025-09-07 | 2025-09-17 08:10
DM00442 | 13 | Burke, Rutherford |  | None | - | VARIOUS SECONDARY ROUTES | 1851539.45 | 1 | 0 miles | EMERY SEALCO INC | STATE FUNDED | Travis R. Jordan | 7047482400 | 2024-03-06 | 2026-01-19 | 2025-11-21 | 2025-12-12 | 10.87% | 10.87% | 2026-02-15 | 2026-02-18 09:10
DM00449 | 13 | Burke | R-5967 | None | SR-1625 | SR-1625 (9TH AVE DR NW) | 3727604.2 | 19 | 0 miles | NEILL GRADING & CONSTRUCTION COMPANY INC | 1687001 | Eric W. Conner | 8284686260 | 2024-01-03 | 2024-05-06 | 2026-10-30 | 2026-11-25 | 66.26% | 66.26% | 2025-12-22 | 2025-12-31 08:10
DM00450 | 13 | Rutherford |  | None | US-221, US-221A | VARIOUS PRIMARY ROUTES | 2923111.33 | 3 | 0 miles | SITE DEVELOPMENT CORPORATION | STATE FUNDED | Travis J. Henley | 8286527848 | 2024-04-17 | 2024-08-23 | 2025-11-21 |  | 37.34% | 37.34% | 2026-05-07 | 2026-05-20 09:10
DM00451 | 13 | Madison |  | None | SR-1116, SR-1151, SR-1175, SR-1385, SR-1390, SR-1395, SR-1530, SR-1574 | VARIOUS SECONDARY ROUTES | 2634960.92 | 4 | 0 miles | APAC ATLANTIC INC DBA HARRISON CONSTRUCTION COMPANY | STATE FUNDED | Colby D. Justice | 8286589439 | 2024-07-03 | 2025-11-06 | 2026-05-15 |  | 94.55% | 94.55% | 2026-04-15 | 2026-04-28 09:10
DM00455 | 13 | Burke, Madison, McDowell, Rutherford |  | None | NC-108, NC-114, NC-126, NC-181, NC-208, NC-209, NC-226ALT, NC-9, SR-VAR, US-221 | VARIOUS PRIMARY AND SECONDARY ROUTES | 1481278.48 | 3 | 114.55 miles | PERFORMANCE SEALING & STRIPING LLC | 4933119 | Travis J. Henley | 8286527848 | 2024-08-07 | 2025-08-18 | 2025-09-26 |  | 47.54% | 47.54% | 2026-05-07
DM00458 | 13 | McDowell | BP13-R048 | Subregional | SR-1560 | OVER THE NORTH FORK OF THE CATAWBA RIVER ON SR-1560 (OLD LIN VILLE RD) | 1837544.59 | 1 | 0.128 miles | SMITH-ROWE, LLC | STATE FUNDED | Travis J. Henley | 8286527848 | 2025-11-19 | 2026-03-12 | 2027-11-12 |  | 9.01% | 9.01% | 2026-04-15 | 2026-04-24 08:10
DM00459 | 13 | Mitchell, Yancey |  | None | SR-1111, SR-1114, SR-1129, SR-1134, SR-1152, SR-1154, SR-1158, SR-1186, SR-1229, SR-1372, SR-1445 | VARIOUS SECONDARY ROUTES | 2447203.16 | 4 | 14.65 miles | MAYMEAD INC | STATE FUNDED | Colby D. Justice | 8286589439 | 2024-08-07 | 2025-07-22 | 2026-06-19 |  | 88.89% | 88.89% | 2025-11-15 | 2025-11-19 09:10
DM00461 | 13 | Madison, Yancey | 1, 2 | None | SR-1115, SR-1139, SR-1140, SR-1151, SR-1172, SR-1181, SR-1195, SR-1330, SR-1339, SR-1351, SR-1357, SR-1360, SR-1389, SR-1392, SR-1399, SR-1401, SR-1404, SR-1405, SR-1418, SR-1426, SR-1432, SR-1433, SR-1444, SR-1453, SR-1454, SR-1533, SR-1573, SR-1590, SR-1614, SR-1619 | VARIOUS SECONDARY ROUTES | 1344349.6 | 1 | 22.42 miles | EMERY SEALCO INC | STATE FUNDED | Colby D. Justice | 8286589439 | 2024-09-04 | 2026-02-19 | 2026-03-17 | 2027-05-28 | 29.89% | 29.89% | 2026-03-15 | 2026-03-19 09:10
DM00464 | 13 | Buncombe, Madison |  | None | SR-1224, US-25 | BRIDGE #100295 ON SR-1224 OVER I-40 IN BUNCOMBE COUNTY AND B RIDGE #560528 ON US 25/70 IN MADISON COUNTY | 3415392.6 | 4 | 0 miles | BUCKEYE BRIDGE LLC | STATE FUNDED | Colby D. Justice | 8286589439 | 2025-07-16 | 2025-12-10 | 2026-10-15 |  | 34.46% | 34.46% | 2026-05-07 | 2026-05-18 08:10
DM00466 | 13 | Burke, McDowell, Rutherford |  |  | - | VARIOUS SECONDARY ROUTES | 0 |  | 0 miles | MAYMEAD INC | STATE FUNDED | Travis J. Henley | 8286527848 | 2026-04-15 |  | 2027-09-03 |  | 0% | 0%
DM00474 | 13 | Buncombe | 1 | None | - | VARIOUS SECONDARY ROUTES | 2041597.4 | 5 | 0 miles | EMERY SEALCO INC | STATE FUNDED | Thomas R. Veazey | 8282980080 | 2025-04-16 | 2025-07-24 | 2026-09-04 |  | 59.57% | 59.57% | 2026-04-15 | 2026-04-24 08:10
DM00478 | 13 | Buncombe |  | Regional | NC-151 | BRIDGE 100086 ON NC 151 OVER STONY FORK CREEK | 849923.08 | 6 | 0.614 miles | TAG CONTRACTING INC | STATE FUNDED | Thomas R. Veazey | 8282980080 | 2025-05-21 | 2025-11-19 | 2026-10-01 |  | 52.31% | 52.31% | 2026-04-22 | 2026-04-27 08:10
DM00482 | 13 | McDowell |  |  | NC-80 | BRIDGES #79, 83, AND 23 OVER BUCK CREEK | 0 |  | 0 miles | ROCK CREEK GRADING LLC | HELENE | Travis J. Henley | 8286527848 | 2025-12-03 | 2026-03-17 | 2026-04-24 |  | 0% | 0%
DM00484 | 13 | McDowell |  | Statewide | I-40 | 1-40 WESTBOUND AT MILE MARKER 67.4 | 1386025.75 | 2 | 0 miles | YOUNG CONSTRUCTION COMPANY INC | HELENE | Travis J. Henley | 8286527848 | 2025-12-03 | 2026-02-16 | 2026-04-24 |  | 64.85% | 64.85% | 2026-04-15 | 2026-04-27 08:10
DM00486 | 13 | Yancey |  | Statewide | US-19 | BRIDGE #990009 OVER CANE RIVER ON US-19 | 518016 | 1 | 0 miles | ROCK CREEK GRADING LLC | HELENE | Colby D. Justice | 8286589439 | 2026-01-21 | 2026-04-01 | 2026-06-30 |  | 28.88% | 28.88% | 2026-04-15 | 2026-04-23 08:10
DM00494 | 13 | Buncombe |  | Regional | NC-9 | BRIDGE #100079 ON NC-9 OVER BROAD RIVER | 318995 | 1 | 0 miles | HOOPERS GRADING CO | HELENE | Thomas R. Veazey | 8282980080 | 2026-02-04 | 2026-03-13 | 2026-06-05 |  | 20.18% | 20.18% | 2026-03-31 | 2026-04-27 08:10
DM00495 | 13 | Buncombe |  |  | I-40 | CULVERT #100491 AND #100478 ON I-40 | 0 |  | 0 miles | MOUNTAIN CREEK CONTRACTORS INC | HELENE | Thomas R. Veazey | 8282980080 | 2026-03-04 | 2026-06-01 | 2026-07-13 |  | 0% | 0%
DM00497 | 13 | McDowell | HS-2413M | Statewide | US-221 | APPROXIMATELY 0.07 MILES NORTH OF SR 1153 MP 6.25 TO MP 32.8 2 ON US 221 IN MCDOWELL COUNTY | 357660.6 | 1 | 26.56 miles | BAGWELL FENCE COMPANY INC | 5098504 | Travis J. Henley | 8286527848 | 2025-12-17 | 2026-04-06 | 2026-09-30 | 2026-10-15 | 41.5% | 41.5% | 2026-04-15 | 2026-04-27 08:10
DM00499 | 13 | McDowell |  | Statewide | I-40 | I-40 WESTBOUND MM 68 | 3777122 | 1 | 0.072 miles | MCCALLS GRADING & CONSTRUCTION INC | HELENE | Travis J. Henley | 8286527848 | 2026-01-21 | 2026-03-30 | 2026-09-28 | 2026-10-15 | 14% | 14% | 2026-04-22 | 2026-05-06 09:10
DM00501 | 13 | McDowell |  |  | - | BRIDGE #580141 OVER MILL CREEK ON SR-1409 (PARIS CREEK RD) | 0 |  | 0.054 miles | MCCALLS GRADING & CONSTRUCTION INC | HELENE | Travis J. Henley | 8286527848 | 2026-03-18 |  | 2027-04-28 |  | 0% | 0%
DM00502 | 13 | Buncombe | HS-2413I | Subregional | SR-1002 | SR-1002 (OLD LEICSESTER HWY) FROM NC 63 TO SR-1607 (BEAR CRE EK RD) | 116516 | 1 | 1.953 miles | BULLINGTON CONSTRUCTION INC | 5098510 | Thomas R. Veazey | 8282980080 | 2026-03-04 | 2026-03-30 | 2026-07-24 |  | 69.97% | 69.97% | 2026-04-30 | 2026-05-11 09:10
DM00503 | 13 | Buncombe | HS-2413J | Subregional | SR-1727 | SR-1727 (MONTICELLO RD) FROM SR-1882 (NEW STOCK RD) TO NC-25 2 (OLD MARSHALL HWY) | 108521 | 1 | 1.22 miles | BULLINGTON CONSTRUCTION INC | 5098511 | Thomas R. Veazey | 8282980080 | 2026-03-04 | 2026-03-23 | 2026-07-24 |  | 90.43% | 90.43% | 2026-03-30 | 2026-05-06 09:10
DM00506 | 13 | McDowell |  |  | - | VARIOUS SECONDARY ROUTES | 0 |  | 10.55 miles | MAYMEAD INC | STATE FUNDED | Travis J. Henley | 8286527848 | 2026-04-01 |  | 2027-08-20 |  | 0% | 0%
DM00507 | 13 | Madison | TN-6128 |  | - | INTERSECTION OF US 25/70 AND US 25/70 BUS (IVY RIVER RD) | 0 |  | 0 miles | APAC ATLANTIC INC ASHEVILLE DIVISION | 5151901 | Colby D. Justice | 8286589439 | 2026-04-15 |  | 2027-05-28 |  | 0% | 0%
DN00474 | 14 | Macon |  | Subregional | SR-1001 | AT BRIDGE #231 OVER NORTH PRONG ELLIJAY CREEK ON SR 1001 (EL LIJAY RD) | 2390463 | 11 | 0.095 miles | BUCKEYE BRIDGE LLC | STATE FUNDED | J. Adam Dockery | 8283215061 | 2024-03-26 | 2024-05-09 | 2025-06-30 |  | 91.09% | 91.09% | 2025-07-15 | 2025-09-10 08:10
DN00586 | 14 | Polk | BP14-R006 | Subregional | SR-1138 | POLK BRIDGE 143 ON SR 1138 (LAKE ADGER ROAD) OVER PANTHER CR EEK | 2614433.48 | 4 | 0.16 miles | IPC PAVING LLC DBA IPC STRUCTURES LLC | STATE FUNDED | Michael D. Patton | 8285862141 | 2025-12-09 | 2026-01-19 | 2027-03-19 |  | 15.35% | 15.35% | 2026-05-07 | 2026-05-18 08:10
DN00780 | 14 | Cherokee |  | Statewide | US-19 | VARIOUS LOCATIONS THROUGHOUT CHEROKEE COUNTY | 3902733.01 | 14 | 7.637 miles | APAC ATLANTIC INC DBA HARRISON CONSTRUCTION COMPANY | STATE FUNDED | J. Adam Dockery | 8283215061 | 2022-04-26 | 2022-10-12 | 2026-07-01 |  | 73.99% | 73.99% | 2026-04-30 | 2026-05-08 09:10
DN01012 | 14 | Macon |  | Subregional | SR-VARI | ALONG VARIOUS SECONDARY ROUTES THROUGHOUT MACON COUNTY | 2126568.69 | 6 | 5.3 miles | APAC ATLANTIC INC DBA HARRISON CONSTRUCTION COMPANY | STATE FUNDED | J. Adam Dockery | 8283215061 | 2023-10-10 | 2024-07-03 | 2025-10-17 |  | 88.42% | 88.42% | 2025-10-23 | 2025-11-21 09:10
DN01014 | 14 | Henderson | R-5794N, R-5794O | Statewide | US-25 B | ALONG US 25 BUS S. FROM APPROXIMATELY 220 FEET SOUTH OF 9TH AVENUE WEST TO US 25 (S. MAIN ST.) | 1374354.37 | 10 | 0 miles | SITE DEVELOPMENT CORPORATION |  | Patrick A. Eubanks | 8288917911 | 2023-10-24 | 2024-04-30 | 2025-10-17 | 2025-12-14 | 83.93% | 83.93% | 2026-03-15 | 2026-03-26 00:10
DN01034 | 14 | Transylvania |  | Statewide | US-VARI | ALONG VARIOUS ROUTES THROUGHOUT TRANSYLVANIA COUNTY | 3586029.15 | 11 | 19.55 miles | APAC ATLANTIC INC DBA HARRISON CONSTRUCTION COMPANY | STATE FUNDED | Patrick A. Eubanks | 8288917911 | 2023-10-10 | 2024-03-25 | 2025-10-17 | 2025-11-21 | 90.87% | 90.87% | 2026-01-07 | 2026-01-16 09:10
DN01039 | 14 | Graham, Swain |  | Statewide | US-129 | VARIOUS PRIMARY AND SECONDARY ROUTES IN GRAHAM COUNTY AND VA RIOUS SECONDARY ROUTES IN SWAIN COUNTY | 3164304.01 | 7 | 9.48 miles | APAC ATLANTIC INC DBA HARRISON CONSTRUCTION COMPANY | STATE FUNDED | J. Adam Dockery | 8283215061 | 2023-11-14 | 2025-06-06 | 2025-10-17 | 2025-11-16 | 93.51% | 93.51% | 2026-04-30 | 2026-05-18 08:10
DN01048 | 14 | Macon |  | Subregional | SR-1533 | BRIDGE #204 OVER WALNUT CREEK ON SR 1533 (WALNUT CREEK RD) I N MACON COUNTY | 2187198 | 11 | 48.09 miles | BRYSON ENTERPRISES LTD DBA BRYSON GRADING & PAVING | STATE FUNDED | J. Adam Dockery | 8283215061 | 2025-03-25 | 2025-05-15 | 2026-12-15 | 2027-02-23 | 44.32% | 44.32% | 2026-05-07 | 2026-05-15 08:10
DN01051 | 14 | Henderson |  | Statewide | US-64, | ALONG VARIOUS PRIMARY ROUTES THROUGHOUT HENDERSON COUNTY | 1967840.5 | 6 | 4.24 miles | TARHEEL PAVING & ASPHALT COMPANY INC DBA TARHEEL PAVING & AS | STATE FUNDED | Patrick A. Eubanks | 8288917911 | 2024-05-28 | 2025-05-28 | 2025-10-17 | 2026-04-04 | 83.96% | 83.96% | 2026-04-30 | 2026-05-11 09:10
DN01057 | 14 | Jackson | W-5714E | Statewide | US-64 | US 64 APPROXIMATELY 0.8 MILE EAST OF SR 1119 (SAPPHIRE POST OFFICE RD.) AT "CHRYSLER CURVE" NEAR SAPPHIRE | 1416527 | 8 | 0.17 miles | MCCALLS GRADING & CONSTRUCTION INC | HSIP-0064(167) | Kenneth C. McCourt | 8284977333 | 2024-07-23 | 2025-02-25 | 2026-01-05 | 2026-08-01 | 59.79% | 59.79% | 2026-01-07 | 2026-01-14 09:10
DN01059 | 14 | Macon |  | Statewide | US-64 | ALONG U.S. 64 AND SR-1653 (HICKORY KNOLL RD) IN MACON COUNTY | 2970161.74 | 4 | 6.95 miles | PARKER PAVING COMPANY INC | STATE FUNDED | J. Adam Dockery | 8283215061 | 2025-01-14 | 2025-07-18 | 2026-10-16 |  | 52.68% | 52.68% | 2025-11-01 | 2026-04-06 08:10
DN01060 | 14 | Henderson |  | Subregional | SR-1586 | BRIDGE 440036 ON SR 1586 OVER CLEAR CREEK | 238873.6 | 1 | 0.01 miles | R E BURNS & SONS CO INC | STATE FUNDED | Patrick A. Eubanks | 8288917911 | 2024-08-13 | 2024-09-12 | 2025-05-15 |  | 12.23% | 12.23% | 2025-05-08 | 2025-05-12 09:10
DN01062 | 14 | Cherokee | HS-2014X | Statewide | US-64 | US HWY 64/74 AT INTERSECTION WITH NC HWY 60 | 789621 | 3 | 0.321 miles | COLWELL CONSTRUCTION COMPANY INC | 4933602 | J. Adam Dockery | 8283215061 | 2025-09-09 | 2026-01-30 | 2026-11-20 |  | 81.43% | 81.43% | 2026-04-30 | 2026-05-12 09:10
DN01066 | 14 | Transylvania |  |  | SR-1504 | ALONG SR-1504 (OLD HENDERSONVILLE HWY) IN TRANSYLVANIA COUNT Y | 0 |  | 3.96 miles | TARHEEL PAVING & ASPHALT COMPANY INC DBA TARHEEL PAVING & AS | STATE FUNDED | Patrick A. Eubanks | 8288917911 | 2025-01-14 | 2026-03-11 | 2026-10-16 |  | 0% | 0%
DN01067 | 14 | Henderson |  | Subregional | SR-1323 | BRIDGE #440015 OVER BOYLSTON CREEK ON SR 1323 (BRICKYARD RD) | 743030.9 | 5 | 0.152 miles | KEMP SIGMON CONSTRUCTION CO INC | STATE FUNDED | Patrick A. Eubanks | 8288917911 | 2024-12-10 | 2025-01-09 | 2026-03-27 |  | 88.23% | 88.23% | 2025-10-07 | 2025-10-29 08:10
DN01069 | 14 | Clay | HF-0005 | Subregional | SR-1140 | BRIDGE NO. 63 OVER BLAIR CREEK AND BRIDGE NO. 88 OVER HYATT MILL CREEK ON SR 1140 (MYERS CHAPEL ROAD | 3590980.67 | 14 | 0.274 miles | IKECO CONSTRUCTION INC | 1140018 | J. Adam Dockery | 8283215061 | 2025-02-11 | 2025-03-24 | 2027-03-30 | 2027-04-01 | 77.76% | 77.76% | 2026-04-30 | 2026-05-11 09:10
DN01071 | 14 | Graham, Swain | HF-0007 |  | NC-28 | ALONG NC-28 IN SWAIN COUNTY AND ALONG SR-1246 / WELCH RD AND SR-1286 / TSALI RD IN GRAHAM COUNTY | 0 |  | 10.39 miles | SITE DEVELOPMENT CORPORATION | STATE FUNDED | J. Adam Dockery | 8283215061 | 2024-12-10 |  | 2026-10-16 |  | 0% | 0%
DN01075 | 14 | Henderson |  | Statewide | US-176 | AT VARIOUS LOCATIONS ALONG US-176 IN HENDERSON COUNTY | 1525057.93 | 7 | 2.87 miles | SITE DEVELOPMENT CORPORATION | HELENE | Patrick A. Eubanks | 8288917911 | 2025-01-28 | 2025-03-25 | 2026-03-27 | 2026-06-19 | 70.17% | 70.17% | 2026-04-15 | 2026-04-23 08:10
DN01082 | 14 | Haywood | HB-0023 | Subregional | SR-1876 | AT BRIDGE #430170 SR 1876 (SONOMA RD) & #430169 SR 1105 (MAX THOMPSON RD) OVER WEST & EAST FORKS OF PIGEON RIVER | 4189737.43 | 7 | 0.202 miles | WHALEY CONSTRUCTION LLC | 5034501 | Kenneth C. McCourt | 8284977333 | 2025-06-24 | 2025-07-23 | 2027-04-16 | 2027-04-23 | 37.44% | 37.44% | 2026-04-15 | 2026-04-22 08:10
DN01083 | 14 | Henderson |  | Subregional | SR-1508 | ALONG VARIOUS SECONDARY ROUTES THROUGHOUT HENDERSON COUNTY | 2656091.63 | 6 | 14.55 miles | TARHEEL PAVING & ASPHALT COMPANY INC DBA TARHEEL PAVING & AS | STATE FUNDED | Patrick A. Eubanks | 8288917911 | 2025-01-14 | 2025-05-28 | 2026-10-16 |  | 42.95% | 42.95% | 2025-11-15 | 2025-11-25 08:10
DN01085 | 14 | Henderson |  | Subregional | SR-1171 | ALONG SR-1171 (FINLEY COVE RD) MP 5.5 TO MP 5.58 AND ALONG S R-2155 (HEBRON RD) FROM MP 0.2 TO MP 0.28 | 1169651.35 | 5 | 0.16 miles | ADAMS CONTRACTING CO INC | HELENE | Patrick A. Eubanks | 8288917911 | 2025-01-28 | 2025-03-03 | 2026-03-27 | 2026-04-15 | 90.26% | 90.26% | 2025-10-15 | 2025-10-23 09:10
DN01087 | 14 | Haywood, Jackson, Macon |  | Subregional | SR-1305 | ALONG VARIOUS SECONDARY ROUTES THROUGHOUT HAYWOOD, JACKSON, AND MACON COUNTIES | 1956494.1 | 3 | 37.65 miles | EMERY SEALCO INC | STATE FUNDED | Kenneth C. McCourt | 8284977333 | 2025-02-11 | 2025-09-09 | 2025-10-16 |  | 47.97% | 47.97% | 2025-11-30 | 2025-12-04 09:10
DN01088 | 14 | Henderson |  | Subregional | SR-1836 | AT VARIOUS LOCATIONS ALONG SR-1836 (POT SHOALS RD) IN HENDER SON COUNTY | 2748969.51 | 7 | 0.78 miles | SITE DEVELOPMENT CORPORATION | HELENE | Patrick A. Eubanks | 8288917911 | 2025-02-11 | 2025-03-27 | 2026-03-11 |  | 61.81% | 61.81% | 2026-04-30 | 2026-05-11 09:10
DN01089 | 14 | Transylvania |  | Subregional | SR-VARI | ALONG VARIOUS SECONDARY ROUTES THROUGHOUT TRANSYLVANIA COUNT Y | 1524770 | 9 | 1.9 miles | MCCALLS GRADING & CONSTRUCTION INC | HELENE | Patrick A. Eubanks | 8288917911 | 2025-01-28 | 2025-04-14 | 2026-09-25 | 2026-09-30 | 73.04% | 73.04% | 2026-04-22 | 2026-05-14 09:10
DN01090 | 14 | Transylvania |  | Subregional | SR-1538 | ALONG SR-1538 (BECKY MOUNTAIN RD) FROM MP 0.7 TO MP 0.76 IN TRANSYLVANIA CO. | 2358769.02 | 5 | 0.06 miles | ECLIPSE COMPANIES LLC | HELENE | Patrick A. Eubanks | 8288917911 | 2025-03-11 | 2025-07-21 | 2026-04-04 | 2026-04-23 | 61.26% | 61.26% | 2025-12-25 | 2026-02-13 08:10
DN01091 | 14 | Henderson, Transylvania |  | Subregional | SR-1201 | ALONG ONE ROUTE IN HENDERSON CO AND ALONG VARIOUS ROUTES IN TRANSYLVANIA CO | 3497428.42 | 9 | 0.39 miles | ADAMS CONTRACTING CO INC | HELENE | Patrick A. Eubanks | 8288917911 | 2025-04-08 | 2025-05-29 | 2026-05-07 | 2026-08-25 | 62.27% | 62.27% | 2026-05-15 | 2026-05-20 09:10
DN01092 | 14 | Transylvania |  | Statewide | US-276 | ALONG VARIOUS ROUTES THROUGHOUT TRANSYLVANIA COUNTY | 1949741 | 6 | 0.22 miles | MCCALLS GRADING & CONSTRUCTION INC | HELENE | Patrick A. Eubanks | 8288917911 | 2025-03-25 | 2025-07-10 | 2026-10-23 | 2027-01-15 | 85.25% | 85.25% | 2026-05-13 | 2026-05-15 08:10
DN01095 | 14 | Henderson, Transylvania |  | Subregional | SR-1528 | AT BRIDGES # 440245 & # 440186 IN HENDERSON, & # 870066 IN T RANSYLVANIA | 4736550 | 12 | 0.224 miles | KEMP SIGMON CONSTRUCTION CO INC | HELENE | Patrick A. Eubanks | 8288917911 | 2024-12-17 | 2025-01-03 | 2026-09-25 | 2026-10-23 | 16.44% | 16.44% | 2026-04-30 | 2026-05-18 08:10
DN01096 | 14 | Henderson |  | Subregional | SR-1602 | AT VARIOUS LOCATIONS ALONG SR-1602 (GRANT MOUNTAIN RD) | 769529.2 | 6 | 0.36 miles | CRW LAND SERVICES LLC | HELENE | Michael D. Patton | 8285862141 | 2025-03-25 | 2025-09-05 | 2026-04-24 | 2027-01-22 | 61.57% | 61.57% | 2026-05-07 | 2026-05-15 08:10
DN01097 | 14 | Transylvania |  | Regional | NC-280 | ALONG VARIOUS SEGMENTS OF NC-280 | 2197663.4 | 1 | 4.83 miles | BRYANTS LAND & DEVELOPMENT INDUSTRIES INC | STATE FUNDED | Patrick A. Eubanks | 8288917911 | 2025-03-25 | 2026-03-30 | 2026-10-16 |  | 4.03% | 4.03% | 2026-04-15 | 2026-04-23 08:10
DN01098 | 14 | Haywood |  | Subregional | SR-1364 | BRIDGE 46 ON SR 1364 (COLEMAN MOUNTAIN ROAD) OVER JONATHAN C REEK | 1594381.25 | 7 | 0.155 miles | MOUNTAIN CREEK CONTRACTORS INC | HELENE | Kenneth C. McCourt | 8284977333 | 2025-08-12 | 2025-11-10 | 2027-03-13 | 2027-05-22 | 23.62% | 23.62% | 2026-05-07 | 2026-05-13 08:10
DN01100 | 14 | Henderson |  | Subregional | SR-1574 | AT HENDERSON BRIDGE 38 ON SR-1574 (FRUITLAND ROAD) | 791426.5 | 5 | 0.05 miles | MICHAEL W NORVILLE DBA BLUE RIDGE GRADING & EXCAVATING | HELENE | Michael D. Patton | 8285862141 | 2025-03-11 | 2025-04-30 | 2026-01-12 | 2026-01-12 | 47.24% | 47.24% | 2025-10-22 | 2025-11-26 08:10
DN01101 | 14 | Henderson |  | Subregional | SR-1572 | BRIDGE # 63 ALONG SR-1572 (APPLE VALLEY ROAD) BETWEEN MP 1.0 40 AND MP 1.060 IN HENDERSON COUNTY | 348650.3 | 4 | 0.02 miles | MICHAEL W NORVILLE DBA BLUE RIDGE GRADING & EXCAVATING | HELENE | Michael D. Patton | 8285862141 | 2025-03-11 | 2025-04-30 | 2026-01-12 |  | 74.11% | 74.11% | 2025-08-22 | 2025-09-16 09:10
DN01102 | 14 | Cherokee, Clay, Jackson, Macon, Swain | HS-2414J, HS-2414K, HS-2414L, HS-2414M | Statewide | US-19, | ALONG VARIOUS ROUTES ACROSS JACKSON, SWAIN, MACON, CHEROKEE, AND CLAY COUNTIES | 1273862.5 | 2 | 114.71 miles | BULLINGTON CONSTRUCTION INC | 5098610 | Jesse 'Andy' Russell | 8283215061 | 2025-08-26 | 2026-02-24 | 2027-03-22 |  | 64.75% | 64.75% | 2026-04-15 | 2026-05-04 10:54
DN01106 | 14 | Cherokee, Clay, Graham, Swain |  | Subregional | SR-SR-1 | ALONG VARIOUS SECONDARY ROUTES THROUGHOUT CHEROKEE, CLAY, GR AHAM, AND SWAIN | 1344887.48 | 5 | 27.14 miles | RUSSELL STANDARD CORPORATION DBA RUSSELL STANDARD | STATE FUNDED | J. Adam Dockery | 8283215061 | 2025-03-25 | 2025-04-30 | 2025-10-16 |  | 88.33% | 88.33% | 2025-09-30 | 2025-10-22 08:10
DN01107 | 14 | Haywood |  | Subregional | SR-1646 | ALONG VARIOUS ROUTES THROUGHOUT HAYWOOD COUNTY | 1550457.32 | 2 | 8.7 miles | WNC PAVING INC | STATE FUNDED | Kenneth C. McCourt | 8284977333 | 2025-04-08 | 2025-05-15 | 2026-10-16 |  | 13.51% | 13.51% | 2025-06-30 | 2025-07-09 08:10
DN01108 | 14 | Jackson | BO-2414 | Statewide | US-19 | AT VARIOUS LOCATIONS ALONG PRIMARY AND SECONDARY ROUTES IN J ACKSON COUNTY | 1948163.2 | 1 | 13.12 miles | APAC ATLANTIC INC ASHEVILLE DIVISION | STATE FUNDED | Kenneth C. McCourt | 8284977333 | 2025-04-22 | 2025-07-15 | 2026-10-16 |  | 4.57% | 4.57% | 2025-07-31 | 2025-08-18 09:10
DN01109 | 14 | Polk |  |  | NC-108 | ALONG NC-108 AND ALONG VARIOUS SECONDARY ROUTES IN POLK COUN TY | 0 |  | 5.98 miles | JLS COMPANY LLC | STATE FUNDED | Patrick A. Eubanks | 8288917911 | 2025-04-22 |  | 2026-10-16 |  | 0% | 0%
DN01111 | 14 | Transylvania |  |  | - | ALONG NC-281 FROM SR 1307 TO BRIDGE 74 | 0 |  | 1.66 miles | APAC ATLANTIC INC ASHEVILLE DIVISION | STATE FUNDED | Patrick A. Eubanks | 8288917911 | 2025-05-13 |  | 2026-10-16 |  | 0% | 0%
DN01112 | 14 | Polk |  | Regional | NC-9 | BRIDGE 29 OVER SOUTH BRANCH LITTLE WHITE OAK CREEK ON NC 9 | 3856784.22 | 8 | 0.319 miles | KEMP SIGMON CONSTRUCTION CO INC | STATE FUNDED | Michael D. Patton | 8285862141 | 2025-08-26 | 2025-09-22 | 2027-05-14 |  | 64.32% | 64.32% | 2026-05-07 | 2026-05-14 09:10
DN01116 | 14 | Transylvania |  | Statewide | US-64 | ALONG U.S.-64 AND ALONG N.C.-215 IN TRANSYLVANIA COUNTY | 3075885.65 | 3 | 0.11 miles | ECLIPSE COMPANIES LLC | HELENE | Patrick A. Eubanks | 8288917911 | 2025-05-27 | 2025-09-03 | 2026-06-26 |  | 62.63% | 62.63% | 2025-11-22 | 2025-12-18 09:10
DN01119 | 14 | Polk |  | Subregional | SR-1179 | BRIDGE 740112 OVER PACOLET RIVER ON SR 1179 (EDNEY ROAD) | 1691888.75 | 1 | 0.057 miles | KEMP SIGMON CONSTRUCTION CO INC | HELENE | Michael D. Patton | 8285862141 | 2026-01-13 | 2026-02-13 | 2027-03-05 |  | 2.99% | 2.99% | 2026-03-31 | 2026-04-07 09:10
DN01121 | 14 | Henderson |  | Subregional | SR-1586 | BRIDGE NO. 440036 ON SR 1586 (SOUTH MILLS GAP ROAD) OVER CLE AR CREEK | 1187916.7 | 5 | 0.149 miles | R E BURNS & SONS CO INC | HELENE | Michael D. Patton | 8285862141 | 2025-07-22 | 2025-08-28 | 2026-09-11 |  | 93.27% | 93.27% | 2026-01-31 | 2026-02-03 08:10
DN01122 | 14 | Henderson |  | Subregional | SR-1605 | AT VAROUS SITES ALONG SR 1605 (MIDDLE FORK ROAD/TOM FALLS RO AD) | 13121389.2 | 7 | 2.77 miles | WRIGHT BROTHERS CONSTRUCTION COMPANY INC | HELENE | Michael D. Patton | 8285862141 | 2025-07-22 | 2025-09-11 | 2027-12-28 |  | 10.75% | 10.75% | 2026-04-22 | 2026-05-06 09:10
DN01123 | 14 | Henderson |  | Subregional | SR-1605 | AT VARIOUS SITES ALONG SR 1605 (MIDDLE FORK ROAD/TOM FALLS R OAD) | 12242865.6 | 7 | 1.274 miles | WRIGHT BROTHERS CONSTRUCTION COMPANY INC | HELENE | Michael D. Patton | 8285862141 | 2025-07-22 | 2025-09-11 | 2027-11-11 |  | 14.99% | 14.99% | 2026-04-22 | 2026-05-06 09:10
DN01125 | 14 | Cherokee, Clay, Graham |  |  | - | ALONG VARIOUS SECONDARY ROUTES IN CHEROKEE, CLAY, AND GRAHAM COUNTY | 0 |  | 29.97 miles | APAC ATLANTIC INC ASHEVILLE DIVISION | STATE FUNDED | J. Adam Dockery | 8283215061 | 2025-09-23 | 2026-04-14 | 2027-05-03 |  | 0% | 0%
DN01126 | 14 | Jackson |  | Statewide | US-64 | US HWY 64 NEAR STILLMONT CIRCLE NEAR CASHIERS IN JACKSON COU NTY | 687318.6 | 1 | 0.01 miles | MICHAEL W NORVILLE DBA BLUE RIDGE GRADING & EXCAVATING | HELENE | Kenneth C. McCourt | 8284977333 | 2025-10-14 | 2026-03-02 | 2026-11-14 |  | 48.36% | 48.36% | 2026-03-22 | 2026-03-31 09:10
DN01128 | 14 | Henderson |  | Subregional | SR-1170 | VARIOUS SITES ALONG SR 1710 (BALD ROCK ROAD) | 4942006.2 | 4 | 0.774 miles | SITE DEVELOPMENT CORPORATION | HELENE | Michael D. Patton | 8285862141 | 2025-09-23 | 2025-12-08 | 2028-02-28 | 2028-04-11 | 19.46% | 19.46% | 2026-04-15 | 2026-04-30 09:10
DN01129 | 14 | Macon | HB-0030 | Subregional | SR-1679 | BRIDGE NO. 550055 ON SR 1679 (PEEKS CREEK RD) OVER CULLASAJA RIVER | 2778223.2 | 3 | 0.095 miles | BUCKEYE BRIDGE LLC | 5064701 | J. Adam Dockery | 8283215061 | 2025-12-09 | 2026-01-19 | 2027-10-20 |  | 9.03% | 9.03% | 2026-04-22 | 2026-05-15 08:10
DN01130 | 14 | Polk |  | Subregional | SR-1102 | AT BRIDGE #740009 ON SR 1102 (PEARSON FALLS ROAD) OVER NORTH PACOLET RIVER | 4367998.75 | 1 | 0.109 miles | BUCKEYE BRIDGE LLC | STATE FUNDED | Michael D. Patton | 8285862141 | 2026-01-13 | 2026-03-05 | 2028-02-28 |  | 3.1% | 3.1% | 2026-03-31 | 2026-04-07 09:10
DN01131 | 14 | Graham |  | Regional | NC-28 | ALONG VARIOUS SEGMENTS OF NC 28 | 4759580.3 | 3 | 12.6 miles | WATSON CONTRACTING INC | STATE FUNDED | J. Adam Dockery | 8283215061 | 2025-10-14 | 2025-11-07 | 2026-11-14 |  | 60.6% | 60.6% | 2026-04-30 | 2026-05-08 09:10
DN01132 | 14 | Haywood, Jackson, Swain |  |  | SR-1947 | ALONG VARIOUS SECONDARY ROUTES THROUGHOUT HAYWOOD, JACKSON, AND SWAIN COUNTIES | 0 |  | 34.79 miles | EMERY SEALCO INC | STATE FUNDED | Kenneth C. McCourt | 8284977333 | 2025-10-28 |  | 2026-10-16 |  | 0% | 0%
DN01133 | 14 | Macon |  |  | US-64 | ALONG US-64 AND VARIOUS SECONDARY ROUTES THROUGHOUT MACON CO UNTY | 0 |  | 7.07 miles | APAC ATLANTIC INC ASHEVILLE DIVISION | STATE FUNDED | J. Adam Dockery | 8283215061 | 2026-02-10 |  | 2027-09-10 |  | 0% | 0%
DN01134 | 14 | Transylvania |  |  | US-64 | US-64 FROM SR 1135 TO SR 1329 & 3 SECTIONS OF SECONDARY ROAD S | 0 |  | 8.23 miles | APAC ATLANTIC INC ASHEVILLE DIVISION | STATE FUNDED | Patrick A. Eubanks | 8288917911 | 2026-01-27 |  | 2027-08-27 |  | 0% | 0%
DN01135 | 14 | Henderson |  | Subregional | SR-1594 | AT VARIOUS SITES ALONG SR 1594 & SR 1569 BEARWALLOW MOUNTAIN RD BETWEEN US74A AND OLD CLEAR CREEK RD | 5304216.37 | 2 | 1.556 miles | PRECISION PIPELINE LLC | HELENE | Michael D. Patton | 8285862141 | 2025-10-28 | 2026-01-19 | 2028-05-31 |  | 20.92% | 20.92% | 2026-04-07 | 2026-04-17 09:10
DN01136 | 14 | Swain | BO-2414A |  | US-19 | 2 SECTIONS OF US-19 AND 3 SECTIONS OF SECONDARY ROADS | 0 |  | 7.2 miles | THE HMC PAVING & CONSTRUCTION CO INC | STATE FUNDED | Kenneth C. McCourt | 8284977333 | 2026-02-10 |  | 2028-02-10 |  | 0% | 0%
DN01138 | 14 | Jackson, Swain | BO-2414, HS-2014, HS-2014AD, HS-2014Z | Subregional | SR-1337 | AT VARIOUS LOCATIONS IN SWAIN AND JACKSON COUNTIES | 222104.5 | 2 | 0.13 miles | LITTLE MOUNTAIN BUILDERS OF CATAWBA COUNTY LLC | 4933604 | W. Cody Weddle | 8284977333 | 2025-11-12 | 2026-02-09 | 2026-11-13 | 2026-11-27 | 61.4% | 61.4% | 2026-04-07 | 2026-04-28 09:10
DN01141 | 14 | Haywood | BO-2414D |  | US-19 | 3 SECTIONS OF US-19 | 0 |  | 7.74 miles | WNC PAVING INC | STATE FUNDED | Kenneth C. McCourt | 8284977333 | 2026-03-10 |  | 2028-04-10 |  | 0% | 0%
DN01143 | 14 | Polk |  | Statewide | US-176 | AT VARIOUS SITES ALONG US-176 AND SEVERAL SECONDARY ROUTES | 932061.63 | 1 | 0.162 miles | SHAUN LACKEY EXCAVATING LLC | HELENE | Michael D. Patton | 8285862141 | 2026-01-13 | 2026-03-03 | 2027-02-05 | 2027-02-07 | 23.5% | 23.5% | 2026-03-31 | 2026-04-30 09:10
DN01146 | 14 | Haywood |  | Subregional | SR-1357 | BRIDGE 430041 ON SR 1357 (CRABTREE CHURCH RD) OVER CRABTREE CREEK IN HAYWOOD COUNTY | 1094502.55 | 2 | 0.051 miles | KEMP SIGMON CONSTRUCTION CO INC | HELENE | Kenneth C. McCourt | 8284977333 | 2026-01-13 | 2026-03-03 | 2027-01-08 | 2027-01-29 | 37.25% | 37.25% | 2026-04-24 | 2026-05-08 09:10
DN01148 | 14 | Macon | B-6029 | Subregional | SR-1001 | BRIDGE #55009 OVER NORTH PRONG ELLIJAY CREEK ON SR 1001 (ELL IJAY RD) | 2092715.5 | 1 | 0.204 miles | HOOPERS GRADING CO | BRZ-1001(090) | J. Adam Dockery | 8283215061 | 2026-02-10 | 2026-03-05 | 2027-04-23 |  | 9.79% | 9.79% | 2026-04-15 | 2026-05-11 09:10
DN01149 | 14 | Haywood, Jackson |  |  | SR-VARI | 2 SECTIONS OF SECONDARY ROADS IN HAYWOOD COUNTY AND 4 SECTIO NS OF SECONDARY ROADS IN JACKSON COUNTY | 0 |  | 16.34 miles | PARKER PAVING COMPANY INC | STATE FUNDED | Kenneth C. McCourt | 8284977333 | 2026-03-24 |  | 2027-10-24 |  | 0% | 0%
DN01150 | 14 | Polk |  |  | SR-1142 | 3 SECTIONS OF SECONDARY ROADS | 0 |  | 3.29 miles | BRYANTS LAND & DEVELOPMENT INDUSTRIES INC | STATE FUNDED | Patrick A. Eubanks | 8288917911 | 2026-04-14 |  | 2027-11-14 |  | 0% | 0%
DN01152 | 14 | Polk |  |  | I-26 | POLK COUNTY WELCOME CENTER ON I-26 | 0 |  | 0 miles | CAROLINA SPECIALTIES CONSTRUCTION LLC | STATE FUNDED | Patrick A. Eubanks | 8288917911 | 2026-03-24 |  |  |  | 0% | 0%
DN01153 | 14 | Haywood |  |  | - | CULVERTS 430187, 430188, 430189 AND 430190 OVER MARTINS CREE K ON SR 1341 (MARTINS CREEK RD) | 0 |  | 100.295 miles | WHALEY CONSTRUCTION LLC | STATE FUNDED | Kenneth C. McCourt | 8284977333 | 2026-03-24 |  | 2029-04-27 |  | 0% | 0%